## Contract Summary
CONTRACT SUMMARY |  |  | Date: | 2025-03-01 |  | Week No: | 9 | Instructions
CONTRACT DETAILS
Client: |  | Nurus-Siraj Nigeria Limited
Name of Contract: |  | PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
Short Name: |  | 6TH BRIDGE OVER RIVER KADUNA
Original Contract Amount: |  | 4617148926.06 | NAIRA
Current Contract Amount: |  | 4617148926.06 | NAIRA | RETC: | No |  |  |  | 4617148926.06 |  | - Check to Detail Sheet
Contract Schedules
• | Date of Contract Award | 2020-11-14 |  | • Works Actually Commenced on Site:
• | Contract Commencement Date: | 2020-12-18
• | Original Contract Duration (Months): | 12 |  | • Duration Already on Site : |  |  | 0
• | Original Contract Completion Date: | 2021-12-18
• | Extension of Time Requested (Months): | 0 |  | • Overdue to Original completion Date: |  |  | -38.4329
• | Extension of Time Granted (Months): | 0
• | Revised Contract Duration (Months) | 12 |  | • Overdue to Revised completion Date: |  |  | -38.4329
• | Revised Completion Date: | 2021-12-18
VALUE OF WORKS TO DATE
CLIENT POSITION (INCL. VAT) - CERTIFICATES
• | Works Vetted & Certified - Payable to Contractor: | 1879930738.36 | 40.72% | [6 empty] | 0 | - Check to Detail Sheet
• | Works submitted and not yet vetted: | 0 | 0% | [6 empty] | 0 | - Check to Detail Sheet
• | Total value of works submitted: | 1879930738.36 | 40.72%
• | Add - Retention Money - Deducted | 203181862.5911
• | Deduct - Retention Money - Released | 0
• | Add -Total Advance Payment Recovered | 0
• | Total Gross Value of Works Completed & Certified: | 2083112600.9511 | 45.12% |  | #VALUE! | #VALUE!
#VALUE!
PW POSITION (INCL. VAT) - WEEKLY PROGRESS REPORTS
• | Add - Bill 1 | 0
• | Permanent Works Completed | 10158750 | 0.22%
• | Add - Contingencies | 25372651.1115
• | Total Value of Works Done | 35531401.1115 | 0.7696% |  | #VALUE! | #VALUE! |  |  |  | 0 | - Check to Detail Sheet
#VALUE!
Total Work in Progress |  | -2047581199.8396 | - Works Certified is greater than physical works Completed
PAYMENT STATUS
Payments Received to Date |  | Gross | Net Amount |  | % Cont. Value
Advance Payments |  | #VALUE! | #VALUE! |  | #VALUE!
Certficates Paid |  | #VALUE! | #VALUE! |  | #VALUE!
On Account |  | #VALUE! | #VALUE! |  | #VALUE!
Total Payments Received |  | #VALUE! | #VALUE! |  | #VALUE! |  |  |  |  | #VALUE! | - Check to Detail Sheet
Amounts Certified - Not Yet Paid |  | #VALUE!
Advance Payment Guarantee: |  | 1500000000 |  | APG Expiry: | 2018-03-27 | Days Expired: | -2531
Advance Payment Recovered (on submitted Certs): |  | 0 | #VALUE! | Renewal Exp:
Advance Payment yet to be recovered: |  | 1500000000 | #VALUE!
BILL 1
Total Bill 1 Requested by client to date: |  | 49933962 | Total Amount Claimed in Certs: |  |  | 23453874.2667
Total Paid out by PW to date: |  | 43357962 | Total Amount Paid by Client: |  |  | 0
Amount Outstanding from Amounts Requested: |  | 6576000 | Total Amount Outstanding to PW: |  |  | 23453874.2667
Note: All amounts are net of Service Charge: |  |  | Amount rec'd by PW - not paid out: |  |  | -43357962
COST & REVENUE SUMMARY
| Completed Works | BEME | Completed Previously |  | This Week | Project to Date | % Compl.
| CONCRETE APRON WORK | 4275137894.5 | 1350077912.0817 |  | 24311509.1345 | 1374389421.2162 | 32.15%
| Total Contingency (Incl. VAT) | 342011031.56 | 0 |  | 0 | 0 | 0%
| Tota Completed Works to Date (Incl VAT) | 4617148926.06 | 1350077912.0817 |  | 24311509.1345 | 1374389421.2162 | 29.77%
| Total Costs to Date |  | 1063288085.1496 |  | 18112042.4583 | 1081400127.6079
Net Earnings - Excluding Bill 1 |  |  | 286789826.9321 |  | 6199466.6762 | 292989293.6083
% Net Earnings |  |  | 21.24% |  | 25.5% | 21.32%
FINANCIAL INFORMATION
|  | Previous Week | This Week |  | Movement
Creditors Balance |  |  |  |  | 0
Bank & Cash Funds Available |  |  |  |  | 0

## Weekly Summary
WEEKLY WORK SUMMARY |  |  | Date: | 2025-03-01 | Week No: | 9 | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
Works Completed |  | BEME | Completed Previously | This Week | Project to Date | % Compl.
CONCRETE APRON WORK
• | Bill 1 | 35500000 | 0 | 0 | 0 | 0%
• | Excavation and Piling | 595098800 | 400446445.2 | 0 | 400446445.2 | 67.29%
• | Pile cap, Pier, Pier caps and Abutment | 953352380 | 304856084.4302 | 4771872 | 309627956.4302 | 32.48%
• | Superstructure | 2095531280 | 550583900.2132 | 17843485.3344 | 568427385.5476 | 27.13%
• | Pavement | 0 | 0 | 0 | 0 | 0%
• | Miscellanous | 297390000 | 0 | 0 | 0 | 0%
SUB-TOTAL |  | 3976872460 | 1255886429.8435 | 22615357.3344 | 1278501787.1779 | 32.15%
Add VAT & State Levies - 7.5% |  | 298265434.5 | 94191482.2383 | 1696151.8001 | 95887634.0383
Total Works Completed (Incl. VAT) |  | 4275137894.5 | 1350077912.0817 | 24311509.1345 | 1374389421.2162 | 32.15%
Contingency |  | 318149796.8 | 0 | 0 | 0 | 0%
Add VAT & State Levies - 7.5% |  | 23861234.76 | 0 | 0 | 0
Total Contingency (Incl. VAT) |  | 342011031.56 | 0 | 0 | 0 | 0%
Total Works Completed (Incl. VAT) |  | 4617148926.06 | 1350077912.0817 | 24311509.1345 | 1374389421.2162 | 0.32148
Costs to Date |  |  | Completed Previously | This Week | Project to Date | % of Total
• | Plant |  | 157729741.0746 | 3269800 | 160999541.0746 | 14.89%
• | AGO |  | 177509365 | 2412300 | 179921665 | 16.64%
• | Materials |  | 459782575.0558 | 10452896.5083 | 470235471.5641 | 43.48%
• | Sub Contractors |  | 34045601.2292 | 0 | 34045601.2292 | 3.148%
• | Local Labour |  | 78887600 | 1364500 | 80252100 | 7.421%
• | Overheads |  | 31000000 | 0 | 31000000 | 2.867%
• | Site Level Expenses |  | 124333202.79 | 612545.95 | 124945748.74 | 11.55%
• |  |  | 0 | 0 | 0
• |  |  | 0 | 0 | 0
Total Costs to Date |  |  | 1063288085.1496 | 18112042.4583 | 1081400127.6079 | 100%
Net Earnings - Excluding Bill 1 |  |  | 286789826.9321 | 6199466.6762 | 292989293.6083
% Net Earnings |  |  | 21.24% | 25.5% | 21.32%
WEEKLY PROGRESS
GENERAL REMARKS

## BEME & Works Completed Fd
| BEME & Works Completed to date | [11 empty] | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
Updated to the 01 March 2025 - Week No. 9
[5 empty] | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 0%
Total Bill No. 1 Carried to Summary | [8 empty] | 0 | 0 | 0 | 0 | 0%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
5 | GENERAL
5.01 | Provide, furnish and maintain office accommodation for the engineer's Representative | P.S | 1 |  |  | 0 | 1 | 2500000 | 2500000 | 0 | 0 | 0 | 0%
5.02 | Provide equipment, labor and assistance as may be required by the Engineer's Representative | P.S | 1 |  |  | 0 | 1 | 2000000 | 2000000 | 0 | 0 | 0 | 0%
5.03 | Allow for Survey and Design | P.S | 1 |  |  | 0 | 1 | 5000000 | 5000000 | 0 | 0 | 0 | 0%
5.04 | Allow for Purchase and maintenance of project vehicles | L.S | 1 |  |  | 0 | 1 | 10000000 | 10000000 | 0 | 0 | 0 | 0%
5.05 | Provide erect and maintain living accommodation for Resident Engineer, Technical officers and Technical Assistants | P.S | 1 |  |  | 0 | 1 | 2000000 | 2000000 | 0 | 0 | 0 | 0%
5.06 | Allow for Envoronmental Impact assessment and safety | P.S | 1 |  |  | 0 | 1 | 3000000 | 3000000 | 0 | 0 | 0 | 0%
5.07 | Allow for insurance of the Engineer and other Highway supervisory Staff against all accidents in connection with operation of the project. | L.S | 1 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0%
5.08 | Allow for Pavement Evaluation Unit Services | P.S | 1 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0%
5.09 | Allow for roadway markings and road signs | P.S | 1 |  |  | 0 | 1 | 5000000 | 5000000 | 0 | 0 | 0 | 0%
5.1 | Allow for cost of progress photographs | P.S | 1 |  |  | 0 | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0%
5.11 | Allow for the removal and relocation of existing installations for electricity, telephone, water supply and other utilities | P.S | 1 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0%
5.12 | Allow for compensation of crop, buildings and other properties affected by the proposed bridge alignment | P.S | 1 |  |  | 0 | 1 | 5000000 | 5000000 | 0 | 0 | 0 | 0%
Total Bill No. 5.0 Carried to Summary | [8 empty] | 35500000 | 0 | 0 | 0 | 0%
5.1 | EXCAVATION AND PILING
5.1.1 | Provide and place lateritic material as filling in river to serve as access for river crossing | m3 | 37224 | 27080 |  | 27080 | 10144 | 6200 | 230788800 | 167896000 | 0 | 167896000 | 72.75%
5.1.2 | Excavate in any kind of material except rock for all foundations including dewatering, shoring and backfilling with suitable material. | m3 | 4500 | 11617 |  | 11617 | -7117 | 5300 | 23850000 | 61570100 | 0 | 61570100 | 258.2%
5.1.3 | Extra over item 5.1.1 for excavation of rock. (haulage inclusive) Provisional | m3 | 1200 | 0 |  | 0 | 1200 | 32500 | 39000000 | 0 | 0 | 0 | 0%
5.1.4 | Earth fill suitable borrowed materials for foundations behind and around abutments | m3 | 4300 | 0 |  | 0 | 4300 | 6200 | 26660000 | 0 | 0 | 0 | 0%
5.1.5 | Grade 15 mass concrete to rock foundation bottom level | m3 | 2000 | 1378.9 |  | 1378.9 | 621.1 | 121500 | 243000000 | 167536350 | 0 | 167536350 | 68.95%
5.1.6 | Provide, place and fix 25mm dia High tensile steel reinforcement in bottom of foundation ( Micro piles ) | Tons | 10 | 2.9186 |  | 2.9186 | 7.0814 | 1180000 | 11800000 | 3443995.2 | 0 | 3443995.2 | 29.19%
5.1.7 | Provide and bore tests 600mm nominal diameter piles to any depth. Rate to include driving casting, filing with concrete grade 25, reinforcement and trimming of pile head as specified. | m | rate only |  |  | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0%
5.1.8 | Allow for confirmatory deep soil investigation at bridge site | LS | 1 |  |  | 0 | 1 | 20000000 | 20000000 | 0 | 0 | 0 | 0%
5.1.9 | Allow for Load tests on 600mm diameter piles to twice the design load | LS | rate only |  |  | 0 | 0 | 40000000 | 0 | 0 | 0 | 0 | 0%
Total Bill No. 2 Carried to Summary | [8 empty] | 595098800 | 400446445.2 | 0 | 400446445.2 | 67.29%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
5.2 | PILE CAP, PIERS ,PIER CAPS, ABUTMENT AND APPROACH SLAB
5.2.1 | Provide, mix and place grade 10 mass concrete 100mm blinding for bottom of pile caps and foundations and approach slab | m3 | 125 | 0 |  | 0 | 125 | 115000 | 14375000 | 0 | 0 | 0 | 0%
5.2.2 | Provide, mix and place grade 30 concrete in pile caps and foundations including formwork and shuttering | m3 | 1254 | 686.4 |  | 686.4 | 567.6 | 180000 | 225720000 | 123552000 | 0 | 123552000 | 54.74%
5.2.3 | Provide, cut and fix high tensile reinforcement in pile caps and foundations. | Tons | 105 | 73.8884 |  | 73.8884 | 31.1116 | 1180000 | 123900000 | 87188326.632 | 0 | 87188326.632 | 70.37%
5.2.4 | Provide, mix and place grade 30 concrete in abutments, wingwalls, piers, Retaining and pier caps | m3 | 1862 | 344.9048 | 26.5104 | 371.4152 | 1490.5848 | 180000 | 335160000 | 62082864 | 4771872 | 66854736 | 19.95%
5.2.5 | Provide, cut and fix high tensile reinforcement in Abutment, Wingwalls, Piers and Pier Cap | Tons | 165 | 27.1465 |  | 27.1465 | 137.8535 | 1180000 | 194700000 | 32032893.7982 | 0 | 32032893.7982 | 16.45%
5.2.6 | Provide and fix 100 mm diameter PVC pipe as weep holes in abutments and wingwalls as shown the drawings. | Nos. | 144 |  |  | 0 | 144 | 6500 | 936000 | 0 | 0 | 0 | 0%
5.2.7 | Grade 20 Concrete for Abutment Slope Protection | m2 | 550 |  |  | 0 | 550 | 17000 | 9350000 | 0 | 0 | 0 | 0%
5.2.8 | Grade 30 Concrete in Toebeam | m3 | 75 |  |  | 0 | 75 | 180000 | 13500000 | 0 | 0 | 0 | 0%
5.2.9 | H.T. Rebar in Toe for Abutment Protection | Tons | 7.5 |  |  | 0 | 7.5 | 1180000 | 8850000 | 0 | 0 | 0 | 0%
5.2.10 | Apply two coat of bitumen paint to concrete surfaces in contact with the earth. | m2 | 350 |  |  | 0 | 350 | 12500 | 4375000 | 0 | 0 | 0 | 0%
5.2.11 | Provide filter layers behind abutment, wingwalls and retaining wall | m2 | 407 |  |  | 0 | 407 | 16500 | 6715500 | 0 | 0 | 0 | 0%
5.2.12 | Provide, mix and place concrete grade 30 in approach slabs including reinforcement as shown on the drawing.. | m3 | 49.284 |  |  | 0 | 49.284 | 320000 | 15770880 | 0 | 0 | 0 | 0%
Total Bill No. 3 Carried to Summary | [8 empty] | 953352380 | 304856084.4302 | 4771872 | 309627956.4302 | 32.48%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
5.3 | SUPERSTRUCTURE
5.3.1 | Provide, mix and place concrete grade 40 in prefabricated longitudinal beams 255 Nos including shuttering, transportation and lauching to the right position | No | 255 | 81.75 | 3 | 84.75 | 170.25 | 2700000 | 688500000 | 220725000 | 8100000 | 228825000 | 33.24%
5.3.2 | Provide, mix and place concrete grade 30 in bridge deck slab including shuttering. | m3 | 820 | 0 |  | 0 | 820 | 180000 | 147600000 | 0 | 0 | 0 | 0%
5.3.3 | Provide, mix and place grade 30 concrete in outer kerbs including steel reinforcement and shuttering. | m | 564 | 0 |  | 0 | 564 | 25000 | 14100000 | 0 | 0 | 0 | 0%
5.3.4 | Ditto item 5.43 but to inner kerbs. | m |  | 0 |  | 0 | 0 | 141400 | 0 | 0 | 0 | 0 | 0%
5.3.5 | Provide, mix and place concrete grade 30 for parapets | m | 564 | 423 |  | 423 | 141 | 110000 | 62040000 | 46530000 | 0 | 46530000 | 75%
5.3.6 | Provide, fix rough shuttering to non-exposed faces of the superstructure. | m2 | 2000 | 0 |  | 0 | 2000 | 10500 | 21000000 | 0 | 0 | 0 | 0%
5.3.7 | Provide, fix wrot shuttering to exposed faces of the superstructure. | m2 | 5000 | 776.36 | 63.12 | 839.48 | 4160.52 | 15000 | 75000000 | 11645400 | 946800 | 12592200 | 16.79%
5.3.8 | Provide and fix H.T. steel reinforcement in beams and deck slab | Tons | 890 | 230.2403 | 7.4548 | 237.6951 | 652.3049 | 1180000 | 1050200000 | 271683500.2132 | 8796685.3344 | 280480185.5476 | 26.71%
5.3.9 | Provide walkway to include service ducts and inspection chambers as shown on the drawings. | m | 564 | 0 |  | 0 | 564 | 63000 | 35532000 | 0 | 0 | 0 | 0%
5.3.12 | Provide, mix and place concrete grade 30 in plinths | m3 | 8.76 |  |  | 0 | 8.76 | 178000 | 1559280 | 0 | 0 | 0 | 0%
Total Bill No. 4 Carried to Summary | [8 empty] | 2095531280 | 550583900.2132 | 17843485.3344 | 568427385.5476 | 27.13%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
5.4 | PAVEMENT
5.4.1 | Sacrify existing asphaltic surface, shape recomapct and use as improved sub base shape and cmpact formation as specified to 100% B.S Compaction | m2 | 0 |  | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0%
5.4.2 | shape and compact formation as specified to 100% B.S Compaction | m2 | 0 |  |  |  |  | 350
5.4.3 | Provide, spread and compact to 100% WASC compaction naturally occurring laterite as sub-base in varying thickness not exceeding a compacted layer of 200mm thickness on the approach road carriageway (haulage inclusive) | m3 | 0 |  |  |  |  | 6800
5.4.4 | Provide , spread, shape and compact approved crushed stone base 200mm thick in the carriageway only | m3 | 0 |  |  | 0 | 0 | 40500 | 0 | 0 | 0 | 0 | 0%
5.4.5 | Provide and lay prime coat using MC1 cut-back bitumen at 1.2/m2 including blinding with sand or quarry fines. | m2 | 0 |  |  | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0%
5.4.6 | Provide and lay 50mm thick asphaltic concrete wearing course inluding tack coat | m2 | 0 |  |  | 0 | 0 | 23200 | 0 | 0 | 0 | 0 | 0%
Total Bill No. 5 Carried to Summary | [8 empty] | 0 | 0 | 0 | 0 | 0%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
5.5 | MISCELLANEOUS
5.5.1 | Provide and place fixed bearings of approved design and type on top of abutment or piers. | Nos | 510 |  | 0 | 0 | 510 | 410000 | 209100000 | 0 | 0 | 0 | 0%
5.5.2 | Provide and install bearings movable bearings of approved design and type on top or Abutment of Piers. | Nos | 0 |  | 0 | 0 | 0 | 385000 | 0 | 0 | 0 | 0 | 0%
5.5.3 | Provide and install Thoma expansion Joint of approved design in the carriageway deck as shown on the drawings. | m | 190 |  | 0 | 0 | 190 | 300000 | 57000000 | 0 | 0 | 0 | 0%
5.5.4 | Ditto item 5.5.3 but along footpaths and kerbs as shown on the drawings. | m | 0 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0%
5.5.5 | Provide and fix into the bridge deck, cast iron inlet grating and finish complete as shown on the drawings. | Nos | 30 |  | 0 | 0 | 30 | 400000 | 12000000 | 0 | 0 | 0 | 0%
5.5.6 | Provide P.V.C. drainage pipes as shown on the drawings. | m | 30 |  | 0 | 0 | 30 | 30000 | 900000 | 0 | 0 | 0 | 0%
5.5.7 | Provide and lay concrete kerbs grade 20 along median as directed including for blinding and haunching. | m | 564 |  | 0 | 0 | 564 | 20000 | 11280000 | 0 | 0 | 0 | 0%
5.5.8 | Provide and place precast concrete bases for electric lighting poles. | Nos | 15 |  | 0 | 0 | 15 | 145000 | 2175000 | 0 | 0 | 0 | 0%
5.5.9 | Provide 100mm thick concrete (Grade 20) median | m | 282 |  | 0 | 0 | 282 | 17500 | 4935000 | 0 | 0 | 0 | 0%
Total Bill No.6 Carried to Summary | [8 empty] | 297390000 | 0 | 0 | 0 | 0%
Contingency & VOP
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
| Add VOP @ 5% |  | 1 |  |  | 0 | 1 | 198843623 | 198843623 | 0 | 0 | 0 | 0%
| Add Contingencies @ 3% |  | 1 | 0 |  | 0 | 1 | 119306173.8 | 119306173.8 | 0 | 0 | 0 | 0%
Total Contingency & VOP Carried to Summary |  |  | 1 | [5 empty] | 318149796.8 | 0 | 0 | 0 | 0%
Summary All
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
#REF! | #REF!
5 | Bill 1 | [7 empty] | 35500000 | 0 | 0 | 0 | 0%
5.1 | Excavation and Piling | [7 empty] | 595098800 | 400446445.2 | 0 | 400446445.2 | 67.29%
5.2 | Pile cap, Pier, Pier caps and Abutment | [7 empty] | 953352380 | 0 | 0 | 0 | 0%
5.3 | Superstructure | [7 empty] | 2095531280 | 0 | 0 | 0 | 0%
5.4 | Pavement | [7 empty] | 0
5.5 | Miscellanous | [7 empty] | 297390000 | 0 | 0 | 0 | 0%
| SUB – TOTAL | [7 empty] | 3976872460 | 400446445.2 | 0 | 400446445.2 | 10.07%
| Contingency & VOP | [7 empty] | 318149796.8 | 0 | 0 | 0 | 0%
| SUB – TOTAL | [7 empty] | 4295022256.8 | 400446445.2 | 0 | 400446445.2 | 9.324%
| Add VAT @ 7.5% | [7 empty] | 322126669.26 | 30033483.39 | 0 | 30033483.39 | 9.324%
| TOTAL | [7 empty] | 4617148926.06 | 430479928.59 | 0 | 430479928.59 | 9.324%

## Certificate Status
CERTIFICATES | [18 empty] | Date: | 2025-03-01 | Week No: | 9 | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
CERTIFICATES
Date Submitted | Cert Number | Gross Value of Works Done | Add Materials on Site | General Bill 1 | Total Value of Work Done | Value of works per Cert | Total Retention Held | Retention This Cert | Total Net Payment in Respect of works | Add Release of Retention | Add Value of Contingency Used | Add Fluctuation on Materials | Total Value of Works Executed | Less Previously Certified without VAT | Add VAT - 7.5% | Add Stamp Duty | Add Admin Charge | Educational Levy | Total Amount Due | Less Recovery of Advance | Less advance Payment Refund per Cert | Total Amount of Payment Certified | Status
|  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 | Not Vetted
|  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Totals | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[7 empty] | Add VAT - 7.5% | 0 |  | 0 | [9 empty] | Add VAT - 7.5% | 0
[7 empty] | Total Retention Deducted - Inc. VAT: | 0 | Ret. Rel. - Inc VAT: | 0 | [9 empty] | Total Advance Recovered - Including VAT: | 0
SUMMARY CERT STATUS
Vetted |  | 0 | 0 | [9 empty] | 0 | [8 empty] | 0
Not Vetted |  | 0 | 0 | [9 empty] | 0 | [8 empty] | 0
|  | 0 | 0 | [9 empty] | 0 | [8 empty] | 0

## Payments Recieved
PAYMENTS RECEIVED |  |  |  |  | Date: | 2025-03-01 |  | Week No: | 9 | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
PAYMENT DETAILS |  |  |  | DEDUCTIONS | [6 empty] | Deductions %
Date | Voucher Number | Payment Type | Gross Amount (Including VAT) | WHT | VAT | Vetting Fee | Stamp Duty | Other | Net Amount Payable |  | VAT % | WHT % | State Levy % | Stamp Duty % | Other %
| Advance No. 1 | Advance | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
| Cert No 2 | Cert | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
|  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0% | 0% | 0% | 0% | 0%
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
Total All: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | 0%
0

## Cost Report
COST REPORT |  |  |  |  | Date: | 2025-03-01 | Week No: | 9 | Instructions
CONSTRUCTION OF BUA LAFIAGI BYPASS ROAD | PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
S/No | Description | Cost Category | Unit | Quantity This Week | Rate N | Amount Previous Week | Amount This Week | Amount Up to Date |  | Source Legend | Source Detail
PLANT DEPARTMENT | [9 empty] | PLANT DEPARTMENT | All information should be obtained from the plant department reports.
1 | Diesel | AGO | Litres | 2193 | 1100 | 177509365 | 2412300 | 179921665 |  | MATERIALS | All information is auto populated from the materials reconcilaition sheet, other than the Amount Previous Week
2 | Diesel (P.W. External Issues) | AGO | Litres |  | 1100 | 0 | 0 | 0 |  | OTHER MATERIALS | Other material not captured on the materails & civils report that may be used on site.
3 | Plant Internal | Plant | N/a |  |  | 121891035.9032 | 2516666.55 | 124407702.4532 |  | OTHER SITE COSTS | All information is auto populated from the headcount and subcontractors report, other than the Amount Previous Week
4 | Hired Plant/Equipment/Vehicle | Plant | N/a |  |  | 813000 | 15000 | 828000 |  | SITE LEVEL ACCOUNTS | All information is obtained from the site accountant weekly financial report.
5 | Petrol | Plant | Litres | 162.3 | 1000 | 9520945.0746 | 162300 | 9683245.0746 |  | OVERHEADS | Information is provided by the PM other than Bill 1 information which is provided by the Accountant in completing the Bill 1 schedule.
6 | Stores Cost | Plant | Various |  |  |  | 0
7 | Engine Oil | Plant | Litres | 53 | 4097.56 | 14865204.2527 | 217170.68 | 15082374.9327
8 | Gear oil | Plant | Litres | 14 | 6786 | 1767586.3415 | 95004 | 1862590.3415
9 | ATF 220 Oil | Plant | Litres | 0 | 6171 | 601902.439 | 0 | 601902.439
10 | Hydroualic Oil Azzolla | Plant | Litres | 33 | 3292.69 | 2334807.0637 | 108658.77 | 2443465.8337
11 | Rarius 427 Comp. Oil | Plant | Litres |  | 0 | 0 | 0 | 0
12 | Almo 529 | Plant | Litres |  | 0 | 0 | 0 | 0
13 | Grease | Plant | Kg | 10 | 12100 | 984180 | 121000 | 1105180
14 | 6440; Tyres | Plant | Each |  |  | 0 |  | 0
MATERIALS | [5 empty] | 0 | 0 | 0
1 | Cement (Bags) | Materials | Bags | 468 | 4650 | 149870500 | 2176200 | 152046700
2 | Cement (Bulk) | Materials | Tonnes | 0 | 95000 | 0 | 0 | 0
3 | Rebar (10mm) Local | Materials | Tonnes | 1.3122 | 550000 | 15191382.4471 | 721701.7533 | 15913084.2004
4 | Rebar (12mm) Local | Materials | Tonnes | 1.5431 | 550000 | 36252566.8068 | 848731.752 | 37101298.5588
5 | Rebar (16mm) Local | Materials | Tonnes | 1.5892 | 550000 | 33672342.213 | 874074.96 | 34546417.173
6 | Rebar (12mm) Imported | Materials | Tonnes | 0 | 550000 | 0 | 0 | 0
7 | Rebar (16mm) Imported | Materials | Tonnes | 0 | 550000 | 0 | 0 | 0
8 | Rebar (20mm) Imported | Materials | Tonnes | 0 | 550000 | 0 | 0 | 0
9 | Rebar (25mm) Imported | Materials | Tonnes | 9.537 | 550000 | 167203800.8896 | 5245336.8 | 172449137.6896
9 | Rebar (32mm) Imported | Materials | Tonne | 0 | 550000 | 0 | 0 | 0
10 | Binding Wire | Materials | Roll | 0 | 14000 | 252000 | 0 | 252000
11 | Sharp Sand | Materials | Tonnes | 47.1994 | 3000 | 11495640.7727 | 141598.2645 | 11637239.0372
12 | Blocks 9" | Materials | Each | 0 | 600 | 1144810 | 0 | 1144810
13 | Geotextile | Materials | M2 | 0 | 1200000 | 0 | 0 | 0
14 | UPVC Pipe(300mm) | Materials | Each | 0 | 2800 | 0 | 0 | 0
15 | UPVC Pipe(100mm) | Materials | Each | 0 | 3800 | 0 | 0 | 0
16 | Interlocking Paving Stone | Materials | m2 | 0 | 3600 | 0 | 0 | 0
17 | Precast Units | Materials | LM | 0 | 25000 | 0 | 0 | 0
QUARRY MATERIALS |  |  | 0
18 | 3/4" Aggregates | Materials | Tonnes | 13.734 | 8350 | 15196028.6535 | 114679.0879 | 15310707.7414
19 | 1/2" Aggregates | Materials | Tonnes | 39.5897 | 8350 | 22873503.2731 | 330573.8906 | 23204077.1638
20 | 3/8" Aggregates | Materials | Tonnes | 0 | 8350 | 0 | 0 | 0
21 | Sand | Materials | Tonnes | 0 | 3000 | 0 | 0 | 0
22 | Stone Base | Materials | Tonnes | 0 | 6500 | 0 | 0 | 0
23 | Hardcore | Materials | Tonnes | 0 | 6500 | 0 | 0 | 0
24 | MC1 | Materials | Tonne | 0 | 0 | 0 | 0 | 0
25 | Tack Coat (MC1) | Materials | Litres | 0 | 0 | 0 | 0 | 0
26 | S125 | Materials | Litres | 0 | 0 | 0 | 0 | 0
27 | Wearing Course Asphalt | Materials | Tonnes | 0 | 0 | 0 | 0 | 0
28 | Binder Course Asphalt | Materials | Tonnes | 0 | 0 | 0 | 0 | 0
29 | Borrow Pit | Materials | m2 | 0 | 0 | 0 | 0 | 0
OTHER MATERIALS
1 | 6400; Timber | Materials |  |  |  | 0 |  | 0
2 | Diesel (P.W. External Issues) | AGO | Litre |  | 1100 | 0 | 0 | 0
3 | [5 empty] | 0 |  | 0
OTHER SITE COSTS | [5 empty] | 0 |  | 0
1 | Sub-Contractor's Expenses | Sub Contractors |  |  |  | 34045601.2292 | 0 | 34045601.2292
2 | Labour | Local Labour | No. | 51 | 25000 | 74500000 | 1275000 | 75775000
[6 empty] | 0 |  | 0
SITE LEVEL ACCOUNTS | [5 empty] | 0 |  | 0
1 | 6320; Spare Parts | Plant |  |  |  | 4675080 | 34000 | 4709080
2 | 1041; Building & Site Development | Site Level Expenses |  |  |  | 261500 |  | 261500
3 | 6021; P.W. Tippers (Haulage-fees) | Materials |  |  |  | 0 |  | 0
4 | 6100; Compensation | Site Level Expenses |  |  |  | 245000 |  | 245000
5 | 6230; Security Expenses | Site Level Expenses |  |  |  | 18769500 | 265000 | 19034500
6 | 6300; Steel Plate/Reinforcement | Plant |  |  |  | 276000 |  | 276000
7 | 6350; Materials | Materials |  |  |  | 6630000 |  | 6630000
8 | 6420; Tools and Consumables | Site Level Expenses |  |  |  | 70395465 | 140007 | 70535472
9 | 6220; External Labour | Local Labour |  |  |  | 4387600 | 89500 | 4477100
10 | 6540; Sundry Expenses | Site Level Expenses |  |  |  | 10700950 |  | 10700950
11 | 7020; Miscellaneous Running Costs/Expenses | Site Level Expenses |  |  |  | 5973093 |  | 5973093
12 | 7220; Expatriate Living Costs | Site Level Expenses |  |  |  | 7046443 | 75200 | 7121643
13 | 7340; Office Equipment Maintenance | Site Level Expenses |  |  |  | 575000 |  | 575000
14 | 7350; I.T. Costs - Internet | Site Level Expenses |  |  |  | 316000 |  | 316000
15 | 7351; I.T. Costs - Software / Maint. Costs | Site Level Expenses |  |  |  | 120000 |  | 120000
16 | 7320; Medical Expenses | Site Level Expenses |  |  |  | 3921660 | 24550 | 3946210
17 | 7460; Rent | Site Level Expenses |  |  |  | 0 |  | 0
18 | 7500; Stationary | Site Level Expenses |  |  |  | 435750 | 3200 | 438950
19 | 7560; Telephone | Site Level Expenses |  |  |  | 1425000 | 31000 | 1456000
20 | 7620; Travelling | Site Level Expenses |  |  |  | 3782250 | 59500 | 3841750
21 | 7622: Outstation | Site Level Expenses |  |  |  | 101250 |  | 101250
22 | 8020; Bank Charges | Site Level Expenses |  |  |  | 264341.79 | 14088.95 | 278430.74
23
24 | [5 empty] | 0 |  | 0
OVERHEADS | [5 empty] | 0 |  | 0
1 | Administration | Overheads | No. | 0 | 1000000 | 31000000 |  | 31000000
| Total |  |  |  |  | 1063288085.1496 | 18112042.4583 | 1081400127.6079

## Plant Return
WEEKLY PLANT RETURNS | [6 empty] | Date: | 2025-03-01 | Week No: | 9 | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
Fleet No. | Description | Plant Category | Hours Worked | S/B Hours | B/D Hours | Rate (N) | Plant Cost | Transfered From | Current Location | Remarks
AC69 | STATIC AIR COMPRESSOR |  | 40 | 30 | 0 | 300 | 12000 |  | Kaduna | working
AC173 | Mobile Air compressor |  | 8 | 62 | 0 | 500 | 4000 |  | Kaduna | working
BB18 | BAR BENDER |  | 40 | 30 | 0 | 500 | 20000 |  | Kaduna | working
BP10 | BATCHING PLANT (DRY) |  | 40 | 30 | 0 | 6100 | 244000 |  | Kaduna | working
D67 | DOZER |  | 23 | 47 | 0 | 8200 | 188600 |  | Kaduna | working
E88 | Excavator |  | 17 | 53 | 0 | 8200 | 139400 |  | Kaduna
E94 | JS200 EXCAVATOR |  | 44 | 26 | 0 | 8200 | 360800 |  | Kaduna | working
EG86 | Generator set |  | 34 | 36 | 0 | 1300 | 44200 |  | Kaduna
EG214 | GENERATOR SET |  | 42 | 28 | 0 | 1300 | 54600 |  | Kaduna | working
EG251 | GENERATOR SET |  | 0 | 0 | 70 | 1300 | 0 |  | Kaduna | Engine problem, to send to Abuja for overhaul
EG252 | GENERATOR SET |  | 0 | 0 | 70 | 1300 | 0 |  | Kaduna | Engine over consuming oil, to send to Abuja for repairs
EG263 | GENERATOR SET |  | 53 | 17 | 0 | 1300 | 68900 |  | Kaduna | working
EG284 | GENERATOR SET Honda |  | 0 | 70 | 0 | 500 | 0 |  | Kaduna | standby
EG287 | GENERATOR SET Firman |  | 0 | 0 | 70 | 500 | 0 |  | Kaduna | Nozzle problem, Not starting
FMP20 | FUEL METER PUMP |  | 40 | 30 | 0 | 500 | 20000 |  | Kaduna | working
G38 | Grader |  | 0 | 70 | 0 | 501 | 0 |  | Kaduna
IC26 | IRON CUTTER |  | 40 | 30 | 0 | 500 | 20000 |  | Kaduna | working
L66 | L70F PAYLOADER |  | 22 | 48 | 0 | 8200 | 180400 |  | Kaduna | working
L67 | L150H PAYLOADER |  | 0 | 70 | 0 | 8200 | 0 |  | Kaduna | standby
LL11 | Low loader |  | 0 | 70 | 0 | 5800 | 0 |  | Kaduna | standby
LT8 | LUXURIOUS BUS |  | 50 | 20 | 0 | 1600 | 80000 |  | Kaduna | working
MCM15 | MOBILE CAR MIXER |  | 8 | 62 | 0 | 2000 | 16000 |  | Kaduna | working
P370 | PICK UP |  | 0 | 0 | 70 | 1000 | 0 |  | Kaduna | Injector pump and Nozzles problem
P413 | PICK UP |  | 50 | 20 | 0 | 1000 | 50000 |  | Kaduna | working
P416 | PICK UP |  | 60 | 10 | 0 | 1000 | 60000 |  | Kaduna | working
P418 | PICK UP |  | 50 | 20 | 0 | 1000 | 50000 |  | Kaduna | Propella plange yoke and cross bearing changed back to work
P439 | PICK UP |  | 50 | 20 | 0 | 1000 | 50000 |  | Kaduna | working
PF5 | POWER FLOAT |  | 0 | 70 | 0 |  | 0 |  | Kaduna | standby
PF6 | POWER FLOAT |  | 0 | 70 | 0 |  | 0 |  | Kaduna | standby
RT12 | GROVE CRANE |  | 15 | 55 | 0 | 13200 | 198000 |  | Kaduna | working
T210 | WATER TANKER |  | 40 | 30 | 0 | 4100 | 164000 |  | Kaduna | working
T229 | WATER TANKER |  | 40 | 30 | 0 | 4100 | 164000 |  | Kaduna | working
T343 | Low loader |  | 0 | 70 | 0 | 4900 | 0 |  | Kaduna | standby
T365 | TRACTOR UNIT |  | 50 | 20 | 0 | 4900 | 245000 |  | Kaduna | working
T385 | TRUCK MIXER |  | 50 | 20 | 0 | 4900 | 245000 |  | Kaduna | working
T403 | Concrete Pump |  | 0 | 70 | 0 |  | 0 |  | Kaduna | standby
T488 | FUEL BOWSER |  | 8 | 62 | 0 | 5800 | 46400 |  | Kaduna | working
T510 | HIAB TRUCK |  | 40 | 30 | 0 | 4900 | 196000 |  | Kaduna | working
T576 | TRUCK MIXER |  | 0 | 70 | 0 | 5800 | 0 |  | Kaduna | working
T607 | VOLVO TIPPER |  | 0 | 70 | 0 | 5800 | 0 |  | Kaduna | standby
T608 | VOLVO TIPPER |  | 0 | 70 | 0 | 5800 | 0 |  | Kaduna | standby
VPE134 | VIBRATING POKER ENGINE |  | 0 | 70 | 0 | 100 | 0 |  | Kaduna | standby
VPE140 | VIBRATING POKER ENGINE |  | 40 | 30 | 0 | 100 | 4000 |  | Kaduna | working
VPE217 | VIBRATING POKER ENGINE |  | 0 | 70 | 0 | 100 | 0 |  | Kaduna | standby
VPE244 | VIBRATING POKER ENGINE |  | 0 | 70 | 0 | 100 | 0 |  | Kaduna | standby
VPE258 | VIBRATING POKER ENGINE |  | 40 | 30 | 0 | 100 | 4000 |  | Kaduna | working
VPE280 | VIBRATING POKER ENGINE |  | 40 | 30 | 0 | 100 | 4000 |  | Kaduna | working
VPE282 | VIBRATING POKER ENGINE |  | 0 | 70 | 0 | 100 | 0 |  | Kaduna | standby
VPE283 | VIBRATING POKER ENGINE |  | 0 | 70 | 0 | 100 | 0 |  | Kaduna | standby
VR132 | ROLLER |  | 0 | 70 | 0 | 2900 | 0 |  | Kaduna | standby
VR134 | ROLLER |  | 48 | 22 | 0 | 2900 | 139200 |  | Kaduna | standby
W111 | WELDING SET |  | 0 | 70 | 0 | 500 | 0 |  | Kaduna | standby
W123 | MOBILE WELDING SET |  | 0 | 70 | 0 | 500 | 0 |  | Kaduna | working
W124 | MOBILE WELDING SET |  | 7 | 63 | 0 | 500 | 3500 |  | Kaduna | working
WM93 | WASHING MACHINE |  | 0 | 70 | 0 | 500 | 0 |  | Kaduna | standby
WP218 | 6'' water Pump |  | 8 | 62 | 0 | 500 | 4000 |  | Kaduna | working
WP332 | WATER PUMP |  | 0 | 70 | 0 | 500 | 0 |  | Kaduna | standby
WP349 | WATER PUMP |  | 25 | 45 | 0 | 500 | 12500 |  | Kaduna | working
WP420 | WATER PUMP |  | 26 | 44 | 0 |  | 0 |  | Kaduna | working
0
| TOTAL All : |  | 1188 | 2662 | 280 |  | 3092500
|  |  |  | % Allocated to the project |  |  | 100%
|  |  |  | Total Internal Plant cost Allocated |  |  | 3092500
Internal Plant Cost Adjusted for
|  |  |  | Engine Oil |  |  | 217170.68
|  |  |  | Gear oil |  |  | 95004
|  |  |  | ATF 220 Oil |  |  | 0
|  |  |  | DTE 26 Oil |  |  | 108658.77
|  |  |  | Rarius 427 Comp. Oil |  |  | 0
|  |  |  | Almo 529 |  |  | 0
|  |  |  | Grease |  |  | 121000
|  |  |  | 6440; Tyres |  |  | 0
|  |  |  | 6320; Spare Parts |  |  | 34000
|  |  |  | Tota All Adjusted |  |  | 575833.45
|  |  |  | Net Plant Cost Cost Report |  |  | 2516666.55

## Diesel Consumption
WEEKLY DIESEL CONSUMPTION | [5 empty] | Date: | 2025-03-01 | [5 empty] | Week No: | 9 |  |  | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
|  | Opening Stock: | 0 |  |  |  | Received this Week: | 0 |  |  | Used This Week: | 2193 |  |  | Closing Stock: | -2193
Fleet No. | Description | Plant Category | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Total Fuel Taken | Standard Ltrs/Hour | Standard Usage | Variance | Variance Value | Usage Value | Remarks
AC69 | STATIC AIR COMPRESSOR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC173 | Mobile Air compressor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB18 | BAR BENDER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
BP10 | BATCHING PLANT (DRY) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
D67 | DOZER |  | 0 | 0 | 100 | 0 | 50 | 100 | 50 | 300 |  | 0 | 300 | 330000 | 330000
E88 | Excavator |  | 0 | 0 | 50 | 0 | 50 | 80 | 60 | 240 |  | 0 | 240 | 264000 | 264000
E94 | JS200 EXCAVATOR |  | 0 | 0 | 120 | 50 | 115 | 80 | 30 | 395 |  | 0 | 395 | 434500 | 434500
EG86 | Generator set |  | 0 | 0 | 30 | 10 | 20 | 30 | 20 | 110 |  | 0 | 110 | 121000 | 121000
EG214 | GENERATOR SET |  | 0 | 0 | 30 | 10 | 20 | 30 | 20 | 110 |  | 0 | 110 | 121000 | 121000
EG251 | GENERATOR SET |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
EG252 | GENERATOR SET |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
EG263 | GENERATOR SET |  | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 |  | 0 | 200 | 220000 | 220000
EG284 | GENERATOR SET Honda |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
EG287 | GENERATOR SET Firman |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
FMP20 | FUEL METER PUMP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
G38 | Grader |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
IC26 | IRON CUTTER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
L66 | L70F PAYLOADER |  | 0 | 0 | 30 | 0 | 0 | 30 | 30 | 90 |  | 0 | 90 | 99000 | 99000
L67 | L150H PAYLOADER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
LL11 | Low loader |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
LT8 | LUXURIOUS BUS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
MCM15 | MOBILE CAR MIXER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
P370 | PICK UP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
P413 | PICK UP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
P416 | PICK UP |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 |  | 0 | 20 | 22000 | 22000
P418 | PICK UP |  | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 |  | 0 | 64 | 70400 | 70400
P439 | PICK UP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PF5 | POWER FLOAT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PF6 | POWER FLOAT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
RT12 | GROVE CRANE |  | 0 | 0 | 45 | 0 | 30 | 40 | 40 | 155 |  | 0 | 155 | 170500 | 170500
T210 | WATER TANKER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
T229 | WATER TANKER |  | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 20 |  | 0 | 20 | 22000 | 22000
T343 | Low loader |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
T365 | TRACTOR UNIT |  | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 150 |  | 0 | 150 | 165000 | 165000
T385 | TRUCK MIXER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
T403 | Concrete Pump |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
T488 | FUEL BOWSER |  | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30 |  | 0 | 30 | 33000 | 33000
T510 | HIAB TRUCK |  | 0 | 0 | 15 | 0 | 10 | 15 | 0 | 40 |  | 0 | 40 | 44000 | 44000
T576 | TRUCK MIXER |  | 0 | 0 | 30 | 0 | 30 | 30 | 30 | 120 |  | 0 | 120 | 132000 | 132000
T607 | VOLVO TIPPER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
T608 | VOLVO TIPPER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE134 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE140 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE217 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE244 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE258 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE280 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE282 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VPE283 | VIBRATING POKER ENGINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VR132 | ROLLER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
VR134 | ROLLER |  | 0 | 0 | 20 | 0 | 0 | 30 | 0 | 50 |  | 0 | 50 | 55000 | 55000
W111 | WELDING SET |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
W123 | MOBILE WELDING SET |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 |  | 0 | 10 | 11000 | 11000
W124 | MOBILE WELDING SET |  | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 30 |  | 0 | 30 | 33000 | 33000
WM93 | WASHING MACHINE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
WP218 | 6'' water Pump |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
WP332 | WATER PUMP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
WP349 | WATER PUMP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
WP420 | WATER PUMP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 530 | 140 | 639 | 515 | 310 | 2134 | 0 | 0 | 2134 | 2347400 | 2347400
0
Other Uses | [14 empty] | 0
Precast |  |  | 0 | 0 | 15 | 0 | 15 | 15 | 10 | 55 |  |  |  |  | 60500
workshop |  |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 |  |  |  |  | 4400
Ministry |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Drillers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
P408 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
Sub Total Other Used |  |  | 0 | 0 | 15 | 0 | 19 | 15 | 10 | 59 |  | 0 | 0 |  | 64900
0
Total All Diesel Used |  |  | 0 | 0 | 545 | 140 | 658 | 530 | 320 | 2193 |  | 0 | 2134 | 2347400 | 2412300
[5 empty] | % Allocated to the project |  |  |  |  | 100%
[5 empty] | Total Internal Plant cost Allocated |  |  |  |  | 2193

## Materials & Civils
MATERIAL STOCKS | [9 empty] | Date: | 2025-03-01 |  | Week No: | 9 | 9
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
USED IN THE WEEK
# | Description | Unit | Current Price | Opening Stock | Received / Purchased | Closing Stock | Available for Use | On Site Works | Precast | Mobilsation | Other Uses | Total Used | Variance Qty | Variance Value | Comments
1 | Cement (Bags) | Bags | 6700 | 934 | 900 | 1366 | 468 | 468 |  |  |  | 468 | 0 | 0
2 | Cement (Bulk) | Tonne | 95000 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
3 | Rebar (10mm) Local | Tonne | 587000 | 15.5812 |  | 14.269 | 1.3122 | 1.3122 |  |  |  | 1.3122 | 0 | 0
4 | Rebar (12mm) Local | Tonne | 587000 | 43.5764 | 20.0558 | 62.0891 | 1.5431 | 1.5431 |  |  |  | 1.5431 | 0 | 0
5 | Rebar (16mm) Local | Tonne | 587000 | 45.5678 |  | 43.9785 | 1.5892 | 1.5892 |  |  |  | 1.5892 | 0 | 0
6 | Rebar (12mm) Imported | Tonne | 657500 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
7 | Rebar (16mm) Imported | Tonne | 657500 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
8 | Rebar (20mm) Imported | Tonne | 657500 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
9 | Rebar (25mm) Imported | Tonne | 657500 | 0.50926 | 10.1851 | 1.1574 | 9.537 | 9.537 |  |  |  | 9.537 | 0 | 0
10 | Rebar (32mm) Imported | Tonne | 657500 | 27.6151 |  | 27.6151 | 0 | 0 |  |  |  | 0 | 0 | 0
11 | Binding Wire | Roll | 4500 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
12 | Sharp Sand | Tonne | 4000 | 132.0823 | 49.23 | 134.1129 | 47.1994 | 47.1994 |  |  |  | 47.1994 | 0 | 0
13 | Blocks 9" | Each | 480 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
14 | Geotextile |  |  | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
QUARRY MATERIALS |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
26 | 1/2" Aggregates | Tonne | 10000 | 150.2271 | 65.85 | 176.4874 | 39.5897 | 39.5897 |  |  |  | 39.5897 | 0 | 0
25 | 3/4" Aggregates | Tonne | 10000 | 150.8647 |  | 137.1307 | 13.734 | 13.734 |  |  |  | 13.734 | 0 | 0
27 | 3/8" Aggregates | Tonne | 6000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
28 | Sand | Tonne | 8200 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
29 | Stone base | Tonne | 6500 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
30 | Hardcore | Tonne | 6500 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
31 | MC1 Priming | Tonne | 918000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
32 | S125 Surface Dressing | Tonne | 957000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
33 | RSII Colas Tack Coat | Tonne | 930000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
34 | Crack Relief Layer CRL | Tonne | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
35 | Asphalt Binder Course | Tonne | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
36 | Asphalt Wearing Course | Tonne | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
37 | 60/70 Bitumen | Tonne |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
38 | Kerosine | Litres |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
39 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0
40 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0
| Total All: | [5 empty] | 0 |  |  |  |  | 582.5047 | 0 | 0

## Hired Vehicles
HIRED VEHICLES |  |  |  |  | Date: | 2025-03-01 | Week No: | 9 | Instructions
#REF! | PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
S/No. | Reg. No | Description | Section | Owners | Days Worked | Rate (N) | Amount (N) | Remarks
1 |  |  | Engineer | engr. | 6 | 2500 | 15000
2 |  |  | Acct | accountant | 0 | 2500 | 0
3 |  |  | Survey | surveyor |  |  | 0
4 |  |  | Lab |  |  |  | 0
5 |  |  | Mechanic | Mechanic | 0 | 2000 | 0
6 |  |  | Mechanic | Mechanic | 0 | 1800 | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0
|  |  |  | Total |  |  | 15000

## Labour Strength
LABOUR STRENGTH |  | Date: | 2025-03-01 | Week No: | 9 | Instructions
PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
S/No | Department | Manning This Week | Manning Previous Week | Movement | Comment
1 | Senior Staff | 0 | 0 | 0
2 | Civil Engineers | 3 | 3 | 0
3 | Civil - Surveyors | 4 | 4 | 0
4 | Administration | 2 | 2 | 0
5 | Lab | 4 | 4 | 0
6 | Domestics | 2 | 2 | 0
7 | Security | 1 | 1 | 0
8 | Plant | 17 | 17 | 0
9 | Transport | 3 | 3 | 0
10 | Earthworks | 4 | 4 | 0
11 | Quarry | 0 | 0 | 0
12 | Asphalt |  |  | 0
13 | Marini | 0 | 0 | 0
14 | Civil Batching Plant | 11 | 11 | 0
15 | Electrical |  |  | 0
| Total Head Count | 51 | 51 | 0
CASUAL STAFF
S/No | Department | Manning This Week | Manning Previous Week | Movement | Comment
1 | Transport & Earthworks |  |  | 0
2 | Engr, Survey, civil store & Batching plant |  |  | 0
3 | Security |  |  | 0
4 | Lab |  |  | 0
5 | Quarry | 0 | 0 | 0
6 | Civil | 0 | 0 | 0
| Total Casual Head Count | 0 |  | 0

## Subcontractors
SUBCONTRACTORS | [12 empty] | Date: | 2025-03-01 | Week No: | 9 | Instructions
#REF! | PROPOSED CONSTRUCTION OF 15 SPAN, DUAL CARRIAGEWAY, 6TH BRIDGE OVER RIVER KADUNA AND APPROACH ROADS
Item | Subcontractor | Description | Location | Unit | Agreed Rate | Assigned Qty | Previous Qty | Qty Executed for Week | Total Qty Executed To-Date | Balance to Complete | Subcontract Value This Week | Previous Value Completed | Value Completed this week | Total Value Completed | Value to Completion | Remarks
| DOMINIC ANI GLOBAL NIG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Excavation |  | m3 | 1100 |  | 64.608 |  | 64.608 | -64.608 | 0 | 71068.8 | 0 | 71068.8 | -71068.8
2 |  | Formwork In Generator House/Iron Bending Floor |  | m2 | 825 |  | 101.8902 |  | 101.8902 | -101.8902 | 0 | 84059.415 | 0 | 84059.415 | -84059.415
3 |  | Formwork In Batching Plant |  | m2 | 825 |  | 24.202 |  | 24.202 | -24.202 | 0 | 19966.65 | 0 | 19966.65 | -19966.65
4 |  | Formwork In Precast Units |  | m2 | 825 |  | 5462.748 |  | 5462.748 | -5462.748 | 0 | 4506767.1 | 0 | 4506767.1 | -4506767.1
5 |  | Strapping/Striking of Formwork |  | m2 | 357.5 |  | 5588.8402 |  | 5588.8402 | -5588.8402 | 0 | 1998010.3715 | 0 | 1998010.3715 | -1998010.3715
6 |  | Woodworks in Containers and Security Houses |  | m2 | 825 |  | 170.04 |  | 170.04 | -170.04 | 0 | 140283 | 0 | 140283 | -140283
7 |  | G15 Concrete Blinding In Batching Plant |  | m3 | 275 |  | 28.8 |  | 28.8 | -28.8 | 0 | 7920 | 0 | 7920 | -7920
8 |  | Block Laying in Yard |  | m2 | 770 |  | 129.09 |  | 129.09 | -129.09 | 0 | 99399.3 | 0 | 99399.3 | -99399.3
9 |  | Block Laying & Infilling in Yard |  | m2 | 1100 |  | 86.93 |  | 86.93 | -86.93 | 0 | 95623 | 0 | 95623 | -95623
10 |  | Block Laying & Infilling in Bridge Foundation |  | m2 | 1100 |  | 1148.55 |  | 1148.55 | -1148.55 | 0 | 1263405 | 0 | 1263405 | -1263405
11 |  | G25 Conc. in Generator House/Iron Bending Floor |  | m3 | 1100 |  | 33.2936 |  | 33.2936 | -33.2936 | 0 | 36622.9715 | 0 | 36622.9715 | -36622.9715
12 |  | G25 Concrete in Batching Plant |  | m3 | 1100 |  | 102.6894 |  | 102.6894 | -102.6894 | 0 | 112958.34 | 0 | 112958.34 | -112958.34
13 |  | G40 Concrete in Precast Units |  | m3 | 1100 |  | 857.969 |  | 857.969 | -857.969 | 0 | 943765.9 | 0 | 943765.9 | -943765.9
14 |  | G25 Concrete in Bridge Mass Leveller |  | m3 | 1100 |  | 1708.155 |  | 1708.155 | -1708.155 | 0 | 1878970.5 | 0 | 1878970.5 | -1878970.5
15 |  | Fixing of Batching Plant Units and Stiching |  | No | 2200 |  | 14 |  | 14 | -14 | 0 | 30800 | 0 | 30800 | -30800
16 |  | Fixing of Perimeter Poles |  | No | 1100 |  | 249 |  | 249 | -249 | 0 | 273900 | 0 | 273900 | -273900
17 |  | Covering of Perimeter Fence with Net |  | m | 220 |  | 880 |  | 880 | -880 | 0 | 193600 | 0 | 193600 | -193600
18 |  | Plastering |  | m2 | 770 |  | 148.2676 |  | 148.2676 | -148.2676 | 0 | 114166.052 | 0 | 114166.052 | -114166.052
19 |  | Batching of Concrete |  | m3 | 440 |  | 211.7 |  | 211.7 | -211.7 | 0 | 93148 | 0 | 93148 | -93148
20 |  | Daywork - Workmen |  | Days | 3300 |  | 505 |  | 505 | -505 | 0 | 1666500 | 0 | 1666500 | -1666500
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| IBRAHIM MUHAMMED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Cuting and Bending Reinforcement Bars in Plant/Yard |  | Ton | 12100 |  | 9.0994 |  | 9.0994 | -9.0994 | 0 | 110102.7511 | 0 | 110102.7511 | -110102.7511
2 |  | Cuting and Bending Reinforcement Bars in Bridge Parapets |  | Ton | 12100 |  | 38.0648 |  | 38.0648 | -38.0648 | 0 | 460584.259 | 0 | 460584.259 | -460584.259
3 |  | Cuting and Bending Reinforcement Bars in Bridge Beams |  | Ton | 12100 |  | 315.01 |  | 315.01 | -315.01 | 0 | 3811620.7855 | 0 | 3811620.7855 | -3811620.7855
4 |  | Cuting and Bending Reinforcement Bars in Bridge Foundation |  | Ton | 12100 |  | 73.5069 |  | 73.5069 | -73.5069 | 0 | 889433.8578 | 0 | 889433.8578 | -889433.8578
5 |  | Cuting and Bending Reinforcement Bars in Bridge Pier Columns |  | Ton | 12100 |  | 26.1217 |  | 26.1217 | -26.1217 | 0 | 316072.7642 | 0 | 316072.7642 | -316072.7642
6 |  | Fixing Reinforcement Bars in Batching Plant/Yard |  | Ton | 8800 |  | 9.0994 |  | 9.0994 | -9.0994 | 0 | 80074.7281 | 0 | 80074.7281 | -80074.7281
7 |  | Fixing Reinforcement Bars in Bridge Parapets |  | Ton | 8800 |  | 38.0648 |  | 38.0648 | -38.0648 | 0 | 334970.3702 | 0 | 334970.3702 | -334970.3702
8 |  | Fixing Reinforcement Bars in Bridge Beams |  | Ton | 8800 |  | 278.3132 |  | 278.3132 | -278.3132 | 0 | 2449156.2332 | 0 | 2449156.2332 | -2449156.2332
9 |  | Fixing Reinforcement Bars in Bridge Foundation |  | Ton | 8800 |  | 70.1656 |  | 70.1656 | -70.1656 | 0 | 617457.7024 | 0 | 617457.7024 | -617457.7024
10 |  | Fixing Reinforcement Bars in Bridge Pier Columns |  | Ton | 8800 |  | 26.1217 |  | 26.1217 | -26.1217 | 0 | 229871.1012 | 0 | 229871.1012 | -229871.1012
11 |  | Off Loading of Reinforcement Bars |  | Ton | 1100 |  | 251 |  | 251 | -251 | 0 | 276100 | 0 | 276100 | -276100
12 |  | Daywork - Workmen |  | Days | 3300 |  | 63.5 |  | 63.5 | -63.5 | 0 | 209550 | 0 | 209550 | -209550
| UMAR AMINU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Excavation for Soakaway |  | m3 | 1 |  | 90000 |  | 90000 | -90000 | 0 | 90000 | 0 | 90000 | -90000
2 |  | Backfiling for Soakaway |  | m3 | 1 |  | 15000 |  | 15000 | -15000 | 0 | 15000 | 0 | 15000 | -15000
3 |  | Block Laying in Toilet Building |  | m2 | 1 |  | 59965.5 |  | 59965.5 | -59965.5 | 0 | 59965.5 | 0 | 59965.5 | -59965.5
4 |  | Block Laying & Infilling in Soakaway |  | m2 | 1 |  | 23186.1 |  | 23186.1 | -23186.1 | 0 | 23186.1 | 0 | 23186.1 | -23186.1
5 |  | Plastering in Soakaway |  | m2 | 1 |  | 84829.78 |  | 84829.78 | -84829.78 | 0 | 84829.78 | 0 | 84829.78 | -84829.78
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PAM JAMA JAMA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Batching of Concrete |  | m3 | 440 |  | 1439.5 |  | 1439.5 | -1439.5 | 0 | 633380 | 0 | 633380 | -633380
2 |  | Daywork - Workmen |  | Days | 3300 |  | 123 |  | 123 | -123 | 0 | 405900 | 0 | 405900 | -405900
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SILAS IKEDICHI & SONS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Casting and Packing of 9" Sancrete Blocks |  | No | 143 |  | 6678 |  | 6678 |  |  | 954954 | 0 | 954954 | -954954
2 |  | Casting of Biscuit |  | No | 5.5 |  | 28907 |  | 28907 |  |  | 158988.5 | 0 | 158988.5 | -158988.5
3 |  | Batching of Concrete |  | m3 | 440 |  | 1842.1 |  | 1842.1 | -1842.1 | 0 | 810524 | 0 | 810524 | -810524
4 |  | Daywork - Workmen |  | Days | 3300 |  | 124 |  | 124 |  |  | 409200 | 0 | 409200 | -409200
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DAVID DELL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Formwork In Batching Plant |  | m2 | 825 |  | 23.4723 |  | 23.4723 | -23.4723 | 0 | 19364.6475 | 0 | 19364.6475 | -19364.6475
2 |  | Batching of Concrete |  | m3 | 440 |  | 7 |  | 7 | -7 | 0 | 3080 | 0 | 3080 | -3080
3 |  | Formwork In Bridge Pier Bases |  | m2 | 825 |  | 734.4 |  | 734.4 | -734.4 | 0 | 605880 | 0 | 605880 | -605880
4 |  | Formwork In Bridge Piers Columns |  | m2 | 825 |  | 1358.4 |  | 1358.4 | -1358.4 | 0 | 1120680 | 0 | 1120680 | -1120680
5 |  | Strapping/Striking of Formwork |  | m2 | 357.5 |  | 2116.2723 |  | 2116.2723 | -2116.2723 | 0 | 756567.3473 | 0 | 756567.3473 | -756567.3473
6 |  | G25 Concrete in Batching Plant |  | m3 | 1100 |  | 2.5819 |  | 2.5819 | -2.5819 | 0 | 2840.046 | 0 | 2840.046 | -2840.046
7 |  | G30 Concrete in Bridge Pier Bases |  | m3 | 1100 |  | 691.104 |  | 691.104 | -691.104 | 0 | 760214.4 | 0 | 760214.4 | -760214.4
8 |  | G30 Concrete in Bridge Pier Columns |  | m3 | 1100 |  | 398.832 |  | 398.832 | -398.832 | 0 | 438715.2 | 0 | 438715.2 | -438715.2
9 |  | Precasting of Parapets |  | No | 5000 |  | 282 |  | 282 | -282 | 0 | 1410000 | 0 | 1410000 | -1410000
10 |  | Fixing of Windows |  | No | 2500 |  | 6 |  | 6 | -6 | 0 | 15000 | 0 | 15000 | -15000
11 |  | Fixing of Doors |  | No | 4500 |  | 2 |  | 2 | -2 | 0 | 9000 | 0 | 9000 | -9000
12 |  | Daywork - Workmen |  | Days | 3300 |  | 229 |  | 229 | -229 | 0 | 755700 | 0 | 755700 | -755700
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S.C. JANG ENTERPRISE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | Casting and Packing of 9" Sancrete Blocks |  | No | 143 |  | 2075 |  | 2075 |  |  | 296725 | 0 | 296725 | -296725
2 |  | Casting of Biscuit |  | No | 5.5 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
3 |  | Batching of Concrete |  | m3 | 440 |  | 518 |  | 518 | -518 | 0 | 227920 | 0 | 227920 | -227920
4 |  | Cuting and Bending Reinforcement Bars in Bridge Pier Columns |  | Ton | 12100 |  | 15.0127 |  | 15.0127 |  |  | 181653.6527 | 0 | 181653.6527 | -181653.6527
|  | Fixing Reinforcement Bars in Bridge Pier Columns |  | Ton | 8800 |  | 11.3515 |  | 11.3515 | -11.3515 | 0 | 99892.8178 | 0 | 99892.8178 | -99892.8178
|  | Daywork - Workmen |  | Days | 3300 |  | 85 |  | 85 | -85 | 0 | 280500 | 0 | 280500 | -280500
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | -301565.2346 | 0 | 34045589.944 | 0 | 34045589.944 | -34045589.944

## Precast
MATERIAL STOCKS | [9 empty] | Date: | 2025-03-01 |  | Week No: | 9
#REF!
S/No | DESCRIPTION | SIZE | UOM | BEME Amount | Previous Cast Amount | Cast This week | Total Cast to Date | Balance Required | Used Previous | Used This week | Total Used | Balance Available | Closing Stock | Variance | REMARKS
1 | Bridge Beam |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Bridge Parapet |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
5 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
6 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
7 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
8 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
9 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
10 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
11 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
12 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
13 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
0

## Bill 1 Summary
BILL 1 SCHEDULE | [5 empty] | Date: | 2025-03-01 | Week No: | 9 | Instructions
#REF! | [7 empty] | Service Charge: | 2.5% |  | CLAIMED IN CERTS (Inclusive of Service Charge)
Item NO. | DESCRIPTION | REQUESTED BY MINISTRY | PAID to date by P.W. | OUTSTANDING By P.W. | CLAIMED IN CERTS (Net of 2.50%) | PAID BY CLIENT (Net of 2.50%) | PAYMENT RECIVED, OUTSTANDING BY PW | Ministry Letter Reference | Request Date |  | Cert 1 | Cert 2 | Cert 3 | Cert 4 | Cert 5 | Cert 6 | Cert 7 | Cert 8 | Cert 9 | Cert 10 | Cert 11 | Cert 12 | Cert 13 | Cert 14 | Cert 15 | Cert 16 | Cert 17 | Cert 18 | Cert 19 | Cert 20 | Cert 21 | Cert 22 | Cert 23 | Total
[10 empty] | Cert Status: |  | Not Paid | [21 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [21 empty] | 0
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [21 empty] | 0
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [21 empty] | 0
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [21 empty] | 0
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [21 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Bill 1 Payments
DETAIL SCHEDULE BILL 1 PAYMENTS |  |  | Date: | 2025-03-01 | Week No: | Instructions
#REF!
Date | Payee | Bank | Chq No. / Ref | Bill 1 Item | Amount |  | Wk- YR
|  |  |  | Total All Bill 1 Items to date: | 0
0

## Lists
Date | Week no. | Wk & Year | UOM | Description | Cost Categories | Plant Categories | Cost Assumption | Rate | Basis | Contract Bank Details |  | CONCRETE CLASS: | 15N/mm² |  |  | 20N/mm² |  |  | 25N/mm² |  |  | 30N/mm² |  |  | 40N/mm² |  |  | P.W. NIGERIA LIMITED |  |  |  | NOVEMBER 2015
2020-01-01 | 1 | 1-20 | m3 | Cubic Metre | Plant | Lowloader | Employer Pension Rate | 10% | % | Bank Name: | First Bank of Nigeria Limited | Bill of Quanties for Design Mix of concrete | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume
2020-01-02 | 1 | 1-20 | m2 | Metre Squared | AGO | Tippers | Administration Cost | 1400000 | Per Expat | Account Name: | P.W. NIGERIA LIMITED | [16 empty] | STANDARD APPROVED RATES FOR SUBCONTRACTS
2020-01-03 | 1 | 1-20 | Lm | Linear Metre | Materials | Tipping Trailers | VAT (Value Added Tax) | 7.5% | % | Account Number: | 2001507098 |  | kg/m³ | % | m³ | kg/m³ | % | m³ | kg/m³ | % | m³ | kg/m³ | % | m³ | kg/m³ | % | m³
2020-01-04 | 1 | 1-20 | Litre | Litres | Sub Contractors | Trucks | Local Staff Cost | 25000 | Per Week | Sort Code: | 001084060 | 20mm (3/4 Inch) | 785 | 33.05% | 0.586 | 733 | 30.54% | 0.547 | 726 | 30.26% | 0.542 |  | 0% |  |  | 0% |  | S/NO | DESCRIPTION |  | UNIT | APROVED | COMMENTS
2020-01-05 | 2 | 2-20 | Tonne | Metric Tonnes | Local Labour | Flat Bed Trailers | Bill 1 Service Charge | 2.5% |  |  |  | 10mm (1/2 Inch) | 391 | 16.46% | 0.294 | 383 | 15.96% | 0.288 | 365 | 15.21% | 0.275 |  | 0% |  |  | 0% | [5 empty] | RATE (N)
2020-01-06 | 2 | 2-20 | Roll | Roll | Overheads | Lorries | Withholding Tax | 7.5% |  |  |  | 12.5mm (3/8 Inch) |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | EXCAVATION
2020-01-07 | 2 | 2-20 | Each | Per Unit | Site Level Expenses | Tractor Units | [5 empty] | River Sand | 717 | 30.19% | 0.496 | 748 | 31.17% | 0.517 | 753 | 31.39% | 0.52 |  | 0% |  |  | 0% |  |  |  | General excavation including any necessary trimming, levelling & compaction of excavated ground surface | m3 | 500 | This is for excavation works carried out solely by the subcontractor. It is not applicable to their attendance on PW excavator.
2020-01-08 | 2 | 2-20 | Bags | Per Bag | Bill 1 | Water Tanker Trucks | [5 empty] | Quarry Dust |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  |  | Backfilling & compaction | m3 | 200
2020-01-09 | 2 | 2-20 | Kgs | Per Kg |  | Water Tanker - Trailers | [5 empty] | Free water Ltrs | 175 | 7.368% | 0.175 | 174 | 7.25% | 0.174 | 180 | 7.503% | 0.18 |  | 0% |  |  | 0% |  |  |  | Ground Preparation | m2 |  | Trimming, levelling & compaction of previously excavated ground
2020-01-10 | 2 | 2-20 | Loads | Per Load |  | Fuel Bowsers | [5 empty] | Complast Admixture |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
2020-01-11 | 2 | 2-20 | Litres | Litres |  | Lube Tankers | [5 empty] | Cement | 307 | 12.93% | 0.249 | 362 | 15.08% | 0.294 | 375 | 15.63% | 0.304 |  | 0% |  |  | 0% |  |  | BLOCK DRAINS, 450MM INTERNAL WIDTH - NO REINFORCEMENT - ALL INCLUSIVE RATE
2020-01-12 | 3 | 3-20 | N/a |  |  | Service Trucks | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  |  | 1 course full block drain | Lm |  | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-13 | 3 | 3-20 |  |  |  | Luxurious | [6 empty] | 2375 | 100% | 1.8 | 2400 | 100% | 1.82 | 2399 | 100% | 1.821 | 0 | 0% | 0 | 0 | 0% | 0 |  |  | 2 courses full block drain | Lm |  | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-14 | 3 | 3-20 |  |  |  | Hiab
2020-01-15 | 3 | 3-20 |  |  |  | Bulk Cement Trucks | [22 empty] | BLOCK DRAINS, 450MM INTERNAL WIDTH - REINFORCED - ALL INCLUSIVE RATE
2020-01-16 | 3 | 3-20 |  |  |  | Ambulance | [23 empty] | 1 course full block drain | Lm | 10100 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-17 | 3 | 3-20 |  |  |  | 4 X 4 Suvs | [23 empty] | 2 courses full block drain | Lm | 12300 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-18 | 3 | 3-20 |  |  |  | Pickups | [23 empty] | 3 courses full block drain | Lm | 13500 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-19 | 4 | 4-20 |  |  |  | Saloon Cars | [23 empty] | 4 courses full block drain | Lm | 15700 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-20 | 4 | 4-20 |  |  |  | Motor Bikes
2020-01-21 | 4 | 4-20 |  |  |  | Dump Truck - Rigid (Cat) | [22 empty] | PRE-CAST DRAINS - LABOUR ONLY
2020-01-22 | 4 | 4-20 |  |  |  | Dump Truck - Articulated (Volvo) | [23 empty] | Casting drain units | Lm | 500 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard other than loading onto flatbed
2020-01-23 | 4 | 4-20 |  |  |  | Scrapers | [23 empty] | Loading & offloading drain units | Lm | 50 | This is specifically for loading the precast units onto the flatbed in the precast yard and offloading at site. This should be paid for once only. All other handling of precast units in the precast yard is covered under casting drain units
2020-01-24 | 4 | 4-20 |  |  |  | Dozers | [23 empty] | Laying & stitching both sides of L drain | Lm | 1550 | Rate includes laying both roadside and kerbside units. Fixing rebar and placing concrete in gap to be stitched.
2020-01-25 | 4 | 4-20 |  |  |  | Excavators | [23 empty] | Casting cover slabs | no. | 600 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard
2020-01-26 | 5 | 5-20 |  |  |  | Hammer Breakers | [23 empty] | Lay cover slabs, including loading & unloading | no. | 500
2020-01-27 | 5 | 5-20 |  |  |  | Payloaders
2020-01-28 | 5 | 5-20 |  |  |  | Graders | [22 empty] | CULVERTS - ALL INCLUSIVE RATE
2020-01-29 | 5 | 5-20 |  |  |  | Dumpers | [23 empty] | 450mm Diam. Culverts | Lm |  | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-30 | 5 | 5-20 |  |  |  | Piling Rigs | [23 empty] | 600mm Diam. Culverts | Lm | 26500 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-31 | 5 | 5-20 |  |  |  | Compactors | [23 empty] | 750mm Diam. Culverts | Lm | 32000 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-02-01 | 5 | 5-20 |  |  |  | Rollers | [23 empty] | 900mm Diam. Culverts | Lm | 42000 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-02-02 | 6 | 6-20 |  |  |  | Vibrating Plates | [23 empty] | Supply & place concrete in culvert headwalls, wingwalls and aprons, including formwork | m3 | 31500 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-02-03 | 6 | 6-20 |  |  |  | Cranes - Mobile
2020-02-04 | 6 | 6-20 |  |  |  | Cranes - Tower | [22 empty] | DEMOLITION OF EXISTING DRAINS / CULVERTS
2020-02-05 | 6 | 6-20 |  |  |  | Slip Form Paver (Gomaco) | [23 empty] | Drainage demolition - Labour only | Lm | 300
2020-02-06 | 6 | 6-20 |  |  |  | Concrete Batching Plants (Static Type) - Wetmix | [23 empty] | Culvert Demolition, including removal | m3 | 1800
2020-02-07 | 6 | 6-20 |  |  |  | Concrete Batching Plants (Static Type) - Drymix | [23 empty] | Concrete demolition - Labour only | m3 | 2750
2020-02-08 | 6 | 6-20 |  |  |  | Concrete Mixer - Mobile (Carmixer Type) | [23 empty] | Drainage Cleaning | Lm | 200
2020-02-09 | 7 | 7-20 |  |  |  | Concrete Mixer - Small (Winget Type) | [23 empty] | Culvert Cleaning | Lm | 200
2020-02-10 | 7 | 7-20 |  |  |  | Concrete Pump - Truck Mounted
2020-02-11 | 7 | 7-20 |  |  |  | Concrete Pump - Static | [22 empty] | CONCRETE BATCHING
2020-02-12 | 7 | 7-20 |  |  |  | Concrete Mixer Trucks | [23 empty] | Batching of Grade 25 Concrete | m3 | 400 | Rate is for all labour required to operate static batching plant in precast yard provided by PW, includes handling of all raw materials and loading concrete onto mixer trucks. PW to provide all materials, payloader for loading aggregates, water tanker if necessary for water.
2020-02-13 | 7 | 7-20 |  |  |  | Vibrating Poker Engines | [22 empty] | CONCRETE SUPPLY & PLACEMENT
2020-02-14 | 7 | 7-20 |  |  |  | Concrete Power Float Machines | [23 empty] | Supply and place Gr. 25 concrete to headwalls, wingwalls and aprons etc into existing formwork | m3 |  | Rate is for supplying and mixing all concrete materials, placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-15 | 7 | 7-20 |  |  |  | Asphalt Batching Plant | [23 empty] | Supply and place Gr. 25 concrete to headwalls, wingwalls and aprons etc including supplying & installing formwork | m3 |  | Rate is for supplying and mixing all concrete materials, placing, vibrating and finishing concrete including supplying and fixing all formwork
2020-02-16 | 8 | 8-20 |  |  |  | Heating Plant
2020-02-17 | 8 | 8-20 |  |  |  | Tar Sprayer - Truck | [22 empty] | CONCRETE PLACEMENT - LABOUR ONLY
2020-02-18 | 8 | 8-20 |  |  |  | Tar Sprayer - Trailer Only | [23 empty] | Blinding Concrete | m3 | 125
2020-02-19 | 8 | 8-20 |  |  |  | Planing Machines | [23 empty] | Mass concrete | m3 | 250
2020-02-20 | 8 | 8-20 |  |  |  | Asphalt Finishers (Pavers) | [23 empty] | Reinforced concrete placement - General | m3 | 300 | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-21 | 8 | 8-20 |  |  |  | Asphalt Cutting Machines | [23 empty] | Reinforced concrete placement - Bridge Substructure - In-situ (not including filling of piles) | m3 |  | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-22 | 8 | 8-20 |  |  |  | Farm Tractors | [23 empty] | Reinforced concrete placement - Bridge Superstructure - In-situ | m3 |  | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-23 | 9 | 9-20 |  |  |  | Road Brushes | [23 empty] | Pre-casting of main longitudinal bridge beams | m3 |  | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-24 | 9 | 9-20 |  |  |  | Chiiping Spreaders | [23 empty] | Pre-casting of bridge deck slabs (2.1m X 1.4 X 0.07) | no. | 750 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard
2020-02-25 | 9 | 9-20 |  |  |  | Generators | [23 empty] | Pre-casting of bridge parapet walls (2.1m long) | no. | 2100 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard
2020-02-26 | 9 | 9-20 |  |  |  | Compressors | [23 empty] | Placement and fixing of pre-cast bridge parapet walls (2.1m long) | no. |  | Rate includes loading the precast units onto the flatbed in the precast yard and offloading at site. This should be paid for once only. All other handling of precast units in the precast yard is covered under casting pre-cast units
2020-02-27 | 9 | 9-20 |  |  |  | Cement Blowers
2020-02-28 | 9 | 9-20 |  |  |  | Fuel Meter Pumps | [22 empty] | REINFORCEMENT - LABOUR ONLY
2020-02-29 | 9 | 9-20 |  |  |  | Weigh Bridges | [23 empty] | Cutting & bending | ton | 9000
2020-03-01 | 10 | 10-20 |  |  |  | Telehandlers / Fork Lifts | [23 empty] | Fixing | ton | 6000
2020-03-02 | 10 | 10-20 |  |  |  | Block Moulding Machines
2020-03-03 | 10 | 10-20 |  |  |  | Welding Sets | [22 empty] | REINFORCEMENT - ALL INCLUSIVE RATE
2020-03-04 | 10 | 10-20 |  |  |  | Bending & Cutting Machines | [23 empty] | Supply, cutting, bending & fixing | ton |  | Rate includes, material supply (including tie wire), delivery, cutting, bending and fixing.
2020-03-05 | 10 | 10-20 |  |  |  | Turning Machines
2020-03-06 | 10 | 10-20 |  |  |  | Sand Blaster
2020-03-07 | 10 | 10-20 |  |  |  | Washing Machines | [22 empty] | FORMWORK - LABOUR ONLY
2020-03-08 | 11 | 11-20 |  |  |  | Grass Cutting Machines | [23 empty] | Placing formwork - generally | m2 | 750
2020-03-09 | 11 | 11-20 |  |  |  | Line Painting Machines
2020-03-10 | 11 | 11-20 |  |  |  | Mobile Lighting Sets | [22 empty] | STONE PITCHING
2020-03-11 | 11 | 11-20 |  |  |  | Water Pumps | [23 empty] | 150mm Stone pitching including trimming, levelling & preparation of ground surface. Materials supplied by PW | m2 | 750
2020-03-12 | 11 | 11-20 |  |  |  | Crusher - Static | [23 empty] | 150mm Stone pitching. Materials by subcontractor - All in rate | m2 | 4200
2020-03-13 | 11 | 11-20 |  |  |  | Crusher - Mobile
2020-03-14 | 11 | 11-20 |  |  |  | Mobile Screen | [22 empty] | KERBING
2020-03-15 | 12 | 12-20 |  |  |  | Vertical Shaft Impactor (Vsi) | [23 empty] | Removal of existing kerbs | Lm |  | Rate includes removal of base & haunch and loading onto trucks for disposal.
2020-03-16 | 12 | 12-20 |  |  |  | Crawler Drill | [23 empty] | Casting kerbs & handling | Lm | 350
2020-03-17 | 12 | 12-20 | [27 empty] | Excavate, blind, lay & haunch | Lm | 900
2020-03-18 | 12 | 12-20
2020-03-19 | 12 | 12-20 | [26 empty] | BLOCKS - CASTING
2020-03-20 | 12 | 12-20 | [27 empty] | 6" Blocks, cast, water & stack - Labour only | no. | 30
2020-03-21 | 12 | 12-20 | [27 empty] | 9" Blocks, cast, water & stack - Labour only | no. | 50
2020-03-22 | 13 | 13-20
2020-03-23 | 13 | 13-20 | [26 empty] | SANDCRETE BLOCKS - LAYING - LABOUR ONLY
2020-03-24 | 13 | 13-20 | [27 empty] | Laying 6" blocks (labour only) | m2 | 500
2020-03-25 | 13 | 13-20 | [27 empty] | Laying 9" blocks (labour only) | m2 | 700
2020-03-26 | 13 | 13-20 | [27 empty] | Filling of block with concrete | m2 | 300
2020-03-27 | 13 | 13-20
2020-03-28 | 13 | 13-20 | [26 empty] | SANDCRETE BLOCKS - ALL INCLUSIVE RATE
2020-03-29 | 14 | 14-20 | [27 empty] | Supply & Laying 6" blocks | m2 |  | Rate includes supply & mixing of all mortar
2020-03-30 | 14 | 14-20 | [27 empty] | Supply & Laying 9" blocks | m2 |  | Rate includes supply & mixing of all mortar
2020-03-31 | 14 | 14-20 | [27 empty] | Filling of block with concrete | m2 |  | Rate includes supply & mixing of all concrete
2020-04-01 | 14 | 14-20
2020-04-02 | 14 | 14-20 | [26 empty] | INTERLOCKING CONCRETE PAVING - 80MM THK
2020-04-03 | 14 | 14-20 | [27 empty] | Place Interlocking Tiles and bedding sand, including filling joints with sand - Labour only | m2 | 500
2020-04-04 | 14 | 14-20 | [27 empty] | Supply & place Interlocking Tiles - All inclusive rate including supply of bedding sand | m2 | 4500
2020-04-05 | 15 | 15-20
2020-04-06 | 15 | 15-20 | [26 empty] | MISCELLANEOUS OTHERS
2020-04-07 | 15 | 15-20 | [27 empty] | Grassing - including supply & placement of topsoil | m2 | 500
2020-04-08 | 15 | 15-20 | [27 empty] | Plastering - Labour only | m2 | 500
2020-04-09 | 15 | 15-20 | [27 empty] | Plastering - All inclusive rate | m2 |  | Rate includes supplying and mixing of all required materials
2020-04-10 | 15 | 15-20 | [27 empty] | Placing of uPVC ducts in excavated trenches - Labour only | Lm |  | Rate includes all handling, cutting & jointing
2020-04-11 | 15 | 15-20
2020-04-12 | 16 | 16-20 | [26 empty] | DAYWORKS - LABOUR SUPPLY
2020-04-13 | 16 | 16-20 | [27 empty] | General Labourer - Daily Rate | day
2020-04-14 | 16 | 16-20 | [27 empty] | Artisan - Daily Rate | day
2020-04-15 | 16 | 16-20
2020-04-16 | 16 | 16-20
2020-04-17 | 16 | 16-20
2020-04-18 | 16 | 16-20
2020-04-19 | 17 | 17-20
2020-04-20 | 17 | 17-20
2020-04-21 | 17 | 17-20
2020-04-22 | 17 | 17-20
2020-04-23 | 17 | 17-20
2020-04-24 | 17 | 17-20
2020-04-25 | 17 | 17-20
2020-04-26 | 18 | 18-20
2020-04-27 | 18 | 18-20
2020-04-28 | 18 | 18-20
2020-04-29 | 18 | 18-20
2020-04-30 | 18 | 18-20
2020-05-01 | 18 | 18-20
2020-05-02 | 18 | 18-20
2020-05-03 | 19 | 19-20
2020-05-04 | 19 | 19-20
2020-05-05 | 19 | 19-20
2020-05-06 | 19 | 19-20
2020-05-07 | 19 | 19-20
2020-05-08 | 19 | 19-20
2020-05-09 | 19 | 19-20
2020-05-10 | 20 | 20-20
2020-05-11 | 20 | 20-20
2020-05-12 | 20 | 20-20
2020-05-13 | 20 | 20-20
2020-05-14 | 20 | 20-20
2020-05-15 | 20 | 20-20
2020-05-16 | 20 | 20-20
2020-05-17 | 21 | 21-20
2020-05-18 | 21 | 21-20
2020-05-19 | 21 | 21-20
2020-05-20 | 21 | 21-20
2020-05-21 | 21 | 21-20
2020-05-22 | 21 | 21-20
2020-05-23 | 21 | 21-20
2020-05-24 | 22 | 22-20
2020-05-25 | 22 | 22-20
2020-05-26 | 22 | 22-20
2020-05-27 | 22 | 22-20
2020-05-28 | 22 | 22-20
2020-05-29 | 22 | 22-20
2020-05-30 | 22 | 22-20
2020-05-31 | 23 | 23-20
2020-06-01 | 23 | 23-20
2020-06-02 | 23 | 23-20
2020-06-03 | 23 | 23-20
2020-06-04 | 23 | 23-20
2020-06-05 | 23 | 23-20
2020-06-06 | 23 | 23-20
2020-06-07 | 24 | 24-20
2020-06-08 | 24 | 24-20
2020-06-09 | 24 | 24-20
2020-06-10 | 24 | 24-20
2020-06-11 | 24 | 24-20
2020-06-12 | 24 | 24-20
2020-06-13 | 24 | 24-20
2020-06-14 | 25 | 25-20
2020-06-15 | 25 | 25-20
2020-06-16 | 25 | 25-20
2020-06-17 | 25 | 25-20
2020-06-18 | 25 | 25-20
2020-06-19 | 25 | 25-20
2020-06-20 | 25 | 25-20
2020-06-21 | 26 | 26-20
2020-06-22 | 26 | 26-20
2020-06-23 | 26 | 26-20
2020-06-24 | 26 | 26-20
2020-06-25 | 26 | 26-20
2020-06-26 | 26 | 26-20
2020-06-27 | 26 | 26-20
2020-06-28 | 27 | 27-20
2020-06-29 | 27 | 27-20
2020-06-30 | 27 | 27-20
2020-07-01 | 27 | 27-20
2020-07-02 | 27 | 27-20
2020-07-03 | 27 | 27-20
2020-07-04 | 27 | 27-20
2020-07-05 | 28 | 28-20
2020-07-06 | 28 | 28-20
2020-07-07 | 28 | 28-20
2020-07-08 | 28 | 28-20
2020-07-09 | 28 | 28-20
2020-07-10 | 28 | 28-20
2020-07-11 | 28 | 28-20
2020-07-12 | 29 | 29-20
2020-07-13 | 29 | 29-20
2020-07-14 | 29 | 29-20
2020-07-15 | 29 | 29-20
2020-07-16 | 29 | 29-20
2020-07-17 | 29 | 29-20
2020-07-18 | 29 | 29-20
2020-07-19 | 30 | 30-20
2020-07-20 | 30 | 30-20
2020-07-21 | 30 | 30-20
2020-07-22 | 30 | 30-20
2020-07-23 | 30 | 30-20
2020-07-24 | 30 | 30-20
2020-07-25 | 30 | 30-20
2020-07-26 | 31 | 31-20
2020-07-27 | 31 | 31-20
2020-07-28 | 31 | 31-20
2020-07-29 | 31 | 31-20
2020-07-30 | 31 | 31-20
2020-07-31 | 31 | 31-20
2020-08-01 | 31 | 31-20
2020-08-02 | 32 | 32-20
2020-08-03 | 32 | 32-20
2020-08-04 | 32 | 32-20
2020-08-05 | 32 | 32-20
2020-08-06 | 32 | 32-20
2020-08-07 | 32 | 32-20
2020-08-08 | 32 | 32-20
2020-08-09 | 33 | 33-20
2020-08-10 | 33 | 33-20
2020-08-11 | 33 | 33-20
2020-08-12 | 33 | 33-20
2020-08-13 | 33 | 33-20
2020-08-14 | 33 | 33-20
2020-08-15 | 33 | 33-20
2020-08-16 | 34 | 34-20
2020-08-17 | 34 | 34-20
2020-08-18 | 34 | 34-20
2020-08-19 | 34 | 34-20
2020-08-20 | 34 | 34-20
2020-08-21 | 34 | 34-20
2020-08-22 | 34 | 34-20
2020-08-23 | 35 | 35-20
2020-08-24 | 35 | 35-20
2020-08-25 | 35 | 35-20
2020-08-26 | 35 | 35-20
2020-08-27 | 35 | 35-20
2020-08-28 | 35 | 35-20
2020-08-29 | 35 | 35-20
2020-08-30 | 36 | 36-20
2020-08-31 | 36 | 36-20
2020-09-01 | 36 | 36-20
2020-09-02 | 36 | 36-20
2020-09-03 | 36 | 36-20
2020-09-04 | 36 | 36-20
2020-09-05 | 36 | 36-20
2020-09-06 | 37 | 37-20
2020-09-07 | 37 | 37-20
2020-09-08 | 37 | 37-20
2020-09-09 | 37 | 37-20
2020-09-10 | 37 | 37-20
2020-09-11 | 37 | 37-20
2020-09-12 | 37 | 37-20
2020-09-13 | 38 | 38-20
2020-09-14 | 38 | 38-20
2020-09-15 | 38 | 38-20
2020-09-16 | 38 | 38-20
2020-09-17 | 38 | 38-20
2020-09-18 | 38 | 38-20
2020-09-19 | 38 | 38-20
2020-09-20 | 39 | 39-20
2020-09-21 | 39 | 39-20
2020-09-22 | 39 | 39-20
2020-09-23 | 39 | 39-20
2020-09-24 | 39 | 39-20
2020-09-25 | 39 | 39-20
2020-09-26 | 39 | 39-20
2020-09-27 | 40 | 40-20
2020-09-28 | 40 | 40-20
2020-09-29 | 40 | 40-20
2020-09-30 | 40 | 40-20
2020-10-01 | 40 | 40-20
2020-10-02 | 40 | 40-20
2020-10-03 | 40 | 40-20
2020-10-04 | 41 | 41-20
2020-10-05 | 41 | 41-20
2020-10-06 | 41 | 41-20
2020-10-07 | 41 | 41-20
2020-10-08 | 41 | 41-20
2020-10-09 | 41 | 41-20
2020-10-10 | 41 | 41-20
2020-10-11 | 42 | 42-20
2020-10-12 | 42 | 42-20
2020-10-13 | 42 | 42-20
2020-10-14 | 42 | 42-20
2020-10-15 | 42 | 42-20
2020-10-16 | 42 | 42-20
2020-10-17 | 42 | 42-20
2020-10-18 | 43 | 43-20
2020-10-19 | 43 | 43-20
2020-10-20 | 43 | 43-20
2020-10-21 | 43 | 43-20
2020-10-22 | 43 | 43-20
2020-10-23 | 43 | 43-20
2020-10-24 | 43 | 43-20
2020-10-25 | 44 | 44-20
2020-10-26 | 44 | 44-20
2020-10-27 | 44 | 44-20
2020-10-28 | 44 | 44-20
2020-10-29 | 44 | 44-20
2020-10-30 | 44 | 44-20
2020-10-31 | 44 | 44-20
2020-11-01 | 45 | 45-20
2020-11-02 | 45 | 45-20
2020-11-03 | 45 | 45-20
2020-11-04 | 45 | 45-20
2020-11-05 | 45 | 45-20
2020-11-06 | 45 | 45-20
2020-11-07 | 45 | 45-20
2020-11-08 | 46 | 46-20
2020-11-09 | 46 | 46-20
2020-11-10 | 46 | 46-20
2020-11-11 | 46 | 46-20
2020-11-12 | 46 | 46-20
2020-11-13 | 46 | 46-20
2020-11-14 | 46 | 46-20
2020-11-15 | 47 | 47-20
2020-11-16 | 47 | 47-20
2020-11-17 | 47 | 47-20
2020-11-18 | 47 | 47-20
2020-11-19 | 47 | 47-20
2020-11-20 | 47 | 47-20
2020-11-21 | 47 | 47-20
2020-11-22 | 48 | 48-20
2020-11-23 | 48 | 48-20
2020-11-24 | 48 | 48-20
2020-11-25 | 48 | 48-20
2020-11-26 | 48 | 48-20
2020-11-27 | 48 | 48-20
2020-11-28 | 48 | 48-20
2020-11-29 | 49 | 49-20
2020-11-30 | 49 | 49-20
2020-12-01 | 49 | 49-20
2020-12-02 | 49 | 49-20
2020-12-03 | 49 | 49-20
2020-12-04 | 49 | 49-20
2020-12-05 | 49 | 49-20
2020-12-06 | 50 | 50-20
2020-12-07 | 50 | 50-20
2020-12-08 | 50 | 50-20
2020-12-09 | 50 | 50-20
2020-12-10 | 50 | 50-20
2020-12-11 | 50 | 50-20
2020-12-12 | 50 | 50-20
2020-12-13 | 51 | 51-20
2020-12-14 | 51 | 51-20
2020-12-15 | 51 | 51-20
2020-12-16 | 51 | 51-20
2020-12-17 | 51 | 51-20
2020-12-18 | 51 | 51-20
2020-12-19 | 51 | 51-20
2020-12-20 | 52 | 52-20
2020-12-21 | 52 | 52-20
2020-12-22 | 52 | 52-20
2020-12-23 | 52 | 52-20
2020-12-24 | 52 | 52-20
2020-12-25 | 52 | 52-20
2020-12-26 | 52 | 52-20
2020-12-27 | 53 | 53-20
2020-12-28 | 53 | 53-20
2020-12-29 | 53 | 53-20
2020-12-30 | 53 | 53-20
2020-12-31 | 53 | 53-20
2021-01-01 | 1 | 53-21
2021-01-02 | 1 | 2-10
2021-01-03 | 2 | 2-10
2021-01-04 | 2 | 2-10
2021-01-05 | 2 | 2-10
2021-01-06 | 2 | 2-10
2021-01-07 | 2 | 2-10
2021-01-08 | 2 | 2-10
2021-01-09 | 2 | 3-10
2021-01-10 | 3 | 3-10
2021-01-11 | 3 | 3-10
2021-01-12 | 3 | 3-10
2021-01-13 | 3 | 3-10
2021-01-14 | 3 | 3-10
2021-01-15 | 3 | 3-10
2021-01-16 | 3 | 4-10
2021-01-17 | 4 | 4-10
2021-01-18 | 4 | 4-10
2021-01-19 | 4 | 4-10
2021-01-20 | 4 | 4-10
2021-01-21 | 4 | 4-10
2021-01-22 | 4 | 4-10
2021-01-23 | 4 | 5-10
2021-01-24 | 5 | 5-10
2021-01-25 | 5 | 5-10
2021-01-26 | 5 | 5-10
2021-01-27 | 5 | 5-10
2021-01-28 | 5 | 5-10
2021-01-29 | 5 | 5-10
2021-01-30 | 5 | 6-10
2021-01-31 | 6 | 6-10
2021-02-01 | 6 | 6-10
2021-02-02 | 6 | 6-10
2021-02-03 | 6 | 6-10
2021-02-04 | 6 | 6-10
2021-02-05 | 6 | 6-10
2021-02-06 | 6 | 7-10
2021-02-07 | 7 | 7-10
2021-02-08 | 7 | 7-10
2021-02-09 | 7 | 7-10
2021-02-10 | 7 | 7-10
2021-02-11 | 7 | 7-10
2021-02-12 | 7 | 7-10
2021-02-13 | 7 | 8-10
2021-02-14 | 8 | 8-10
2021-02-15 | 8 | 8-10
2021-02-16 | 8 | 8-10
2021-02-17 | 8 | 8-10
2021-02-18 | 8 | 8-10
2021-02-19 | 8 | 8-10
2021-02-20 | 8 | 9-10
2021-02-21 | 9 | 9-10
2021-02-22 | 9 | 9-10
2021-02-23 | 9 | 9-10
2021-02-24 | 9 | 9-10
2021-02-25 | 9 | 9-10
2021-02-26 | 9 | 9-10
2021-02-27 | 9 | 10-10
2021-02-28 | 10 | 10-10
2021-03-01 | 10 | 10-10
2021-03-02 | 10 | 10-10
2021-03-03 | 10 | 10-10
2021-03-04 | 10 | 10-10
2021-03-05 | 10 | 10-10
2021-03-06 | 10 | 11-10
2021-03-07 | 11 | 11-10
2021-03-08 | 11 | 11-10
2021-03-09 | 11 | 11-10
2021-03-10 | 11 | 11-10
2021-03-11 | 11 | 11-10
2021-03-12 | 11 | 11-10
2021-03-13 | 11 | 12-10
2021-03-14 | 12 | 12-10
2021-03-15 | 12 | 12-10
2021-03-16 | 12 | 12-10
2021-03-17 | 12 | 12-10
2021-03-18 | 12 | 12-10
2021-03-19 | 12 | 12-10
2021-03-20 | 12 | 13-10
2021-03-21 | 13 | 13-10
2021-03-22 | 13 | 13-10
2021-03-23 | 13 | 13-10
2021-03-24 | 13 | 13-10
2021-03-25 | 13 | 13-10
2021-03-26 | 13 | 13-10
2021-03-27 | 13 | 14-10
2021-03-28 | 14 | 14-10
2021-03-29 | 14 | 14-10
2021-03-30 | 14 | 14-10
2021-03-31 | 14 | 14-10
2021-04-01 | 14 | 14-10
2021-04-02 | 14 | 14-10
2021-04-03 | 14 | 15-10
2021-04-04 | 15 | 15-10
2021-04-05 | 15 | 15-10
2021-04-06 | 15 | 15-10
2021-04-07 | 15 | 15-10
2021-04-08 | 15 | 15-10
2021-04-09 | 15 | 15-10
2021-04-10 | 15 | 16-10
2021-04-11 | 16 | 16-10
2021-04-12 | 16 | 16-10
2021-04-13 | 16 | 16-10
2021-04-14 | 16 | 16-10
2021-04-15 | 16 | 16-10
2021-04-16 | 16 | 16-10
2021-04-17 | 16 | 17-10
2021-04-18 | 17 | 17-10
2021-04-19 | 17 | 17-10
2021-04-20 | 17 | 17-10
2021-04-21 | 17 | 17-10
2021-04-22 | 17 | 17-10
2021-04-23 | 17 | 17-10
2021-04-24 | 17 | 18-10
2021-04-25 | 18 | 18-10
2021-04-26 | 18 | 18-10
2021-04-27 | 18 | 18-10
2021-04-28 | 18 | 18-10
2021-04-29 | 18 | 18-10
2021-04-30 | 18 | 18-10
2021-05-01 | 18 | 19-10
2021-05-02 | 19 | 19-10
2021-05-03 | 19 | 19-10
2021-05-04 | 19 | 19-10
2021-05-05 | 19 | 19-10
2021-05-06 | 19 | 19-10
2021-05-07 | 19 | 19-10
2021-05-08 | 19 | 20-10
2021-05-09 | 20 | 20-10
2021-05-10 | 20 | 20-10
2021-05-11 | 20 | 20-10
2021-05-12 | 20 | 20-10
2021-05-13 | 20 | 20-10
2021-05-14 | 20 | 20-10
2021-05-15 | 20 | 21-10
2021-05-16 | 21 | 21-10
2021-05-17 | 21 | 21-10
2021-05-18 | 21 | 21-10
2021-05-19 | 21 | 21-10
2021-05-20 | 21 | 21-10
2021-05-21 | 21 | 21-10
2021-05-22 | 21 | 22-10
2021-05-23 | 22 | 22-10
2021-05-24 | 22 | 22-10
2021-05-25 | 22 | 22-10
2021-05-26 | 22 | 22-10
2021-05-27 | 22 | 22-10
2021-05-28 | 22 | 22-10
2021-05-29 | 22 | 23-10
2021-05-30 | 23 | 23-10
2021-05-31 | 23 | 23-10
2021-06-01 | 23 | 23-10
2021-06-02 | 23 | 23-10
2021-06-03 | 23 | 23-10
2021-06-04 | 23 | 23-10
2021-06-05 | 23 | 24-10
2021-06-06 | 24 | 24-10
2021-06-07 | 24 | 24-10
2021-06-08 | 24 | 24-10
2021-06-09 | 24 | 24-10
2021-06-10 | 24 | 24-10
2021-06-11 | 24 | 24-10
2021-06-12 | 24 | 25-10
2021-06-13 | 25 | 25-10
2021-06-14 | 25 | 25-10
2021-06-15 | 25 | 25-10
2021-06-16 | 25 | 25-10
2021-06-17 | 25 | 25-10
2021-06-18 | 25 | 25-10
2021-06-19 | 25 | 26-10
2021-06-20 | 26 | 26-10
2021-06-21 | 26 | 26-10
2021-06-22 | 26 | 26-10
2021-06-23 | 26 | 26-10
2021-06-24 | 26 | 26-10
2021-06-25 | 26 | 26-10
2021-06-26 | 26 | 27-10
2021-06-27 | 27 | 27-10
2021-06-28 | 27 | 27-10
2021-06-29 | 27 | 27-10
2021-06-30 | 27 | 27-10
2021-07-01 | 27 | 27-10
2021-07-02 | 27 | 27-10
2021-07-03 | 27 | 28-10
2021-07-04 | 28 | 28-10
2021-07-05 | 28 | 28-10
2021-07-06 | 28 | 28-10
2021-07-07 | 28 | 28-10
2021-07-08 | 28 | 28-10
2021-07-09 | 28 | 28-10
2021-07-10 | 28 | 29-10
2021-07-11 | 29 | 29-10
2021-07-12 | 29 | 29-10
2021-07-13 | 29 | 29-10
2021-07-14 | 29 | 29-10
2021-07-15 | 29 | 29-10
2021-07-16 | 29 | 29-10
2021-07-17 | 29 | 30-10
2021-07-18 | 30 | 30-10
2021-07-19 | 30 | 30-10
2021-07-20 | 30 | 30-10
2021-07-21 | 30 | 30-10
2021-07-22 | 30 | 30-10
2021-07-23 | 30 | 30-10
2021-07-24 | 30 | 31-10
2021-07-25 | 31 | 31-10
2021-07-26 | 31 | 31-10
2021-07-27 | 31 | 31-10
2021-07-28 | 31 | 31-10
2021-07-29 | 31 | 31-10
2021-07-30 | 31 | 31-10
2021-07-31 | 31 | 32-10
2021-08-01 | 32 | 32-10
2021-08-02 | 32 | 32-10
2021-08-03 | 32 | 32-10
2021-08-04 | 32 | 32-10
2021-08-05 | 32 | 32-10
2021-08-06 | 32 | 32-10
2021-08-07 | 32 | 33-10
2021-08-08 | 33 | 33-10
2021-08-09 | 33 | 33-10
2021-08-10 | 33 | 33-10
2021-08-11 | 33 | 33-10
2021-08-12 | 33 | 33-10
2021-08-13 | 33 | 33-10
2021-08-14 | 33 | 34-10
2021-08-15 | 34 | 34-10
2021-08-16 | 34 | 34-10
2021-08-17 | 34 | 34-10
2021-08-18 | 34 | 34-10
2021-08-19 | 34 | 34-10
2021-08-20 | 34 | 34-10
2021-08-21 | 34 | 35-10
2021-08-22 | 35 | 35-10
2021-08-23 | 35 | 35-10
2021-08-24 | 35 | 35-10
2021-08-25 | 35 | 35-10
2021-08-26 | 35 | 35-10
2021-08-27 | 35 | 35-10
2021-08-28 | 35 | 36-10
2021-08-29 | 36 | 36-10
2021-08-30 | 36 | 36-10
2021-08-31 | 36 | 36-10
2021-09-01 | 36 | 36-10
2021-09-02 | 36 | 36-10
2021-09-03 | 36 | 36-10
2021-09-04 | 36 | 37-10
2021-09-05 | 37 | 37-10
2021-09-06 | 37 | 37-10
2021-09-07 | 37 | 37-10
2021-09-08 | 37 | 37-10
2021-09-09 | 37 | 37-10
2021-09-10 | 37 | 37-10
2021-09-11 | 37 | 38-10
2021-09-12 | 38 | 38-10
2021-09-13 | 38 | 38-10
2021-09-14 | 38 | 38-10
2021-09-15 | 38 | 38-10
2021-09-16 | 38 | 38-10
2021-09-17 | 38 | 38-10
2021-09-18 | 38 | 39-10
2021-09-19 | 39 | 39-10
2021-09-20 | 39 | 39-10
2021-09-21 | 39 | 39-10
2021-09-22 | 39 | 39-10
2021-09-23 | 39 | 39-10
2021-09-24 | 39 | 39-10
2021-09-25 | 39 | 40-10
2021-09-26 | 40 | 40-10
2021-09-27 | 40 | 40-10
2021-09-28 | 40 | 40-10
2021-09-29 | 40 | 40-10
2021-09-30 | 40 | 40-10
2021-10-01 | 40 | 40-10
2021-10-02 | 40 | 41-10
2021-10-03 | 41 | 41-10
2021-10-04 | 41 | 41-10
2021-10-05 | 41 | 41-10
2021-10-06 | 41 | 41-10
2021-10-07 | 41 | 41-10
2021-10-08 | 41 | 41-10
2021-10-09 | 41 | 42-10
2021-10-10 | 42 | 42-10
2021-10-11 | 42 | 42-10
2021-10-12 | 42 | 42-10
2021-10-13 | 42 | 42-10
2021-10-14 | 42 | 42-10
2021-10-15 | 42 | 42-10
2021-10-16 | 42 | 43-10
2021-10-17 | 43 | 43-10
2021-10-18 | 43 | 43-10
2021-10-19 | 43 | 43-10
2021-10-20 | 43 | 43-10
2021-10-21 | 43 | 43-10
2021-10-22 | 43 | 43-10
2021-10-23 | 43 | 44-10
2021-10-24 | 44 | 44-10
2021-10-25 | 44 | 44-10
2021-10-26 | 44 | 44-10
2021-10-27 | 44 | 44-10
2021-10-28 | 44 | 44-10
2021-10-29 | 44 | 44-10
2021-10-30 | 44 | 45-10
2021-10-31 | 45 | 45-10
2021-11-01 | 45 | 45-10
2021-11-02 | 45 | 45-10
2021-11-03 | 45 | 45-10
2021-11-04 | 45 | 45-10
2021-11-05 | 45 | 45-10
2021-11-06 | 45 | 46-10
2021-11-07 | 46 | 46-10
2021-11-08 | 46 | 46-10
2021-11-09 | 46 | 46-10
2021-11-10 | 46 | 46-10
2021-11-11 | 46 | 46-10
2021-11-12 | 46 | 46-10
2021-11-13 | 46 | 47-10
2021-11-14 | 47 | 47-10
2021-11-15 | 47 | 47-10
2021-11-16 | 47 | 47-10
2021-11-17 | 47 | 47-10
2021-11-18 | 47 | 47-10
2021-11-19 | 47 | 47-10
2021-11-20 | 47 | 48-10
2021-11-21 | 48 | 48-10
2021-11-22 | 48 | 48-10
2021-11-23 | 48 | 48-10
2021-11-24 | 48 | 48-10
2021-11-25 | 48 | 48-10
2021-11-26 | 48 | 48-10
2021-11-27 | 48 | 49-10
2021-11-28 | 49 | 49-10
2021-11-29 | 49 | 49-10
2021-11-30 | 49 | 49-10
2021-12-01 | 49 | 49-10
2021-12-02 | 49 | 49-10
2021-12-03 | 49 | 49-10
2021-12-04 | 49 | 50-10
2021-12-05 | 50 | 50-10
2021-12-06 | 50 | 50-10
2021-12-07 | 50 | 50-10
2021-12-08 | 50 | 50-10
2021-12-09 | 50 | 50-10
2021-12-10 | 50 | 50-10
2021-12-11 | 50 | 51-10
2021-12-12 | 51 | 51-10
2021-12-13 | 51 | 51-10
2021-12-14 | 51 | 51-10
2021-12-15 | 51 | 51-10
2021-12-16 | 51 | 51-10
2021-12-17 | 51 | 51-10
2021-12-18 | 51 | 52-10
2021-12-19 | 52 | 52-10
2021-12-20 | 52 | 52-10
2021-12-21 | 52 | 52-10
2021-12-22 | 52 | 52-10
2021-12-23 | 52 | 52-10
2021-12-24 | 52 | 52-10
2021-12-25 | 52 | 53-10
2021-12-26 | 53 | 53-10
2021-12-27 | 53 | 53-10
2021-12-28 | 53 | 53-10
2021-12-29 | 53 | 53-10
2021-12-30 | 53 | 53-10
2021-12-31 | 53 | 1-11
2022-01-01 | 1 | 2-11
2022-01-02 | 2 | 2-11
2022-01-03 | 2 | 2-11
2022-01-04 | 2 | 2-11
2022-01-05 | 2 | 2-11
2022-01-06 | 2 | 2-11
2022-01-07 | 2 | 2-11
2022-01-08 | 2 | 3-11
2022-01-09 | 3 | 3-11
2022-01-10 | 3 | 3-11
2022-01-11 | 3 | 3-11
2022-01-12 | 3 | 3-11
2022-01-13 | 3 | 3-11
2022-01-14 | 3 | 3-11
2022-01-15 | 3 | 4-11
2022-01-16 | 4 | 4-11
2022-01-17 | 4 | 4-11
2022-01-18 | 4 | 4-11
2022-01-19 | 4 | 4-11
2022-01-20 | 4 | 4-11
2022-01-21 | 4 | 4-11
2022-01-22 | 4 | 5-11
2022-01-23 | 5 | 5-11
2022-01-24 | 5 | 5-11
2022-01-25 | 5 | 5-11
2022-01-26 | 5 | 5-11
2022-01-27 | 5 | 5-11
2022-01-28 | 5 | 5-11
2022-01-29 | 5 | 6-11
2022-01-30 | 6 | 6-11
2022-01-31 | 6 | 6-11
2022-02-01 | 6 | 6-11
2022-02-02 | 6 | 6-11
2022-02-03 | 6 | 6-11
2022-02-04 | 6 | 6-11
2022-02-05 | 6 | 7-11
2022-02-06 | 7 | 7-11
2022-02-07 | 7 | 7-11
2022-02-08 | 7 | 7-11
2022-02-09 | 7 | 7-11
2022-02-10 | 7 | 7-11
2022-02-11 | 7 | 7-11
2022-02-12 | 7 | 8-11
2022-02-13 | 8 | 8-11
2022-02-14 | 8 | 8-11
2022-02-15 | 8 | 8-11
2022-02-16 | 8 | 8-11
2022-02-17 | 8 | 8-11
2022-02-18 | 8 | 8-11
2022-02-19 | 8 | 9-11
2022-02-20 | 9 | 9-11
2022-02-21 | 9 | 9-11
2022-02-22 | 9 | 9-11
2022-02-23 | 9 | 9-11
2022-02-24 | 9 | 9-11
2022-02-25 | 9 | 9-11
2022-02-26 | 9 | 10-11
2022-02-27 | 10 | 10-11
2022-02-28 | 10 | 10-11
2022-03-01 | 10 | 10-11
2022-03-02 | 10 | 10-11
2022-03-03 | 10 | 10-11
2022-03-04 | 10 | 10-11
2022-03-05 | 10 | 11-11
2022-03-06 | 11 | 11-11
2022-03-07 | 11 | 11-11
2022-03-08 | 11 | 11-11
2022-03-09 | 11 | 11-11
2022-03-10 | 11 | 11-11
2022-03-11 | 11 | 11-11
2022-03-12 | 11 | 12-11
2022-03-13 | 12 | 12-11
2022-03-14 | 12 | 12-11
2022-03-15 | 12 | 12-11
2022-03-16 | 12 | 12-11
2022-03-17 | 12 | 12-11
2022-03-18 | 12 | 12-11
2022-03-19 | 12 | 13-11
2022-03-20 | 13 | 13-11
2022-03-21 | 13 | 13-11
2022-03-22 | 13 | 13-11
2022-03-23 | 13 | 13-11
2022-03-24 | 13 | 13-11
2022-03-25 | 13 | 13-11
2022-03-26 | 13 | 14-11
2022-03-27 | 14 | 14-11
2022-03-28 | 14 | 14-11
2022-03-29 | 14 | 14-11
2022-03-30 | 14 | 14-11
2022-03-31 | 14 | 14-11
2022-04-01 | 14 | 14-11
2022-04-02 | 14 | 15-11
2022-04-03 | 15 | 15-11
2022-04-04 | 15 | 15-11
2022-04-05 | 15 | 15-11
2022-04-06 | 15 | 15-11
2022-04-07 | 15 | 15-11
2022-04-08 | 15 | 15-11
2022-04-09 | 15 | 16-11
2022-04-10 | 16 | 16-11
2022-04-11 | 16 | 16-11
2022-04-12 | 16 | 16-11
2022-04-13 | 16 | 16-11
2022-04-14 | 16 | 16-11
2022-04-15 | 16 | 16-11
2022-04-16 | 16 | 17-11
2022-04-17 | 17 | 17-11
2022-04-18 | 17 | 17-11
2022-04-19 | 17 | 17-11
2022-04-20 | 17 | 17-11
2022-04-21 | 17 | 17-11
2022-04-22 | 17 | 17-11
2022-04-23 | 17 | 18-11
2022-04-24 | 18 | 18-11
2022-04-25 | 18 | 18-11
2022-04-26 | 18 | 18-11
2022-04-27 | 18 | 18-11
2022-04-28 | 18 | 18-11
2022-04-29 | 18 | 18-11
2022-04-30 | 18 | 19-11
2022-05-01 | 19 | 19-11
2022-05-02 | 19 | 19-11
2022-05-03 | 19 | 19-11
2022-05-04 | 19 | 19-11
2022-05-05 | 19 | 19-11
2022-05-06 | 19 | 19-11
2022-05-07 | 19 | 20-11
2022-05-08 | 20 | 20-11
2022-05-09 | 20 | 20-11
2022-05-10 | 20 | 20-11
2022-05-11 | 20 | 20-11
2022-05-12 | 20 | 20-11
2022-05-13 | 20 | 20-11
2022-05-14 | 20 | 21-11
2022-05-15 | 21 | 21-11
2022-05-16 | 21 | 21-11
2022-05-17 | 21 | 21-11
2022-05-18 | 21 | 21-11
2022-05-19 | 21 | 21-11
2022-05-20 | 21 | 21-11
2022-05-21 | 21 | 22-11
2022-05-22 | 22 | 22-11
2022-05-23 | 22 | 22-11
2022-05-24 | 22 | 22-11
2022-05-25 | 22 | 22-11
2022-05-26 | 22 | 22-11
2022-05-27 | 22 | 22-11
2022-05-28 | 22 | 23-11
2022-05-29 | 23 | 23-11
2022-05-30 | 23 | 23-11
2022-05-31 | 23 | 23-11
2022-06-01 | 23 | 23-11
2022-06-02 | 23 | 23-11
2022-06-03 | 23 | 23-11
2022-06-04 | 23 | 24-11
2022-06-05 | 24 | 24-11
2022-06-06 | 24 | 24-11
2022-06-07 | 24 | 24-11
2022-06-08 | 24 | 24-11
2022-06-09 | 24 | 24-11
2022-06-10 | 24 | 24-11
2022-06-11 | 24 | 25-11
2022-06-12 | 25 | 25-11
2022-06-13 | 25 | 25-11
2022-06-14 | 25 | 25-11
2022-06-15 | 25 | 25-11
2022-06-16 | 25 | 25-11
2022-06-17 | 25 | 25-11
2022-06-18 | 25 | 26-11
2022-06-19 | 26 | 26-11
2022-06-20 | 26 | 26-11
2022-06-21 | 26 | 26-11
2022-06-22 | 26 | 26-11
2022-06-23 | 26 | 26-11
2022-06-24 | 26 | 26-11
2022-06-25 | 26 | 27-11
2022-06-26 | 27 | 27-11
2022-06-27 | 27 | 27-11
2022-06-28 | 27 | 27-11
2022-06-29 | 27 | 27-11
2022-06-30 | 27 | 27-11
2022-07-01 | 27 | 27-11
2022-07-02 | 27 | 28-11
2022-07-03 | 28 | 28-11
2022-07-04 | 28 | 28-11
2022-07-05 | 28 | 28-11
2022-07-06 | 28 | 28-11
2022-07-07 | 28 | 28-11
2022-07-08 | 28 | 28-11
2022-07-09 | 28 | 29-11
2022-07-10 | 29 | 29-11
2022-07-11 | 29 | 29-11
2022-07-12 | 29 | 29-11
2022-07-13 | 29 | 29-11
2022-07-14 | 29 | 29-11
2022-07-15 | 29 | 29-11
2022-07-16 | 29 | 30-11
2022-07-17 | 30 | 30-11
2022-07-18 | 30 | 30-11
2022-07-19 | 30 | 30-11
2022-07-20 | 30 | 30-11
2022-07-21 | 30 | 30-11
2022-07-22 | 30 | 30-11
2022-07-23 | 30 | 31-11
2022-07-24 | 31 | 31-11
2022-07-25 | 31 | 31-11
2022-07-26 | 31 | 31-11
2022-07-27 | 31 | 31-11
2022-07-28 | 31 | 31-11
2022-07-29 | 31 | 31-11
2022-07-30 | 31 | 32-11
2022-07-31 | 32 | 32-11
2022-08-01 | 32 | 32-11
2022-08-02 | 32 | 32-11
2022-08-03 | 32 | 32-11
2022-08-04 | 32 | 32-11
2022-08-05 | 32 | 32-11
2022-08-06 | 32 | 33-11
2022-08-07 | 33 | 33-11
2022-08-08 | 33 | 33-11
2022-08-09 | 33 | 33-11
2022-08-10 | 33 | 33-11
2022-08-11 | 33 | 33-11
2022-08-12 | 33 | 33-11
2022-08-13 | 33 | 34-11
2022-08-14 | 34 | 34-11
2022-08-15 | 34 | 34-11
2022-08-16 | 34 | 34-11
2022-08-17 | 34 | 34-11
2022-08-18 | 34 | 34-11
2022-08-19 | 34 | 34-11
2022-08-20 | 34 | 35-11
2022-08-21 | 35 | 35-11
2022-08-22 | 35 | 35-11
2022-08-23 | 35 | 35-11
2022-08-24 | 35 | 35-11
2022-08-25 | 35 | 35-11
2022-08-26 | 35 | 35-11
2022-08-27 | 35 | 36-11
2022-08-28 | 36 | 36-11
2022-08-29 | 36 | 36-11
2022-08-30 | 36 | 36-11
2022-08-31 | 36 | 36-11
2022-09-01 | 36 | 36-11
2022-09-02 | 36 | 36-11
2022-09-03 | 36 | 37-11
2022-09-04 | 37 | 37-11
2022-09-05 | 37 | 37-11
2022-09-06 | 37 | 37-11
2022-09-07 | 37 | 37-11
2022-09-08 | 37 | 37-11
2022-09-09 | 37 | 37-11
2022-09-10 | 37 | 38-11
2022-09-11 | 38 | 38-11
2022-09-12 | 38 | 38-11
2022-09-13 | 38 | 38-11
2022-09-14 | 38 | 38-11
2022-09-15 | 38 | 38-11
2022-09-16 | 38 | 38-11
2022-09-17 | 38 | 39-11
2022-09-18 | 39 | 39-11
2022-09-19 | 39 | 39-11
2022-09-20 | 39 | 39-11
2022-09-21 | 39 | 39-11
2022-09-22 | 39 | 39-11
2022-09-23 | 39 | 39-11
2022-09-24 | 39 | 40-11
2022-09-25 | 40 | 40-11
2022-09-26 | 40 | 40-11
2022-09-27 | 40 | 40-11
2022-09-28 | 40 | 40-11
2022-09-29 | 40 | 40-11
2022-09-30 | 40 | 40-11
2022-10-01 | 40 | 41-11
2022-10-02 | 41 | 41-11
2022-10-03 | 41 | 41-11
2022-10-04 | 41 | 41-11
2022-10-05 | 41 | 41-11
2022-10-06 | 41 | 41-11
2022-10-07 | 41 | 41-11
2022-10-08 | 41 | 42-11
2022-10-09 | 42 | 42-11
2022-10-10 | 42 | 42-11
2022-10-11 | 42 | 42-11
2022-10-12 | 42 | 42-11
2022-10-13 | 42 | 42-11
2022-10-14 | 42 | 42-11
2022-10-15 | 42 | 43-11
2022-10-16 | 43 | 43-11
2022-10-17 | 43 | 43-11
2022-10-18 | 43 | 43-11
2022-10-19 | 43 | 43-11
2022-10-20 | 43 | 43-11
2022-10-21 | 43 | 43-11
2022-10-22 | 43 | 44-11
2022-10-23 | 44 | 44-11
2022-10-24 | 44 | 44-11
2022-10-25 | 44 | 44-11
2022-10-26 | 44 | 44-11
2022-10-27 | 44 | 44-11
2022-10-28 | 44 | 44-11
2022-10-29 | 44 | 45-11
2022-10-30 | 45 | 45-11
2022-10-31 | 45 | 45-11
2022-11-01 | 45 | 45-11
2022-11-02 | 45 | 45-11
2022-11-03 | 45 | 45-11
2022-11-04 | 45 | 45-11
2022-11-05 | 45 | 46-11
2022-11-06 | 46 | 46-11
2022-11-07 | 46 | 46-11
2022-11-08 | 46 | 46-11
2022-11-09 | 46 | 46-11
2022-11-10 | 46 | 46-11
2022-11-11 | 46 | 46-11
2022-11-12 | 46 | 47-11
2022-11-13 | 47 | 47-11
2022-11-14 | 47 | 47-11
2022-11-15 | 47 | 47-11
2022-11-16 | 47 | 47-11
2022-11-17 | 47 | 47-11
2022-11-18 | 47 | 47-11
2022-11-19 | 47 | 48-11
2022-11-20 | 48 | 48-11
2022-11-21 | 48 | 48-11
2022-11-22 | 48 | 48-11
2022-11-23 | 48 | 48-11
2022-11-24 | 48 | 48-11
2022-11-25 | 48 | 48-11
2022-11-26 | 48 | 49-11
2022-11-27 | 49 | 49-11
2022-11-28 | 49 | 49-11
2022-11-29 | 49 | 49-11
2022-11-30 | 49 | 49-11
2022-12-01 | 49 | 49-11
2022-12-02 | 49 | 49-11
2022-12-03 | 49 | 50-11
2022-12-04 | 50 | 50-11
2022-12-05 | 50 | 50-11
2022-12-06 | 50 | 50-11
2022-12-07 | 50 | 50-11
2022-12-08 | 50 | 50-11
2022-12-09 | 50 | 50-11
2022-12-10 | 50 | 51-11
2022-12-11 | 51 | 51-11
2022-12-12 | 51 | 51-11
2022-12-13 | 51 | 51-11
2022-12-14 | 51 | 51-11
2022-12-15 | 51 | 51-11
2022-12-16 | 51 | 51-11
2022-12-17 | 51 | 52-11
2022-12-18 | 52 | 52-11
2022-12-19 | 52 | 52-11
2022-12-20 | 52 | 52-11
2022-12-21 | 52 | 52-11
2022-12-22 | 52 | 52-11
2022-12-23 | 52 | 52-11
2022-12-24 | 52 | 53-11
2022-12-25 | 53 | 53-11
2022-12-26 | 53 | 53-11
2022-12-27 | 53 | 53-11
2022-12-28 | 53 | 53-11
2022-12-29 | 53 | 53-11
2022-12-30 | 53 | 53-11
2022-12-31 | 53 | 1-12
2023-01-01 | 1 | 1-12
2023-01-02 | 1 | 1-12
2023-01-03 | 1 | 1-12
2023-01-04 | 1 | 1-12
2023-01-05 | 1 | 1-12
2023-01-06 | 1 | 1-12
2023-01-07 | 1 | 2-12
2023-01-08 | 2 | 2-12
2023-01-09 | 2 | 2-12
2023-01-10 | 2 | 2-12
2023-01-11 | 2 | 2-12
2023-01-12 | 2 | 2-12
2023-01-13 | 2 | 2-12
2023-01-14 | 2 | 3-12
2023-01-15 | 3 | 3-12
2023-01-16 | 3 | 3-12
2023-01-17 | 3 | 3-12
2023-01-18 | 3 | 3-12
2023-01-19 | 3 | 3-12
2023-01-20 | 3 | 3-12
2023-01-21 | 3 | 4-12
2023-01-22 | 4 | 4-12
2023-01-23 | 4 | 4-12
2023-01-24 | 4 | 4-12
2023-01-25 | 4 | 4-12
2023-01-26 | 4 | 4-12
2023-01-27 | 4 | 4-12
2023-01-28 | 4 | 5-12
2023-01-29 | 5 | 5-12
2023-01-30 | 5 | 5-12
2023-01-31 | 5 | 5-12
2023-02-01 | 5 | 5-12
2023-02-02 | 5 | 5-12
2023-02-03 | 5 | 5-12
2023-02-04 | 5 | 6-12
2023-02-05 | 6 | 6-12
2023-02-06 | 6 | 6-12
2023-02-07 | 6 | 6-12
2023-02-08 | 6 | 6-12
2023-02-09 | 6 | 6-12
2023-02-10 | 6 | 6-12
2023-02-11 | 6 | 7-12
2023-02-12 | 7 | 7-12
2023-02-13 | 7 | 7-12
2023-02-14 | 7 | 7-12
2023-02-15 | 7 | 7-12
2023-02-16 | 7 | 7-12
2023-02-17 | 7 | 7-12
2023-02-18 | 7 | 8-12
2023-02-19 | 8 | 8-12
2023-02-20 | 8 | 8-12
2023-02-21 | 8 | 8-12
2023-02-22 | 8 | 8-12
2023-02-23 | 8 | 8-12
2023-02-24 | 8 | 8-12
2023-02-25 | 8 | 9-12
2023-02-26 | 9 | 9-12
2023-02-27 | 9 | 9-12
2023-02-28 | 9 | 9-12
2023-03-01 | 9 | 9-12
2023-03-02 | 9 | 9-12
2023-03-03 | 9 | 9-12
2023-03-04 | 9 | 10-12
2023-03-05 | 10 | 10-12
2023-03-06 | 10 | 10-12
2023-03-07 | 10 | 10-12
2023-03-08 | 10 | 10-12
2023-03-09 | 10 | 10-12
2023-03-10 | 10 | 10-12
2023-03-11 | 10 | 11-12
2023-03-12 | 11 | 11-12
2023-03-13 | 11 | 11-12
2023-03-14 | 11 | 11-12
2023-03-15 | 11 | 11-12
2023-03-16 | 11 | 11-12
2023-03-17 | 11 | 11-12
2023-03-18 | 11 | 12-12
2023-03-19 | 12 | 12-12
2023-03-20 | 12 | 12-12
2023-03-21 | 12 | 12-12
2023-03-22 | 12 | 12-12
2023-03-23 | 12 | 12-12
2023-03-24 | 12 | 12-12
2023-03-25 | 12 | 13-12
2023-03-26 | 13 | 13-12
2023-03-27 | 13 | 13-12
2023-03-28 | 13 | 13-12
2023-03-29 | 13 | 13-12
2023-03-30 | 13 | 13-12
2023-03-31 | 13 | 13-12
2023-04-01 | 13 | 14-12
2023-04-02 | 14 | 14-12
2023-04-03 | 14 | 14-12
2023-04-04 | 14 | 14-12
2023-04-05 | 14 | 14-12
2023-04-06 | 14 | 14-12
2023-04-07 | 14 | 14-12
2023-04-08 | 14 | 15-12
2023-04-09 | 15 | 15-12
2023-04-10 | 15 | 15-12
2023-04-11 | 15 | 15-12
2023-04-12 | 15 | 15-12
2023-04-13 | 15 | 15-12
2023-04-14 | 15 | 15-12
2023-04-15 | 15 | 16-12
2023-04-16 | 16 | 16-12
2023-04-17 | 16 | 16-12
2023-04-18 | 16 | 16-12
2023-04-19 | 16 | 16-12
2023-04-20 | 16 | 16-12
2023-04-21 | 16 | 16-12
2023-04-22 | 16 | 17-12
2023-04-23 | 17 | 17-12
2023-04-24 | 17 | 17-12
2023-04-25 | 17 | 17-12
2023-04-26 | 17 | 17-12
2023-04-27 | 17 | 17-12
2023-04-28 | 17 | 17-12
2023-04-29 | 17 | 18-12
2023-04-30 | 18 | 18-12
2023-05-01 | 18 | 18-12
2023-05-02 | 18 | 18-12
2023-05-03 | 18 | 18-12
2023-05-04 | 18 | 18-12
2023-05-05 | 18 | 18-12
2023-05-06 | 18 | 19-12
2023-05-07 | 19 | 19-12
2023-05-08 | 19 | 19-12
2023-05-09 | 19 | 19-12
2023-05-10 | 19 | 19-12
2023-05-11 | 19 | 19-12
2023-05-12 | 19 | 19-12
2023-05-13 | 19 | 20-12
2023-05-14 | 20 | 20-12
2023-05-15 | 20 | 20-12
2023-05-16 | 20 | 20-12
2023-05-17 | 20 | 20-12
2023-05-18 | 20 | 20-12
2023-05-19 | 20 | 20-12
2023-05-20 | 20 | 21-12
2023-05-21 | 21 | 21-12
2023-05-22 | 21 | 21-12
2023-05-23 | 21 | 21-12
2023-05-24 | 21 | 21-12
2023-05-25 | 21 | 21-12
2023-05-26 | 21 | 21-12
2023-05-27 | 21 | 22-12
2023-05-28 | 22 | 22-12
2023-05-29 | 22 | 22-12
2023-05-30 | 22 | 22-12
2023-05-31 | 22 | 22-12
2023-06-01 | 22 | 22-12
2023-06-02 | 22 | 22-12
2023-06-03 | 22 | 23-12
2023-06-04 | 23 | 23-12
2023-06-05 | 23 | 23-12
2023-06-06 | 23 | 23-12
2023-06-07 | 23 | 23-12
2023-06-08 | 23 | 23-12
2023-06-09 | 23 | 23-12
2023-06-10 | 23 | 24-12
2023-06-11 | 24 | 24-12
2023-06-12 | 24 | 24-12
2023-06-13 | 24 | 24-12
2023-06-14 | 24 | 24-12
2023-06-15 | 24 | 24-12
2023-06-16 | 24 | 24-12
2023-06-17 | 24 | 25-12
2023-06-18 | 25 | 25-12
2023-06-19 | 25 | 25-12
2023-06-20 | 25 | 25-12
2023-06-21 | 25 | 25-12
2023-06-22 | 25 | 25-12
2023-06-23 | 25 | 25-12
2023-06-24 | 25 | 26-12
2023-06-25 | 26 | 26-12
2023-06-26 | 26 | 26-12
2023-06-27 | 26 | 26-12
2023-06-28 | 26 | 26-12
2023-06-29 | 26 | 26-12
2023-06-30 | 26 | 26-12
2023-07-01 | 26 | 27-12
2023-07-02 | 27 | 27-12
2023-07-03 | 27 | 27-12
2023-07-04 | 27 | 27-12
2023-07-05 | 27 | 27-12
2023-07-06 | 27 | 27-12
2023-07-07 | 27 | 27-12
2023-07-08 | 27 | 28-12
2023-07-09 | 28 | 28-12
2023-07-10 | 28 | 28-12
2023-07-11 | 28 | 28-12
2023-07-12 | 28 | 28-12
2023-07-13 | 28 | 28-12
2023-07-14 | 28 | 28-12
2023-07-15 | 28 | 29-12
2023-07-16 | 29 | 29-12
2023-07-17 | 29 | 29-12
2023-07-18 | 29 | 29-12
2023-07-19 | 29 | 29-12
2023-07-20 | 29 | 29-12
2023-07-21 | 29 | 29-12
2023-07-22 | 29 | 30-12
2023-07-23 | 30 | 30-12
2023-07-24 | 30 | 30-12
2023-07-25 | 30 | 30-12
2023-07-26 | 30 | 30-12
2023-07-27 | 30 | 30-12
2023-07-28 | 30 | 30-12
2023-07-29 | 30 | 31-12
2023-07-30 | 31 | 31-12
2023-07-31 | 31 | 31-12
2023-08-01 | 31 | 31-12
2023-08-02 | 31 | 31-12
2023-08-03 | 31 | 31-12
2023-08-04 | 31 | 31-12
2023-08-05 | 31 | 32-12
2023-08-06 | 32 | 32-12
2023-08-07 | 32 | 32-12
2023-08-08 | 32 | 32-12
2023-08-09 | 32 | 32-12
2023-08-10 | 32 | 32-12
2023-08-11 | 32 | 32-12
2023-08-12 | 32 | 33-12
2023-08-13 | 33 | 33-12
2023-08-14 | 33 | 33-12
2023-08-15 | 33 | 33-12
2023-08-16 | 33 | 33-12
2023-08-17 | 33 | 33-12
2023-08-18 | 33 | 33-12
2023-08-19 | 33 | 34-12
2023-08-20 | 34 | 34-12
2023-08-21 | 34 | 34-12
2023-08-22 | 34 | 34-12
2023-08-23 | 34 | 34-12
2023-08-24 | 34 | 34-12
2023-08-25 | 34 | 34-12
2023-08-26 | 34 | 35-12
2023-08-27 | 35 | 35-12
2023-08-28 | 35 | 35-12
2023-08-29 | 35 | 35-12
2023-08-30 | 35 | 35-12
2023-08-31 | 35 | 35-12
2023-09-01 | 35 | 35-12
2023-09-02 | 35 | 36-12
2023-09-03 | 36 | 36-12
2023-09-04 | 36 | 36-12
2023-09-05 | 36 | 36-12
2023-09-06 | 36 | 36-12
2023-09-07 | 36 | 36-12
2023-09-08 | 36 | 36-12
2023-09-09 | 36 | 37-12
2023-09-10 | 37 | 37-12
2023-09-11 | 37 | 37-12
2023-09-12 | 37 | 37-12
2023-09-13 | 37 | 37-12
2023-09-14 | 37 | 37-12
2023-09-15 | 37 | 37-12
2023-09-16 | 37 | 38-12
2023-09-17 | 38 | 38-12
2023-09-18 | 38 | 38-12
2023-09-19 | 38 | 38-12
2023-09-20 | 38 | 38-12
2023-09-21 | 38 | 38-12
2023-09-22 | 38 | 38-12
2023-09-23 | 38 | 39-12
2023-09-24 | 39 | 39-12
2023-09-25 | 39 | 39-12
2023-09-26 | 39 | 39-12
2023-09-27 | 39 | 39-12
2023-09-28 | 39 | 39-12
2023-09-29 | 39 | 39-12
2023-09-30 | 39 | 40-12
2023-10-01 | 40 | 40-12
2023-10-02 | 40 | 40-12
2023-10-03 | 40 | 40-12
2023-10-04 | 40 | 40-12
2023-10-05 | 40 | 40-12
2023-10-06 | 40 | 40-12
2023-10-07 | 40 | 41-12
2023-10-08 | 41 | 41-12
2023-10-09 | 41 | 41-12
2023-10-10 | 41 | 41-12
2023-10-11 | 41 | 41-12
2023-10-12 | 41 | 41-12
2023-10-13 | 41 | 41-12
2023-10-14 | 41 | 42-12
2023-10-15 | 42 | 42-12
2023-10-16 | 42 | 42-12
2023-10-17 | 42 | 42-12
2023-10-18 | 42 | 42-12
2023-10-19 | 42 | 42-12
2023-10-20 | 42 | 42-12
2023-10-21 | 42 | 43-12
2023-10-22 | 43 | 43-12
2023-10-23 | 43 | 43-12
2023-10-24 | 43 | 43-12
2023-10-25 | 43 | 43-12
2023-10-26 | 43 | 43-12
2023-10-27 | 43 | 43-12
2023-10-28 | 43 | 44-12
2023-10-29 | 44 | 44-12
2023-10-30 | 44 | 44-12
2023-10-31 | 44 | 44-12
2023-11-01 | 44 | 44-12
2023-11-02 | 44 | 44-12
2023-11-03 | 44 | 44-12
2023-11-04 | 44 | 45-12
2023-11-05 | 45 | 45-12
2023-11-06 | 45 | 45-12
2023-11-07 | 45 | 45-12
2023-11-08 | 45 | 45-12
2023-11-09 | 45 | 45-12
2023-11-10 | 45 | 45-12
2023-11-11 | 45 | 46-12
2023-11-12 | 46 | 46-12
2023-11-13 | 46 | 46-12
2023-11-14 | 46 | 46-12
2023-11-15 | 46 | 46-12
2023-11-16 | 46 | 46-12
2023-11-17 | 46 | 46-12
2023-11-18 | 46 | 47-12
2023-11-19 | 47 | 47-12
2023-11-20 | 47 | 47-12
2023-11-21 | 47 | 47-12
2023-11-22 | 47 | 47-12
2023-11-23 | 47 | 47-12
2023-11-24 | 47 | 47-12
2023-11-25 | 47 | 48-12
2023-11-26 | 48 | 48-12
2023-11-27 | 48 | 48-12
2023-11-28 | 48 | 48-12
2023-11-29 | 48 | 48-12
2023-11-30 | 48 | 48-12
2023-12-01 | 48 | 48-12
2023-12-02 | 48 | 49-12
2023-12-03 | 49 | 49-12
2023-12-04 | 49 | 49-12
2023-12-05 | 49 | 49-12
2023-12-06 | 49 | 49-12
2023-12-07 | 49 | 49-12
2023-12-08 | 49 | 49-12
2023-12-09 | 49 | 50-12
2023-12-10 | 50 | 50-12
2023-12-11 | 50 | 50-12
2023-12-12 | 50 | 50-12
2023-12-13 | 50 | 50-12
2023-12-14 | 50 | 50-12
2023-12-15 | 50 | 50-12
2023-12-16 | 50 | 51-12
2023-12-17 | 51 | 51-12
2023-12-18 | 51 | 51-12
2023-12-19 | 51 | 51-12
2023-12-20 | 51 | 51-12
2023-12-21 | 51 | 51-12
2023-12-22 | 51 | 51-12
2023-12-23 | 51 | 52-12
2023-12-24 | 52 | 52-12
2023-12-25 | 52 | 52-12
2023-12-26 | 52 | 52-12
2023-12-27 | 52 | 52-12
2023-12-28 | 52 | 52-12
2023-12-29 | 52 | 52-12
2023-12-30 | 52 | 53-12
2023-12-31 | 53 | 53-12
2024-01-01 | 1 | 1-13
2024-01-02 | 1 | 1-13
2024-01-03 | 1 | 1-13
2024-01-04 | 1 | 1-13
2024-01-05 | 1 | 1-13
2024-01-06 | 1 | 2-13
2024-01-07 | 2 | 2-13
2024-01-08 | 2 | 2-13
2024-01-09 | 2 | 2-13
2024-01-10 | 2 | 2-13
2024-01-11 | 2 | 2-13
2024-01-12 | 2 | 2-13
2024-01-13 | 2 | 3-13
2024-01-14 | 3 | 3-13
2024-01-15 | 3 | 3-13
2024-01-16 | 3 | 3-13
2024-01-17 | 3 | 3-13
2024-01-18 | 3 | 3-13
2024-01-19 | 3 | 3-13
2024-01-20 | 3 | 4-13
2024-01-21 | 4 | 4-13
2024-01-22 | 4 | 4-13
2024-01-23 | 4 | 4-13
2024-01-24 | 4 | 4-13
2024-01-25 | 4 | 4-13
2024-01-26 | 4 | 4-13
2024-01-27 | 4 | 5-13
2024-01-28 | 5 | 5-13
2024-01-29 | 5 | 5-13
2024-01-30 | 5 | 5-13
2024-01-31 | 5 | 5-13
2024-02-01 | 5 | 5-13
2024-02-02 | 5 | 5-13
2024-02-03 | 5 | 6-13
2024-02-04 | 6 | 6-13
2024-02-05 | 6 | 6-13
2024-02-06 | 6 | 6-13
2024-02-07 | 6 | 6-13
2024-02-08 | 6 | 6-13
2024-02-09 | 6 | 6-13
2024-02-10 | 6 | 7-13
2024-02-11 | 7 | 7-13
2024-02-12 | 7 | 7-13
2024-02-13 | 7 | 7-13
2024-02-14 | 7 | 7-13
2024-02-15 | 7 | 7-13
2024-02-16 | 7 | 7-13
2024-02-17 | 7 | 8-13
2024-02-18 | 8 | 8-13
2024-02-19 | 8 | 8-13
2024-02-20 | 8 | 8-13
2024-02-21 | 8 | 8-13
2024-02-22 | 8 | 8-13
2024-02-23 | 8 | 8-13
2024-02-24 | 8 | 9-13
2024-02-25 | 9 | 9-13
2024-02-26 | 9 | 9-13
2024-02-27 | 9 | 9-13
2024-02-28 | 9 | 9-13
2024-02-29 | 9 | 9-13
2024-03-01 | 9 | 9-13
2024-03-02 | 9 | 10-13
2024-03-03 | 10 | 10-13
2024-03-04 | 10 | 10-13
2024-03-05 | 10 | 10-13
2024-03-06 | 10 | 10-13
2024-03-07 | 10 | 10-13
2024-03-08 | 10 | 10-13
2024-03-09 | 10 | 11-13
2024-03-10 | 11 | 11-13
2024-03-11 | 11 | 11-13
2024-03-12 | 11 | 11-13
2024-03-13 | 11 | 11-13
2024-03-14 | 11 | 11-13
2024-03-15 | 11 | 11-13
2024-03-16 | 11 | 12-13
2024-03-17 | 12 | 12-13
2024-03-18 | 12 | 12-13
2024-03-19 | 12 | 12-13
2024-03-20 | 12 | 12-13
2024-03-21 | 12 | 12-13
2024-03-22 | 12 | 12-13
2024-03-23 | 12 | 13-13
2024-03-24 | 13 | 13-13
2024-03-25 | 13 | 13-13
2024-03-26 | 13 | 13-13
2024-03-27 | 13 | 13-13
2024-03-28 | 13 | 13-13
2024-03-29 | 13 | 13-13
2024-03-30 | 13 | 14-13
2024-03-31 | 14 | 14-13
2024-04-01 | 14 | 14-13
2024-04-02 | 14 | 14-13
2024-04-03 | 14 | 14-13
2024-04-04 | 14 | 14-13
2024-04-05 | 14 | 14-13
2024-04-06 | 14 | 15-13
2024-04-07 | 15 | 15-13
2024-04-08 | 15 | 15-13
2024-04-09 | 15 | 15-13
2024-04-10 | 15 | 15-13
2024-04-11 | 15 | 15-13
2024-04-12 | 15 | 15-13
2024-04-13 | 15 | 16-13
2024-04-14 | 16 | 16-13
2024-04-15 | 16 | 16-13
2024-04-16 | 16 | 16-13
2024-04-17 | 16 | 16-13
2024-04-18 | 16 | 16-13
2024-04-19 | 16 | 16-13
2024-04-20 | 16 | 17-13
2024-04-21 | 17 | 17-13
2024-04-22 | 17 | 17-13
2024-04-23 | 17 | 17-13
2024-04-24 | 17 | 17-13
2024-04-25 | 17 | 17-13
2024-04-26 | 17 | 17-13
2024-04-27 | 17 | 18-13
2024-04-28 | 18 | 18-13
2024-04-29 | 18 | 18-13
2024-04-30 | 18 | 18-13
2024-05-01 | 18 | 18-13
2024-05-02 | 18 | 18-13
2024-05-03 | 18 | 18-13
2024-05-04 | 18 | 19-13
2024-05-05 | 19 | 19-13
2024-05-06 | 19 | 19-13
2024-05-07 | 19 | 19-13
2024-05-08 | 19 | 19-13
2024-05-09 | 19 | 19-13
2024-05-10 | 19 | 19-13
2024-05-11 | 19 | 20-13
2024-05-12 | 20 | 20-13
2024-05-13 | 20 | 20-13
2024-05-14 | 20 | 20-13
2024-05-15 | 20 | 20-13
2024-05-16 | 20 | 20-13
2024-05-17 | 20 | 20-13
2024-05-18 | 20 | 21-13
2024-05-19 | 21 | 21-13
2024-05-20 | 21 | 21-13
2024-05-21 | 21 | 21-13
2024-05-22 | 21 | 21-13
2024-05-23 | 21 | 21-13
2024-05-24 | 21 | 21-13
2024-05-25 | 21 | 22-13
2024-05-26 | 22 | 22-13
2024-05-27 | 22 | 22-13
2024-05-28 | 22 | 22-13
2024-05-29 | 22 | 22-13
2024-05-30 | 22 | 22-13
2024-05-31 | 22 | 22-13
2024-06-01 | 22 | 23-13
2024-06-02 | 23 | 23-13
2024-06-03 | 23 | 23-13
2024-06-04 | 23 | 23-13
2024-06-05 | 23 | 23-13
2024-06-06 | 23 | 23-13
2024-06-07 | 23 | 23-13
2024-06-08 | 23 | 24-13
2024-06-09 | 24 | 24-13
2024-06-10 | 24 | 24-13
2024-06-11 | 24 | 24-13
2024-06-12 | 24 | 24-13
2024-06-13 | 24 | 24-13
2024-06-14 | 24 | 24-13
2024-06-15 | 24 | 25-13
2024-06-16 | 25 | 25-13
2024-06-17 | 25 | 25-13
2024-06-18 | 25 | 25-13
2024-06-19 | 25 | 25-13
2024-06-20 | 25 | 25-13
2024-06-21 | 25 | 25-13
2024-06-22 | 25 | 26-13
2024-06-23 | 26 | 26-13
2024-06-24 | 26 | 26-13
2024-06-25 | 26 | 26-13
2024-06-26 | 26 | 26-13
2024-06-27 | 26 | 26-13
2024-06-28 | 26 | 26-13
2024-06-29 | 26 | 27-13
2024-06-30 | 27 | 27-13
2024-07-01 | 27 | 27-13
2024-07-02 | 27 | 27-13
2024-07-03 | 27 | 27-13
2024-07-04 | 27 | 27-13
2024-07-05 | 27 | 27-13
2024-07-06 | 27 | 28-13
2024-07-07 | 28 | 28-13
2024-07-08 | 28 | 28-13
2024-07-09 | 28 | 28-13
2024-07-10 | 28 | 28-13
2024-07-11 | 28 | 28-13
2024-07-12 | 28 | 28-13
2024-07-13 | 28 | 29-13
2024-07-14 | 29 | 29-13
2024-07-15 | 29 | 29-13
2024-07-16 | 29 | 29-13
2024-07-17 | 29 | 29-13
2024-07-18 | 29 | 29-13
2024-07-19 | 29 | 29-13
2024-07-20 | 29 | 30-13
2024-07-21 | 30 | 30-13
2024-07-22 | 30 | 30-13
2024-07-23 | 30 | 30-13
2024-07-24 | 30 | 30-13
2024-07-25 | 30 | 30-13
2024-07-26 | 30 | 30-13
2024-07-27 | 30 | 31-13
2024-07-28 | 31 | 31-13
2024-07-29 | 31 | 31-13
2024-07-30 | 31 | 31-13
2024-07-31 | 31 | 31-13
2024-08-01 | 31 | 31-13
2024-08-02 | 31 | 31-13
2024-08-03 | 31 | 32-13
2024-08-04 | 32 | 32-13
2024-08-05 | 32 | 32-13
2024-08-06 | 32 | 32-13
2024-08-07 | 32 | 32-13
2024-08-08 | 32 | 32-13
2024-08-09 | 32 | 32-13
2024-08-10 | 32 | 33-13
2024-08-11 | 33 | 33-13
2024-08-12 | 33 | 33-13
2024-08-13 | 33 | 33-13
2024-08-14 | 33 | 33-13
2024-08-15 | 33 | 33-13
2024-08-16 | 33 | 33-13
2024-08-17 | 33 | 34-13
2024-08-18 | 34 | 34-13
2024-08-19 | 34 | 34-13
2024-08-20 | 34 | 34-13
2024-08-21 | 34 | 34-13
2024-08-22 | 34 | 34-13
2024-08-23 | 34 | 34-13
2024-08-24 | 34 | 35-13
2024-08-25 | 35 | 35-13
2024-08-26 | 35 | 35-13
2024-08-27 | 35 | 35-13
2024-08-28 | 35 | 35-13
2024-08-29 | 35 | 35-13
2024-08-30 | 35 | 35-13
2024-08-31 | 35 | 36-13
2024-09-01 | 36 | 36-13
2024-09-02 | 36 | 36-13
2024-09-03 | 36 | 36-13
2024-09-04 | 36 | 36-13
2024-09-05 | 36 | 36-13
2024-09-06 | 36 | 36-13
2024-09-07 | 36 | 37-13
2024-09-08 | 37 | 37-13
2024-09-09 | 37 | 37-13
2024-09-10 | 37 | 37-13
2024-09-11 | 37 | 37-13
2024-09-12 | 37 | 37-13
2024-09-13 | 37 | 37-13
2024-09-14 | 37 | 38-13
2024-09-15 | 38 | 38-13
2024-09-16 | 38 | 38-13
2024-09-17 | 38 | 38-13
2024-09-18 | 38 | 38-13
2024-09-19 | 38 | 38-13
2024-09-20 | 38 | 38-13
2024-09-21 | 38 | 39-13
2024-09-22 | 39 | 39-13
2024-09-23 | 39 | 39-13
2024-09-24 | 39 | 39-13
2024-09-25 | 39 | 39-13
2024-09-26 | 39 | 39-13
2024-09-27 | 39 | 39-13
2024-09-28 | 39 | 40-13
2024-09-29 | 40 | 40-13
2024-09-30 | 40 | 40-13
2024-10-01 | 40 | 40-13
2024-10-02 | 40 | 40-13
2024-10-03 | 40 | 40-13
2024-10-04 | 40 | 40-13
2024-10-05 | 40 | 41-13
2024-10-06 | 41 | 41-13
2024-10-07 | 41 | 41-13
2024-10-08 | 41 | 41-13
2024-10-09 | 41 | 41-13
2024-10-10 | 41 | 41-13
2024-10-11 | 41 | 41-13
2024-10-12 | 41 | 42-13
2024-10-13 | 42 | 42-13
2024-10-14 | 42 | 42-13
2024-10-15 | 42 | 42-13
2024-10-16 | 42 | 42-13
2024-10-17 | 42 | 42-13
2024-10-18 | 42 | 42-13
2024-10-19 | 42 | 43-13
2024-10-20 | 43 | 43-13
2024-10-21 | 43 | 43-13
2024-10-22 | 43 | 43-13
2024-10-23 | 43 | 43-13
2024-10-24 | 43 | 43-13
2024-10-25 | 43 | 43-13
2024-10-26 | 43 | 44-13
2024-10-27 | 44 | 44-13
2024-10-28 | 44 | 44-13
2024-10-29 | 44 | 44-13
2024-10-30 | 44 | 44-13
2024-10-31 | 44 | 44-13
2024-11-01 | 44 | 44-13
2024-11-02 | 44 | 45-13
2024-11-03 | 45 | 45-13
2024-11-04 | 45 | 45-13
2024-11-05 | 45 | 45-13
2024-11-06 | 45 | 45-13
2024-11-07 | 45 | 45-13
2024-11-08 | 45 | 45-13
2024-11-09 | 45 | 46-13
2024-11-10 | 46 | 46-13
2024-11-11 | 46 | 46-13
2024-11-12 | 46 | 46-13
2024-11-13 | 46 | 46-13
2024-11-14 | 46 | 46-13
2024-11-15 | 46 | 46-13
2024-11-16 | 46 | 47-13
2024-11-17 | 47 | 47-13
2024-11-18 | 47 | 47-13
2024-11-19 | 47 | 47-13
2024-11-20 | 47 | 47-13
2024-11-21 | 47 | 47-13
2024-11-22 | 47 | 47-13
2024-11-23 | 47 | 48-13
2024-11-24 | 48 | 48-13
2024-11-25 | 48 | 48-13
2024-11-26 | 48 | 48-13
2024-11-27 | 48 | 48-13
2024-11-28 | 48 | 48-13
2024-11-29 | 48 | 48-13
2024-11-30 | 48 | 49-13
2024-12-01 | 49 | 49-13
2024-12-02 | 49 | 49-13
2024-12-03 | 49 | 49-13
2024-12-04 | 49 | 49-13
2024-12-05 | 49 | 49-13
2024-12-06 | 49 | 49-13
2024-12-07 | 49 | 50-13
2024-12-08 | 50 | 50-13
2024-12-09 | 50 | 50-13
2024-12-10 | 50 | 50-13
2024-12-11 | 50 | 50-13
2024-12-12 | 50 | 50-13
2024-12-13 | 50 | 50-13
2024-12-14 | 50 | 51-13
2024-12-15 | 51 | 51-13
2024-12-16 | 51 | 51-13
2024-12-17 | 51 | 51-13
2024-12-18 | 51 | 51-13
2024-12-19 | 51 | 51-13
2024-12-20 | 51 | 51-13
2024-12-21 | 51 | 52-13
2024-12-22 | 52 | 52-13
2024-12-23 | 52 | 52-13
2024-12-24 | 52 | 52-13
2024-12-25 | 52 | 52-13
2024-12-26 | 52 | 52-13
2024-12-27 | 52 | 52-13
2024-12-28 | 52 | 53-13
2024-12-29 | 53 | 53-13
2024-12-30 | 53 | 53-13
2024-12-31 | 53 | 1-14
2025-01-01 | 1 | 1-14
2025-01-02 | 1 | 1-14
2025-01-03 | 1 | 1-14
2025-01-04 | 1 | 2-14
2025-01-05 | 2 | 2-14
2025-01-06 | 2 | 2-14
2025-01-07 | 2 | 2-14
2025-01-08 | 2 | 2-14
2025-01-09 | 2 | 2-14
2025-01-10 | 2 | 2-14
2025-01-11 | 2 | 3-14
2025-01-12 | 3 | 3-14
2025-01-13 | 3 | 3-14
2025-01-14 | 3 | 3-14
2025-01-15 | 3 | 3-14
2025-01-16 | 3 | 3-14
2025-01-17 | 3 | 3-14
2025-01-18 | 3 | 4-14
2025-01-19 | 4 | 4-14
2025-01-20 | 4 | 4-14
2025-01-21 | 4 | 4-14
2025-01-22 | 4 | 4-14
2025-01-23 | 4 | 4-14
2025-01-24 | 4 | 4-14
2025-01-25 | 4 | 5-14
2025-01-26 | 5 | 5-14
2025-01-27 | 5 | 5-14
2025-01-28 | 5 | 5-14
2025-01-29 | 5 | 5-14
2025-01-30 | 5 | 5-14
2025-01-31 | 5 | 5-14
2025-02-01 | 5 | 6-14
2025-02-02 | 6 | 6-14
2025-02-03 | 6 | 6-14
2025-02-04 | 6 | 6-14
2025-02-05 | 6 | 6-14
2025-02-06 | 6 | 6-14
2025-02-07 | 6 | 6-14
2025-02-08 | 6 | 7-14
2025-02-09 | 7 | 7-14
2025-02-10 | 7 | 7-14
2025-02-11 | 7 | 7-14
2025-02-12 | 7 | 7-14
2025-02-13 | 7 | 7-14
2025-02-14 | 7 | 7-14
2025-02-15 | 7 | 8-14
2025-02-16 | 8 | 8-14
2025-02-17 | 8 | 8-14
2025-02-18 | 8 | 8-14
2025-02-19 | 8 | 8-14
2025-02-20 | 8 | 8-14
2025-02-21 | 8 | 8-14
2025-02-22 | 8 | 9-14
2025-02-23 | 9 | 9-14
2025-02-24 | 9 | 9-14
2025-02-25 | 9 | 9-14
2025-02-26 | 9 | 9-14
2025-02-27 | 9 | 9-14
2025-02-28 | 9 | 9-14
2025-03-01 | 9 | 10-14
2025-03-02 | 10 | 10-14
2025-03-03 | 10 | 10-14
2025-03-04 | 10 | 10-14
2025-03-05 | 10 | 10-14
2025-03-06 | 10 | 10-14
2025-03-07 | 10 | 10-14
2025-03-08 | 10 | 11-14
2025-03-09 | 11 | 11-14
2025-03-10 | 11 | 11-14
2025-03-11 | 11 | 11-14
2025-03-12 | 11 | 11-14
2025-03-13 | 11 | 11-14
2025-03-14 | 11 | 11-14
2025-03-15 | 11 | 12-14
2025-03-16 | 12 | 12-14
2025-03-17 | 12 | 12-14
2025-03-18 | 12 | 12-14
2025-03-19 | 12 | 12-14
2025-03-20 | 12 | 12-14
2025-03-21 | 12 | 12-14
2025-03-22 | 12 | 13-14
2025-03-23 | 13 | 13-14
2025-03-24 | 13 | 13-14
2025-03-25 | 13 | 13-14
2025-03-26 | 13 | 13-14
2025-03-27 | 13 | 13-14
2025-03-28 | 13 | 13-14
2025-03-29 | 13 | 14-14
2025-03-30 | 14 | 14-14
2025-03-31 | 14 | 14-14
2025-04-01 | 14 | 14-14
2025-04-02 | 14 | 14-14
2025-04-03 | 14 | 14-14
2025-04-04 | 14 | 14-14
2025-04-05 | 14 | 15-14
2025-04-06 | 15 | 15-14
2025-04-07 | 15 | 15-14
2025-04-08 | 15 | 15-14
2025-04-09 | 15 | 15-14
2025-04-10 | 15 | 15-14
2025-04-11 | 15 | 15-14
2025-04-12 | 15 | 16-14
2025-04-13 | 16 | 16-14
2025-04-14 | 16 | 16-14
2025-04-15 | 16 | 16-14
2025-04-16 | 16 | 16-14
2025-04-17 | 16 | 16-14
2025-04-18 | 16 | 16-14
2025-04-19 | 16 | 17-14
2025-04-20 | 17 | 17-14
2025-04-21 | 17 | 17-14
2025-04-22 | 17 | 17-14
2025-04-23 | 17 | 17-14
2025-04-24 | 17 | 17-14
2025-04-25 | 17 | 17-14
2025-04-26 | 17 | 18-14
2025-04-27 | 18 | 18-14
2025-04-28 | 18 | 18-14
2025-04-29 | 18 | 18-14
2025-04-30 | 18 | 18-14
2025-05-01 | 18 | 18-14
2025-05-02 | 18 | 18-14
2025-05-03 | 18 | 19-14
2025-05-04 | 19 | 19-14
2025-05-05 | 19 | 19-14
2025-05-06 | 19 | 19-14
2025-05-07 | 19 | 19-14
2025-05-08 | 19 | 19-14
2025-05-09 | 19 | 19-14
2025-05-10 | 19 | 20-14
2025-05-11 | 20 | 20-14
2025-05-12 | 20 | 20-14
2025-05-13 | 20 | 20-14
2025-05-14 | 20 | 20-14
2025-05-15 | 20 | 20-14
2025-05-16 | 20 | 20-14
2025-05-17 | 20 | 21-14
2025-05-18 | 21 | 21-14
2025-05-19 | 21 | 21-14
2025-05-20 | 21 | 21-14
2025-05-21 | 21 | 21-14
2025-05-22 | 21 | 21-14
2025-05-23 | 21 | 21-14
2025-05-24 | 21 | 22-14
2025-05-25 | 22 | 22-14
2025-05-26 | 22 | 22-14
2025-05-27 | 22 | 22-14
2025-05-28 | 22 | 22-14
2025-05-29 | 22 | 22-14
2025-05-30 | 22 | 22-14
2025-05-31 | 22 | 23-14
2025-06-01 | 23 | 23-14
2025-06-02 | 23 | 23-14
2025-06-03 | 23 | 23-14
2025-06-04 | 23 | 23-14
2025-06-05 | 23 | 23-14
2025-06-06 | 23 | 23-14
2025-06-07 | 23 | 24-14
2025-06-08 | 24 | 24-14
2025-06-09 | 24 | 24-14
2025-06-10 | 24 | 24-14
2025-06-11 | 24 | 24-14
2025-06-12 | 24 | 24-14
2025-06-13 | 24 | 24-14
2025-06-14 | 24 | 25-14
2025-06-15 | 25 | 25-14
2025-06-16 | 25 | 25-14
2025-06-17 | 25 | 25-14
2025-06-18 | 25 | 25-14
2025-06-19 | 25 | 25-14
2025-06-20 | 25 | 25-14
2025-06-21 | 25 | 26-14
2025-06-22 | 26 | 26-14
2025-06-23 | 26 | 26-14
2025-06-24 | 26 | 26-14
2025-06-25 | 26 | 26-14
2025-06-26 | 26 | 26-14
2025-06-27 | 26 | 26-14
2025-06-28 | 26 | 27-14
2025-06-29 | 27 | 27-14
2025-06-30 | 27 | 27-14
2025-07-01 | 27 | 27-14
2025-07-02 | 27 | 27-14
2025-07-03 | 27 | 27-14
2025-07-04 | 27 | 27-14
2025-07-05 | 27 | 28-14
2025-07-06 | 28 | 28-14
2025-07-07 | 28 | 28-14
2025-07-08 | 28 | 28-14
2025-07-09 | 28 | 28-14
2025-07-10 | 28 | 28-14
2025-07-11 | 28 | 28-14
2025-07-12 | 28 | 29-14
2025-07-13 | 29 | 29-14
2025-07-14 | 29 | 29-14
2025-07-15 | 29 | 29-14
2025-07-16 | 29 | 29-14
2025-07-17 | 29 | 29-14
2025-07-18 | 29 | 29-14
2025-07-19 | 29 | 30-14
2025-07-20 | 30 | 30-14
2025-07-21 | 30 | 30-14
2025-07-22 | 30 | 30-14
2025-07-23 | 30 | 30-14
2025-07-24 | 30 | 30-14
2025-07-25 | 30 | 30-14
2025-07-26 | 30 | 31-14
2025-07-27 | 31 | 31-14
2025-07-28 | 31 | 31-14
2025-07-29 | 31 | 31-14
2025-07-30 | 31 | 31-14
2025-07-31 | 31 | 31-14
2025-08-01 | 31 | 31-14
2025-08-02 | 31 | 32-14
2025-08-03 | 32 | 32-14
2025-08-04 | 32 | 32-14
2025-08-05 | 32 | 32-14
2025-08-06 | 32 | 32-14
2025-08-07 | 32 | 32-14
2025-08-08 | 32 | 32-14
2025-08-09 | 32 | 33-14
2025-08-10 | 33 | 33-14
2025-08-11 | 33 | 33-14
2025-08-12 | 33 | 33-14
2025-08-13 | 33 | 33-14
2025-08-14 | 33 | 33-14
2025-08-15 | 33 | 33-14
2025-08-16 | 33 | 34-14
2025-08-17 | 34 | 34-14
2025-08-18 | 34 | 34-14
2025-08-19 | 34 | 34-14
2025-08-20 | 34 | 34-14
2025-08-21 | 34 | 34-14
2025-08-22 | 34 | 34-14
2025-08-23 | 34 | 35-14
2025-08-24 | 35 | 35-14
2025-08-25 | 35 | 35-14
2025-08-26 | 35 | 35-14
2025-08-27 | 35 | 35-14
2025-08-28 | 35 | 35-14
2025-08-29 | 35 | 35-14
2025-08-30 | 35 | 36-14
2025-08-31 | 36 | 36-14
2025-09-01 | 36 | 36-14
2025-09-02 | 36 | 36-14
2025-09-03 | 36 | 36-14
2025-09-04 | 36 | 36-14
2025-09-05 | 36 | 36-14
2025-09-06 | 36 | 37-14
2025-09-07 | 37 | 37-14
2025-09-08 | 37 | 37-14
2025-09-09 | 37 | 37-14
2025-09-10 | 37 | 37-14
2025-09-11 | 37 | 37-14
2025-09-12 | 37 | 37-14
2025-09-13 | 37 | 38-14
2025-09-14 | 38 | 38-14
2025-09-15 | 38 | 38-14
2025-09-16 | 38 | 38-14
2025-09-17 | 38 | 38-14
2025-09-18 | 38 | 38-14
2025-09-19 | 38 | 38-14
2025-09-20 | 38 | 39-14
2025-09-21 | 39 | 39-14
2025-09-22 | 39 | 39-14
2025-09-23 | 39 | 39-14
2025-09-24 | 39 | 39-14
2025-09-25 | 39 | 39-14
2025-09-26 | 39 | 39-14
2025-09-27 | 39 | 40-14
2025-09-28 | 40 | 40-14
2025-09-29 | 40 | 40-14
2025-09-30 | 40 | 40-14
2025-10-01 | 40 | 40-14
2025-10-02 | 40 | 40-14
2025-10-03 | 40 | 40-14
2025-10-04 | 40 | 41-14
2025-10-05 | 41 | 41-14
2025-10-06 | 41 | 41-14
2025-10-07 | 41 | 41-14
2025-10-08 | 41 | 41-14
2025-10-09 | 41 | 41-14
2025-10-10 | 41 | 41-14
2025-10-11 | 41 | 42-14
2025-10-12 | 42 | 42-14
2025-10-13 | 42 | 42-14
2025-10-14 | 42 | 42-14
2025-10-15 | 42 | 42-14
2025-10-16 | 42 | 42-14
2025-10-17 | 42 | 42-14
2025-10-18 | 42 | 43-14
2025-10-19 | 43 | 43-14
2025-10-20 | 43 | 43-14
2025-10-21 | 43 | 43-14
2025-10-22 | 43 | 43-14
2025-10-23 | 43 | 43-14
2025-10-24 | 43 | 43-14
2025-10-25 | 43 | 44-14
2025-10-26 | 44 | 44-14
2025-10-27 | 44 | 44-14
2025-10-28 | 44 | 44-14
2025-10-29 | 44 | 44-14
2025-10-30 | 44 | 44-14
2025-10-31 | 44 | 44-14
2025-11-01 | 44 | 45-14
2025-11-02 | 45 | 45-14
2025-11-03 | 45 | 45-14
2025-11-04 | 45 | 45-14
2025-11-05 | 45 | 45-14
2025-11-06 | 45 | 45-14
2025-11-07 | 45 | 45-14
2025-11-08 | 45 | 46-14
2025-11-09 | 46 | 46-14
2025-11-10 | 46 | 46-14
2025-11-11 | 46 | 46-14
2025-11-12 | 46 | 46-14
2025-11-13 | 46 | 46-14
2025-11-14 | 46 | 46-14
2025-11-15 | 46 | 47-14
2025-11-16 | 47 | 47-14
2025-11-17 | 47 | 47-14
2025-11-18 | 47 | 47-14
2025-11-19 | 47 | 47-14
2025-11-20 | 47 | 47-14
2025-11-21 | 47 | 47-14
2025-11-22 | 47 | 48-14
2025-11-23 | 48 | 48-14
2025-11-24 | 48 | 48-14
2025-11-25 | 48 | 48-14
2025-11-26 | 48 | 48-14
2025-11-27 | 48 | 48-14
2025-11-28 | 48 | 48-14
2025-11-29 | 48 | 49-14
2025-11-30 | 49 | 49-14
2025-12-01 | 49 | 49-14
2025-12-02 | 49 | 49-14
2025-12-03 | 49 | 49-14
2025-12-04 | 49 | 49-14
2025-12-05 | 49 | 49-14
2025-12-06 | 49 | 50-14
2025-12-07 | 50 | 50-14
2025-12-08 | 50 | 50-14
2025-12-09 | 50 | 50-14
2025-12-10 | 50 | 50-14
2025-12-11 | 50 | 50-14
2025-12-12 | 50 | 50-14
2025-12-13 | 50 | 51-14
2025-12-14 | 51 | 51-14
2025-12-15 | 51 | 51-14
2025-12-16 | 51 | 51-14
2025-12-17 | 51 | 51-14
2025-12-18 | 51 | 51-14
2025-12-19 | 51 | 51-14
2025-12-20 | 51 | 52-14
2025-12-21 | 52 | 52-14
2025-12-22 | 52 | 52-14
2025-12-23 | 52 | 52-14
2025-12-24 | 52 | 52-14
2025-12-25 | 52 | 52-14
2025-12-26 | 52 | 52-14
2025-12-27 | 52 | 53-14
2025-12-28 | 53 | 53-14
2025-12-29 | 53 | 53-14
2025-12-30 | 53 | 53-14
2025-12-31 | 1 | 1-15
2026-01-01 | 1 | 1-15
2026-01-02 | 1 | 1-15
2026-01-03 | 2 | 2-15
2026-01-04 | 2 | 2-15
2026-01-05 | 2 | 2-15
2026-01-06 | 2 | 2-15
2026-01-07 | 2 | 2-15
2026-01-08 | 2 | 2-15
2026-01-09 | 2 | 2-15
2026-01-10 | 3 | 3-15
2026-01-11 | 3 | 3-15
2026-01-12 | 3 | 3-15
2026-01-13 | 3 | 3-15
2026-01-14 | 3 | 3-15
2026-01-15 | 3 | 3-15
2026-01-16 | 3 | 3-15
2026-01-17 | 4 | 4-15
2026-01-18 | 4 | 4-15
2026-01-19 | 4 | 4-15
2026-01-20 | 4 | 4-15
2026-01-21 | 4 | 4-15
2026-01-22 | 4 | 4-15
2026-01-23 | 4 | 4-15
2026-01-24 | 5 | 5-15
2026-01-25 | 5 | 5-15
2026-01-26 | 5 | 5-15
2026-01-27 | 5 | 5-15
2026-01-28 | 5 | 5-15
2026-01-29 | 5 | 5-15
2026-01-30 | 5 | 5-15
2026-01-31 | 6 | 6-15
2026-02-01 | 6 | 6-15
2026-02-02 | 6 | 6-15
2026-02-03 | 6 | 6-15
2026-02-04 | 6 | 6-15
2026-02-05 | 6 | 6-15
2026-02-06 | 6 | 6-15
2026-02-07 | 7 | 7-15
2026-02-08 | 7 | 7-15
2026-02-09 | 7 | 7-15
2026-02-10 | 7 | 7-15
2026-02-11 | 7 | 7-15
2026-02-12 | 7 | 7-15
2026-02-13 | 7 | 7-15
2026-02-14 | 8 | 8-15
2026-02-15 | 8 | 8-15
2026-02-16 | 8 | 8-15
2026-02-17 | 8 | 8-15
2026-02-18 | 8 | 8-15
2026-02-19 | 8 | 8-15
2026-02-20 | 8 | 8-15
2026-02-21 | 9 | 9-15
2026-02-22 | 9 | 9-15
2026-02-23 | 9 | 9-15
2026-02-24 | 9 | 9-15
2026-02-25 | 9 | 9-15
2026-02-26 | 9 | 9-15
2026-02-27 | 9 | 9-15
2026-02-28 | 10 | 10-15
2026-03-01 | 10 | 10-15
2026-03-02 | 10 | 10-15
2026-03-03 | 10 | 10-15
2026-03-04 | 10 | 10-15
2026-03-05 | 10 | 10-15
2026-03-06 | 10 | 10-15
2026-03-07 | 11 | 11-15
2026-03-08 | 11 | 11-15
2026-03-09 | 11 | 11-15
2026-03-10 | 11 | 11-15
2026-03-11 | 11 | 11-15
2026-03-12 | 11 | 11-15
2026-03-13 | 11 | 11-15
2026-03-14 | 12 | 12-15
2026-03-15 | 12 | 12-15
2026-03-16 | 12 | 12-15
2026-03-17 | 12 | 12-15
2026-03-18 | 12 | 12-15
2026-03-19 | 12 | 12-15
2026-03-20 | 12 | 12-15
2026-03-21 | 13 | 13-15
2026-03-22 | 13 | 13-15
2026-03-23 | 13 | 13-15
2026-03-24 | 13 | 13-15
2026-03-25 | 13 | 13-15
2026-03-26 | 13 | 13-15
2026-03-27 | 13 | 13-15
2026-03-28 | 14 | 14-15
2026-03-29 | 14 | 14-15
2026-03-30 | 14 | 14-15
2026-03-31 | 14 | 14-15
2026-04-01 | 14 | 14-15
2026-04-02 | 14 | 14-15
2026-04-03 | 14 | 14-15
2026-04-04 | 15 | 15-15
2026-04-05 | 15 | 15-15
2026-04-06 | 15 | 15-15
2026-04-07 | 15 | 15-15
2026-04-08 | 15 | 15-15
2026-04-09 | 15 | 15-15
2026-04-10 | 15 | 15-15
2026-04-11 | 16 | 16-15
2026-04-12 | 16 | 16-15
2026-04-13 | 16 | 16-15
2026-04-14 | 16 | 16-15
2026-04-15 | 16 | 16-15
2026-04-16 | 16 | 16-15
2026-04-17 | 16 | 16-15
2026-04-18 | 17 | 17-15
2026-04-19 | 17 | 17-15
2026-04-20 | 17 | 17-15
2026-04-21 | 17 | 17-15
2026-04-22 | 17 | 17-15
2026-04-23 | 17 | 17-15
2026-04-24 | 17 | 17-15
2026-04-25 | 18 | 18-15
2026-04-26 | 18 | 18-15
2026-04-27 | 18 | 18-15
2026-04-28 | 18 | 18-15
2026-04-29 | 18 | 18-15
2026-04-30 | 18 | 18-15
2026-05-01 | 18 | 18-15
2026-05-02 | 19 | 19-15
2026-05-03 | 19 | 19-15
2026-05-04 | 19 | 19-15
2026-05-05 | 19 | 19-15
2026-05-06 | 19 | 19-15
2026-05-07 | 19 | 19-15
2026-05-08 | 19 | 19-15
2026-05-09 | 20 | 20-15
2026-05-10 | 20 | 20-15
2026-05-11 | 20 | 20-15
2026-05-12 | 20 | 20-15
2026-05-13 | 20 | 20-15
2026-05-14 | 20 | 20-15
2026-05-15 | 20 | 20-15
2026-05-16 | 21 | 21-15
2026-05-17 | 21 | 21-15
2026-05-18 | 21 | 21-15
2026-05-19 | 21 | 21-15
2026-05-20 | 21 | 21-15
2026-05-21 | 21 | 21-15
2026-05-22 | 21 | 21-15
2026-05-23 | 22 | 22-15
2026-05-24 | 22 | 22-15
2026-05-25 | 22 | 22-15
2026-05-26 | 22 | 22-15
2026-05-27 | 22 | 22-15
2026-05-28 | 22 | 22-15
2026-05-29 | 22 | 22-15
2026-05-30 | 23 | 23-15
2026-05-31 | 23 | 23-15
2026-06-01 | 23 | 23-15
2026-06-02 | 23 | 23-15
2026-06-03 | 23 | 23-15
2026-06-04 | 23 | 23-15
2026-06-05 | 23 | 23-15
2026-06-06 | 24 | 24-15
2026-06-07 | 24 | 24-15
2026-06-08 | 24 | 24-15
2026-06-09 | 24 | 24-15
2026-06-10 | 24 | 24-15
2026-06-11 | 24 | 24-15
2026-06-12 | 24 | 24-15
2026-06-13 | 25 | 25-15
2026-06-14 | 25 | 25-15
2026-06-15 | 25 | 25-15
2026-06-16 | 25 | 25-15
2026-06-17 | 25 | 25-15
2026-06-18 | 25 | 25-15
2026-06-19 | 25 | 25-15
2026-06-20 | 26 | 26-15
2026-06-21 | 26 | 26-15
2026-06-22 | 26 | 26-15
2026-06-23 | 26 | 26-15
2026-06-24 | 26 | 26-15
2026-06-25 | 26 | 26-15
2026-06-26 | 26 | 26-15
2026-06-27 | 27 | 27-15
2026-06-28 | 27 | 27-15
2026-06-29 | 27 | 27-15
2026-06-30 | 27 | 27-15
2026-07-01 | 27 | 27-15
2026-07-02 | 27 | 27-15
2026-07-03 | 27 | 27-15
2026-07-04 | 28 | 28-15
2026-07-05 | 28 | 28-15
2026-07-06 | 28 | 28-15
2026-07-07 | 28 | 28-15
2026-07-08 | 28 | 28-15
2026-07-09 | 28 | 28-15
2026-07-10 | 28 | 28-15
2026-07-11 | 29 | 29-15
2026-07-12 | 29 | 29-15
2026-07-13 | 29 | 29-15
2026-07-14 | 29 | 29-15
2026-07-15 | 29 | 29-15
2026-07-16 | 29 | 29-15
2026-07-17 | 29 | 29-15
2026-07-18 | 30 | 30-15
2026-07-19 | 30 | 30-15
2026-07-20 | 30 | 30-15
2026-07-21 | 30 | 30-15
2026-07-22 | 30 | 30-15
2026-07-23 | 30 | 30-15
2026-07-24 | 30 | 30-15
2026-07-25 | 31 | 31-15
2026-07-26 | 31 | 31-15
2026-07-27 | 31 | 31-15
2026-07-28 | 31 | 31-15
2026-07-29 | 31 | 31-15
2026-07-30 | 31 | 31-15
2026-07-31 | 31 | 31-15
2026-08-01 | 32 | 32-15
2026-08-02 | 32 | 32-15
2026-08-03 | 32 | 32-15
2026-08-04 | 32 | 32-15
2026-08-05 | 32 | 32-15
2026-08-06 | 32 | 32-15
2026-08-07 | 32 | 32-15
2026-08-08 | 33 | 33-15
2026-08-09 | 33 | 33-15
2026-08-10 | 33 | 33-15
2026-08-11 | 33 | 33-15
2026-08-12 | 33 | 33-15
2026-08-13 | 33 | 33-15
2026-08-14 | 33 | 33-15
2026-08-15 | 34 | 34-15
2026-08-16 | 34 | 34-15
2026-08-17 | 34 | 34-15
2026-08-18 | 34 | 34-15
2026-08-19 | 34 | 34-15
2026-08-20 | 34 | 34-15
2026-08-21 | 34 | 34-15
2026-08-22 | 35 | 35-15
2026-08-23 | 35 | 35-15
2026-08-24 | 35 | 35-15
2026-08-25 | 35 | 35-15
2026-08-26 | 35 | 35-15
2026-08-27 | 35 | 35-15
2026-08-28 | 35 | 35-15
2026-08-29 | 36 | 36-15
2026-08-30 | 36 | 36-15
2026-08-31 | 36 | 36-15
2026-09-01 | 36 | 36-15
2026-09-02 | 36 | 36-15
2026-09-03 | 36 | 36-15
2026-09-04 | 36 | 36-15
2026-09-05 | 37 | 37-15
2026-09-06 | 37 | 37-15
2026-09-07 | 37 | 37-15
2026-09-08 | 37 | 37-15
2026-09-09 | 37 | 37-15
2026-09-10 | 37 | 37-15
2026-09-11 | 37 | 37-15
2026-09-12 | 38 | 38-15
2026-09-13 | 38 | 38-15
2026-09-14 | 38 | 38-15
2026-09-15 | 38 | 38-15
2026-09-16 | 38 | 38-15
2026-09-17 | 38 | 38-15
2026-09-18 | 38 | 38-15
2026-09-19 | 39 | 39-15
2026-09-20 | 39 | 39-15
2026-09-21 | 39 | 39-15
2026-09-22 | 39 | 39-15
2026-09-23 | 39 | 39-15
2026-09-24 | 39 | 39-15
2026-09-25 | 39 | 39-15
2026-09-26 | 40 | 40-15
2026-09-27 | 40 | 40-15
2026-09-28 | 40 | 40-15
2026-09-29 | 40 | 40-15
2026-09-30 | 40 | 40-15
2026-10-01 | 40 | 40-15
2026-10-02 | 40 | 40-15
2026-10-03 | 41 | 41-15
2026-10-04 | 41 | 41-15
2026-10-05 | 41 | 41-15
2026-10-06 | 41 | 41-15
2026-10-07 | 41 | 41-15
2026-10-08 | 41 | 41-15
2026-10-09 | 41 | 41-15
2026-10-10 | 42 | 42-15
2026-10-11 | 42 | 42-15
2026-10-12 | 42 | 42-15
2026-10-13 | 42 | 42-15
2026-10-14 | 42 | 42-15
2026-10-15 | 42 | 42-15
2026-10-16 | 42 | 42-15
2026-10-17 | 43 | 43-15
2026-10-18 | 43 | 43-15
2026-10-19 | 43 | 43-15
2026-10-20 | 43 | 43-15
2026-10-21 | 43 | 43-15
2026-10-22 | 43 | 43-15
2026-10-23 | 43 | 43-15
2026-10-24 | 44 | 44-15
2026-10-25 | 44 | 44-15
2026-10-26 | 44 | 44-15
2026-10-27 | 44 | 44-15
2026-10-28 | 44 | 44-15
2026-10-29 | 44 | 44-15
2026-10-30 | 44 | 44-15
2026-10-31 | 45 | 45-15
2026-11-01 | 45 | 45-15
2026-11-02 | 45 | 45-15
2026-11-03 | 45 | 45-15
2026-11-04 | 45 | 45-15
2026-11-05 | 45 | 45-15
2026-11-06 | 45 | 45-15
2026-11-07 | 46 | 46-15
2026-11-08 | 46 | 46-15
2026-11-09 | 46 | 46-15
2026-11-10 | 46 | 46-15
2026-11-11 | 46 | 46-15
2026-11-12 | 46 | 46-15
2026-11-13 | 46 | 46-15
2026-11-14 | 47 | 47-15
2026-11-15 | 47 | 47-15
2026-11-16 | 47 | 47-15
2026-11-17 | 47 | 47-15
2026-11-18 | 47 | 47-15
2026-11-19 | 47 | 47-15
2026-11-20 | 47 | 47-15
2026-11-21 | 48 | 48-15
2026-11-22 | 48 | 48-15
2026-11-23 | 48 | 48-15
2026-11-24 | 48 | 48-15
2026-11-25 | 48 | 48-15
2026-11-26 | 48 | 48-15
2026-11-27 | 48 | 48-15
2026-11-28 | 49 | 49-15
2026-11-29 | 49 | 49-15
2026-11-30 | 49 | 49-15
2026-12-01 | 49 | 49-15
2026-12-02 | 49 | 49-15
2026-12-03 | 49 | 49-15
2026-12-04 | 49 | 49-15
2026-12-05 | 50 | 50-15
2026-12-06 | 50 | 50-15
2026-12-07 | 50 | 50-15
2026-12-08 | 50 | 50-15
2026-12-09 | 50 | 50-15
2026-12-10 | 50 | 50-15
2026-12-11 | 50 | 50-15
2026-12-12 | 51 | 51-15
2026-12-13 | 51 | 51-15
2026-12-14 | 51 | 51-15
2026-12-15 | 51 | 51-15
2026-12-16 | 51 | 51-15
2026-12-17 | 51 | 51-15
2026-12-18 | 51 | 51-15
2026-12-19 | 52 | 52-15
2026-12-20 | 52 | 52-15
2026-12-21 | 52 | 52-15
2026-12-22 | 52 | 52-15
2026-12-23 | 52 | 52-15
2026-12-24 | 52 | 52-15
2026-12-25 | 52 | 52-15
2026-12-26 | 53 | 53-15
2026-12-27 | 53 | 53-15
2026-12-28 | 53 | 53-15
2026-12-29 | 53 | 53-15
2026-12-30 | 53 | 53-15
2026-12-31 | 1 | 1-16
2027-01-01 | 1 | 1-16
2027-01-02 | 1 | 1-16
2027-01-03 | 2 | 2-16
2027-01-04 | 2 | 2-16
2027-01-05 | 2 | 2-16
2027-01-06 | 2 | 2-16
2027-01-07 | 2 | 2-16
2027-01-08 | 2 | 2-16
2027-01-09 | 2 | 2-16
2027-01-10 | 3 | 3-16
2027-01-11 | 3 | 3-16
2027-01-12 | 3 | 3-16
2027-01-13 | 3 | 3-16
2027-01-14 | 3 | 3-16
2027-01-15 | 3 | 3-16
2027-01-16 | 3 | 3-16
2027-01-17 | 4 | 4-16
2027-01-18 | 4 | 4-16
2027-01-19 | 4 | 4-16
2027-01-20 | 4 | 4-16
2027-01-21 | 4 | 4-16
2027-01-22 | 4 | 4-16
2027-01-23 | 4 | 4-16
2027-01-24 | 5 | 5-16
2027-01-25 | 5 | 5-16
2027-01-26 | 5 | 5-16
2027-01-27 | 5 | 5-16
2027-01-28 | 5 | 5-16
2027-01-29 | 5 | 5-16
2027-01-30 | 5 | 5-16
2027-01-31 | 6 | 6-16
2027-02-01 | 6 | 6-16
2027-02-02 | 6 | 6-16
2027-02-03 | 6 | 6-16
2027-02-04 | 6 | 6-16
2027-02-05 | 6 | 6-16
2027-02-06 | 6 | 6-16
2027-02-07 | 7 | 7-16
2027-02-08 | 7 | 7-16
2027-02-09 | 7 | 7-16
2027-02-10 | 7 | 7-16
2027-02-11 | 7 | 7-16
2027-02-12 | 7 | 7-16
2027-02-13 | 7 | 7-16
2027-02-14 | 8 | 8-16
2027-02-15 | 8 | 8-16
2027-02-16 | 8 | 8-16
2027-02-17 | 8 | 8-16
2027-02-18 | 8 | 8-16
2027-02-19 | 8 | 8-16
2027-02-20 | 8 | 8-16
2027-02-21 | 9 | 9-16
2027-02-22 | 9 | 9-16
2027-02-23 | 9 | 9-16
2027-02-24 | 9 | 9-16
2027-02-25 | 9 | 9-16
2027-02-26 | 9 | 9-16
2027-02-27 | 9 | 9-16
2027-02-28 | 10 | 10-16
2027-03-01 | 10 | 10-16
2027-03-02 | 10 | 10-16
2027-03-03 | 10 | 10-16
2027-03-04 | 10 | 10-16
2027-03-05 | 10 | 10-16
2027-03-06 | 10 | 10-16
2027-03-07 | 11 | 11-16
2027-03-08 | 11 | 11-16
2027-03-09 | 11 | 11-16
2027-03-10 | 11 | 11-16
2027-03-11 | 11 | 11-16
2027-03-12 | 11 | 11-16
2027-03-13 | 11 | 11-16
2027-03-14 | 12 | 12-16
2027-03-15 | 12 | 12-16
2027-03-16 | 12 | 12-16
2027-03-17 | 12 | 12-16
2027-03-18 | 12 | 12-16
2027-03-19 | 12 | 12-16
2027-03-20 | 12 | 12-16
2027-03-21 | 13 | 13-16
2027-03-22 | 13 | 13-16
2027-03-23 | 13 | 13-16
2027-03-24 | 13 | 13-16
2027-03-25 | 13 | 13-16
2027-03-26 | 13 | 13-16
2027-03-27 | 13 | 13-16
2027-03-28 | 14 | 14-16
2027-03-29 | 14 | 14-16
2027-03-30 | 14 | 14-16
2027-03-31 | 14 | 14-16
2027-04-01 | 14 | 14-16
2027-04-02 | 14 | 14-16
2027-04-03 | 14 | 14-16
2027-04-04 | 15 | 15-16
2027-04-05 | 15 | 15-16
2027-04-06 | 15 | 15-16
2027-04-07 | 15 | 15-16
2027-04-08 | 15 | 15-16
2027-04-09 | 15 | 15-16
2027-04-10 | 15 | 15-16
2027-04-11 | 16 | 16-16
2027-04-12 | 16 | 16-16
2027-04-13 | 16 | 16-16
2027-04-14 | 16 | 16-16
2027-04-15 | 16 | 16-16
2027-04-16 | 16 | 16-16
2027-04-17 | 16 | 16-16
2027-04-18 | 17 | 17-16
2027-04-19 | 17 | 17-16
2027-04-20 | 17 | 17-16
2027-04-21 | 17 | 17-16
2027-04-22 | 17 | 17-16
2027-04-23 | 17 | 17-16
2027-04-24 | 17 | 17-16
2027-04-25 | 18 | 18-16
2027-04-26 | 18 | 18-16
2027-04-27 | 18 | 18-16
2027-04-28 | 18 | 18-16
2027-04-29 | 18 | 18-16
2027-04-30 | 18 | 18-16
2027-05-01 | 18 | 18-16
2027-05-02 | 19 | 19-16
2027-05-03 | 19 | 19-16
2027-05-04 | 19 | 19-16
2027-05-05 | 19 | 19-16
2027-05-06 | 19 | 19-16
2027-05-07 | 19 | 19-16
2027-05-08 | 19 | 19-16
2027-05-09 | 20 | 20-16
2027-05-10 | 20 | 20-16
2027-05-11 | 20 | 20-16
2027-05-12 | 20 | 20-16
2027-05-13 | 20 | 20-16
2027-05-14 | 20 | 20-16
2027-05-15 | 20 | 20-16
2027-05-16 | 21 | 21-16
2027-05-17 | 21 | 21-16
2027-05-18 | 21 | 21-16
2027-05-19 | 21 | 21-16
2027-05-20 | 21 | 21-16
2027-05-21 | 21 | 21-16
2027-05-22 | 21 | 21-16
2027-05-23 | 22 | 22-16
2027-05-24 | 22 | 22-16
2027-05-25 | 22 | 22-16
2027-05-26 | 22 | 22-16
2027-05-27 | 22 | 22-16
2027-05-28 | 22 | 22-16
2027-05-29 | 22 | 22-16
2027-05-30 | 23 | 23-16
2027-05-31 | 23 | 23-16
2027-06-01 | 23 | 23-16
2027-06-02 | 23 | 23-16
2027-06-03 | 23 | 23-16
2027-06-04 | 23 | 23-16
2027-06-05 | 23 | 23-16
2027-06-06 | 24 | 24-16
2027-06-07 | 24 | 24-16
2027-06-08 | 24 | 24-16
2027-06-09 | 24 | 24-16
2027-06-10 | 24 | 24-16
2027-06-11 | 24 | 24-16
2027-06-12 | 24 | 24-16
2027-06-13 | 25 | 25-16
2027-06-14 | 25 | 25-16
2027-06-15 | 25 | 25-16
2027-06-16 | 25 | 25-16
2027-06-17 | 25 | 25-16
2027-06-18 | 25 | 25-16
2027-06-19 | 25 | 25-16
2027-06-20 | 26 | 26-16
2027-06-21 | 26 | 26-16
2027-06-22 | 26 | 26-16
2027-06-23 | 26 | 26-16
2027-06-24 | 26 | 26-16
2027-06-25 | 26 | 26-16
2027-06-26 | 26 | 26-16
2027-06-27 | 27 | 27-16
2027-06-28 | 27 | 27-16
2027-06-29 | 27 | 27-16
2027-06-30 | 27 | 27-16
2027-07-01 | 27 | 27-16
2027-07-02 | 27 | 27-16
2027-07-03 | 27 | 27-16
2027-07-04 | 28 | 28-16
2027-07-05 | 28 | 28-16
2027-07-06 | 28 | 28-16
2027-07-07 | 28 | 28-16
2027-07-08 | 28 | 28-16
2027-07-09 | 28 | 28-16
2027-07-10 | 28 | 28-16
2027-07-11 | 29 | 29-16
2027-07-12 | 29 | 29-16
2027-07-13 | 29 | 29-16
2027-07-14 | 29 | 29-16
2027-07-15 | 29 | 29-16
2027-07-16 | 29 | 29-16
2027-07-17 | 29 | 29-16
2027-07-18 | 30 | 30-16
2027-07-19 | 30 | 30-16
2027-07-20 | 30 | 30-16
2027-07-21 | 30 | 30-16
2027-07-22 | 30 | 30-16
2027-07-23 | 30 | 30-16
2027-07-24 | 30 | 30-16
2027-07-25 | 31 | 31-16
2027-07-26 | 31 | 31-16
2027-07-27 | 31 | 31-16
2027-07-28 | 31 | 31-16
2027-07-29 | 31 | 31-16
2027-07-30 | 31 | 31-16
2027-07-31 | 31 | 31-16
2027-08-01 | 32 | 32-16
2027-08-02 | 32 | 32-16
2027-08-03 | 32 | 32-16
2027-08-04 | 32 | 32-16
2027-08-05 | 32 | 32-16
2027-08-06 | 32 | 32-16
2027-08-07 | 32 | 32-16
2027-08-08 | 33 | 33-16
2027-08-09 | 33 | 33-16
2027-08-10 | 33 | 33-16
2027-08-11 | 33 | 33-16
2027-08-12 | 33 | 33-16
2027-08-13 | 33 | 33-16
2027-08-14 | 33 | 33-16
2027-08-15 | 34 | 34-16
2027-08-16 | 34 | 34-16
2027-08-17 | 34 | 34-16
2027-08-18 | 34 | 34-16
2027-08-19 | 34 | 34-16
2027-08-20 | 34 | 34-16
2027-08-21 | 34 | 34-16
2027-08-22 | 35 | 35-16
2027-08-23 | 35 | 35-16
2027-08-24 | 35 | 35-16
2027-08-25 | 35 | 35-16
2027-08-26 | 35 | 35-16
2027-08-27 | 35 | 35-16
2027-08-28 | 35 | 35-16
2027-08-29 | 36 | 36-16
2027-08-30 | 36 | 36-16
2027-08-31 | 36 | 36-16
2027-09-01 | 36 | 36-16
2027-09-02 | 36 | 36-16
2027-09-03 | 36 | 36-16
2027-09-04 | 36 | 36-16
2027-09-05 | 37 | 37-16
2027-09-06 | 37 | 37-16
2027-09-07 | 37 | 37-16
2027-09-08 | 37 | 37-16
2027-09-09 | 37 | 37-16
2027-09-10 | 37 | 37-16
2027-09-11 | 37 | 37-16
2027-09-12 | 38 | 38-16
2027-09-13 | 38 | 38-16
2027-09-14 | 38 | 38-16
2027-09-15 | 38 | 38-16
2027-09-16 | 38 | 38-16
2027-09-17 | 38 | 38-16
2027-09-18 | 38 | 38-16
2027-09-19 | 39 | 39-16
2027-09-20 | 39 | 39-16
2027-09-21 | 39 | 39-16
2027-09-22 | 39 | 39-16
2027-09-23 | 39 | 39-16
2027-09-24 | 39 | 39-16
2027-09-25 | 39 | 39-16
2027-09-26 | 40 | 40-16
2027-09-27 | 40 | 40-16
2027-09-28 | 40 | 40-16
2027-09-29 | 40 | 40-16
2027-09-30 | 40 | 40-16
2027-10-01 | 40 | 40-16
2027-10-02 | 40 | 40-16
2027-10-03 | 41 | 41-16
2027-10-04 | 41 | 41-16
2027-10-05 | 41 | 41-16
2027-10-06 | 41 | 41-16
2027-10-07 | 41 | 41-16
2027-10-08 | 41 | 41-16
2027-10-09 | 41 | 41-16
2027-10-10 | 42 | 42-16
2027-10-11 | 42 | 42-16
2027-10-12 | 42 | 42-16
2027-10-13 | 42 | 42-16
2027-10-14 | 42 | 42-16
2027-10-15 | 42 | 42-16
2027-10-16 | 42 | 42-16
2027-10-17 | 43 | 43-16
2027-10-18 | 43 | 43-16
2027-10-19 | 43 | 43-16
2027-10-20 | 43 | 43-16
2027-10-21 | 43 | 43-16
2027-10-22 | 43 | 43-16
2027-10-23 | 43 | 43-16
2027-10-24 | 44 | 44-16
2027-10-25 | 44 | 44-16
2027-10-26 | 44 | 44-16
2027-10-27 | 44 | 44-16
2027-10-28 | 44 | 44-16
2027-10-29 | 44 | 44-16
2027-10-30 | 44 | 44-16
2027-10-31 | 45 | 45-16
2027-11-01 | 45 | 45-16
2027-11-02 | 45 | 45-16
2027-11-03 | 45 | 45-16
2027-11-04 | 45 | 45-16
2027-11-05 | 45 | 45-16
2027-11-06 | 45 | 45-16
2027-11-07 | 46 | 46-16
2027-11-08 | 46 | 46-16
2027-11-09 | 46 | 46-16
2027-11-10 | 46 | 46-16
2027-11-11 | 46 | 46-16
2027-11-12 | 46 | 46-16
2027-11-13 | 46 | 46-16
2027-11-14 | 47 | 47-16
2027-11-15 | 47 | 47-16
2027-11-16 | 47 | 47-16
2027-11-17 | 47 | 47-16
2027-11-18 | 47 | 47-16
2027-11-19 | 47 | 47-16
2027-11-20 | 47 | 47-16
2027-11-21 | 48 | 48-16
2027-11-22 | 48 | 48-16
2027-11-23 | 48 | 48-16
2027-11-24 | 48 | 48-16
2027-11-25 | 48 | 48-16
2027-11-26 | 48 | 48-16
2027-11-27 | 48 | 48-16
2027-11-28 | 49 | 49-16
2027-11-29 | 49 | 49-16
2027-11-30 | 49 | 49-16
2027-12-01 | 49 | 49-16
2027-12-02 | 49 | 49-16
2027-12-03 | 49 | 49-16
2027-12-04 | 49 | 49-16
2027-12-05 | 50 | 50-16
2027-12-06 | 50 | 50-16
2027-12-07 | 50 | 50-16
2027-12-08 | 50 | 50-16
2027-12-09 | 50 | 50-16
2027-12-10 | 50 | 50-16
2027-12-11 | 50 | 50-16
2027-12-12 | 51 | 51-16
2027-12-13 | 51 | 51-16
2027-12-14 | 51 | 51-16
2027-12-15 | 51 | 51-16
2027-12-16 | 51 | 51-16
2027-12-17 | 51 | 51-16
2027-12-18 | 51 | 51-16
2027-12-19 | 52 | 52-16
2027-12-20 | 52 | 52-16
2027-12-21 | 52 | 52-16
2027-12-22 | 52 | 52-16
2027-12-23 | 52 | 52-16
2027-12-24 | 52 | 52-16
2027-12-25 | 52 | 52-16
2027-12-26 | 53 | 53-16
2027-12-27 | 53 | 53-16
2027-12-28 | 53 | 53-16
2027-12-29 | 53 | 53-16
2027-12-30 | 53 | 53-16
2027-12-31 | 53 | 53-16
2028-01-01 | 53 | 53-16
2028-01-02 | 1 | 1-17
2028-01-03 | 1 | 1-17
2028-01-04 | 1 | 1-17
2028-01-05 | 1 | 1-17
2028-01-06 | 1 | 1-17
2028-01-07 | 1 | 1-17
2028-01-08 | 1 | 1-17
2028-01-09 | 2 | 2-17
2028-01-10 | 2 | 2-17
2028-01-11 | 2 | 2-17
2028-01-12 | 2 | 2-17
2028-01-13 | 2 | 2-17
2028-01-14 | 2 | 2-17
2028-01-15 | 2 | 2-17
2028-01-16 | 3 | 3-17
2028-01-17 | 3 | 3-17
2028-01-18 | 3 | 3-17
2028-01-19 | 3 | 3-17
2028-01-20 | 3 | 3-17
2028-01-21 | 3 | 3-17
2028-01-22 | 3 | 3-17
2028-01-23 | 4 | 4-17
2028-01-24 | 4 | 4-17
2028-01-25 | 4 | 4-17
2028-01-26 | 4 | 4-17
2028-01-27 | 4 | 4-17
2028-01-28 | 4 | 4-17
2028-01-29 | 4 | 4-17
2028-01-30 | 5 | 5-17
2028-01-31 | 5 | 5-17
2028-02-01 | 5 | 5-17
2028-02-02 | 5 | 5-17
2028-02-03 | 5 | 5-17
2028-02-04 | 5 | 5-17
2028-02-05 | 5 | 5-17
2028-02-06 | 6 | 6-17
2028-02-07 | 6 | 6-17
2028-02-08 | 6 | 6-17
2028-02-09 | 6 | 6-17
2028-02-10 | 6 | 6-17
2028-02-11 | 6 | 6-17
2028-02-12 | 6 | 6-17
2028-02-13 | 7 | 7-17
2028-02-14 | 7 | 7-17
2028-02-15 | 7 | 7-17
2028-02-16 | 7 | 7-17
2028-02-17 | 7 | 7-17
2028-02-18 | 7 | 7-17
2028-02-19 | 7 | 7-17
2028-02-20 | 8 | 8-17
2028-02-21 | 8 | 8-17
2028-02-22 | 8 | 8-17
2028-02-23 | 8 | 8-17
2028-02-24 | 8 | 8-17
2028-02-25 | 8 | 8-17
2028-02-26 | 8 | 8-17
2028-02-27 | 9 | 9-17
2028-02-28 | 9 | 9-17
2028-02-29 | 9 | 9-17
2028-03-01 | 9 | 9-17
2028-03-02 | 9 | 9-17
2028-03-03 | 9 | 9-17
2028-03-04 | 9 | 9-17
2028-03-05 | 10 | 10-17
2028-03-06 | 10 | 10-17
2028-03-07 | 10 | 10-17
2028-03-08 | 10 | 10-17
2028-03-09 | 10 | 10-17
2028-03-10 | 10 | 10-17
2028-03-11 | 10 | 10-17
2028-03-12 | 11 | 11-17
2028-03-13 | 11 | 11-17
2028-03-14 | 11 | 11-17
2028-03-15 | 11 | 11-17
2028-03-16 | 11 | 11-17
2028-03-17 | 11 | 11-17
2028-03-18 | 11 | 11-17
2028-03-19 | 12 | 12-17
2028-03-20 | 12 | 12-17
2028-03-21 | 12 | 12-17
2028-03-22 | 12 | 12-17
2028-03-23 | 12 | 12-17
2028-03-24 | 12 | 12-17
2028-03-25 | 12 | 12-17
2028-03-26 | 13 | 13-17
2028-03-27 | 13 | 13-17
2028-03-28 | 13 | 13-17
2028-03-29 | 13 | 13-17
2028-03-30 | 13 | 13-17
2028-03-31 | 13 | 13-17
2028-04-01 | 13 | 13-17
2028-04-02 | 14 | 14-17
2028-04-03 | 14 | 14-17
2028-04-04 | 14 | 14-17
2028-04-05 | 14 | 14-17
2028-04-06 | 14 | 14-17
2028-04-07 | 14 | 14-17
2028-04-08 | 14 | 14-17
2028-04-09 | 15 | 15-17
2028-04-10 | 15 | 15-17
2028-04-11 | 15 | 15-17
2028-04-12 | 15 | 15-17
2028-04-13 | 15 | 15-17
2028-04-14 | 15 | 15-17
2028-04-15 | 15 | 15-17
2028-04-16 | 16 | 16-17
2028-04-17 | 16 | 16-17
2028-04-18 | 16 | 16-17
2028-04-19 | 16 | 16-17
2028-04-20 | 16 | 16-17
2028-04-21 | 16 | 16-17
2028-04-22 | 16 | 16-17
2028-04-23 | 17 | 17-17
2028-04-24 | 17 | 17-17
2028-04-25 | 17 | 17-17
2028-04-26 | 17 | 17-17
2028-04-27 | 17 | 17-17
2028-04-28 | 17 | 17-17
2028-04-29 | 17 | 17-17
2028-04-30 | 18 | 18-17
2028-05-01 | 18 | 18-17
2028-05-02 | 18 | 18-17
2028-05-03 | 18 | 18-17
2028-05-04 | 18 | 18-17
2028-05-05 | 18 | 18-17
2028-05-06 | 18 | 18-17
2028-05-07 | 19 | 19-17
2028-05-08 | 19 | 19-17
2028-05-09 | 19 | 19-17
2028-05-10 | 19 | 19-17
2028-05-11 | 19 | 19-17
2028-05-12 | 19 | 19-17
2028-05-13 | 19 | 19-17
2028-05-14 | 20 | 20-17
2028-05-15 | 20 | 20-17
2028-05-16 | 20 | 20-17
2028-05-17 | 20 | 20-17
2028-05-18 | 20 | 20-17
2028-05-19 | 20 | 20-17
2028-05-20 | 20 | 20-17
2028-05-21 | 21 | 21-17
2028-05-22 | 21 | 21-17
2028-05-23 | 21 | 21-17
2028-05-24 | 21 | 21-17
2028-05-25 | 21 | 21-17
2028-05-26 | 21 | 21-17
2028-05-27 | 21 | 21-17
2028-05-28 | 22 | 22-17
2028-05-29 | 22 | 22-17
2028-05-30 | 22 | 22-17
2028-05-31 | 22 | 22-17
2028-06-01 | 22 | 22-17
2028-06-02 | 22 | 22-17
2028-06-03 | 22 | 22-17
2028-06-04 | 23 | 23-17
2028-06-05 | 23 | 23-17
2028-06-06 | 23 | 23-17
2028-06-07 | 23 | 23-17
2028-06-08 | 23 | 23-17
2028-06-09 | 23 | 23-17
2028-06-10 | 23 | 23-17
2028-06-11 | 24 | 24-17
2028-06-12 | 24 | 24-17
2028-06-13 | 24 | 24-17
2028-06-14 | 24 | 24-17
2028-06-15 | 24 | 24-17
2028-06-16 | 24 | 24-17
2028-06-17 | 24 | 24-17
2028-06-18 | 25 | 25-17
2028-06-19 | 25 | 25-17
2028-06-20 | 25 | 25-17
2028-06-21 | 25 | 25-17
2028-06-22 | 25 | 25-17
2028-06-23 | 25 | 25-17
2028-06-24 | 25 | 25-17
2028-06-25 | 26 | 26-17
2028-06-26 | 26 | 26-17
2028-06-27 | 26 | 26-17
2028-06-28 | 26 | 26-17
2028-06-29 | 26 | 26-17
2028-06-30 | 26 | 26-17
2028-07-01 | 26 | 26-17
2028-07-02 | 27 | 27-17
2028-07-03 | 27 | 27-17
2028-07-04 | 27 | 27-17
2028-07-05 | 27 | 27-17
2028-07-06 | 27 | 27-17
2028-07-07 | 27 | 27-17
2028-07-08 | 27 | 27-17
2028-07-09 | 28 | 28-17
2028-07-10 | 28 | 28-17
2028-07-11 | 28 | 28-17
2028-07-12 | 28 | 28-17
2028-07-13 | 28 | 28-17
2028-07-14 | 28 | 28-17
2028-07-15 | 28 | 28-17
2028-07-16 | 29 | 29-17
2028-07-17 | 29 | 29-17
2028-07-18 | 29 | 29-17
2028-07-19 | 29 | 29-17
2028-07-20 | 29 | 29-17
2028-07-21 | 29 | 29-17
2028-07-22 | 29 | 29-17
2028-07-23 | 30 | 30-17
2028-07-24 | 30 | 30-17
2028-07-25 | 30 | 30-17
2028-07-26 | 30 | 30-17
2028-07-27 | 30 | 30-17
2028-07-28 | 30 | 30-17
2028-07-29 | 30 | 30-17
2028-07-30 | 31 | 31-17
2028-07-31 | 31 | 31-17
2028-08-01 | 31 | 31-17
2028-08-02 | 31 | 31-17
2028-08-03 | 31 | 31-17
2028-08-04 | 31 | 31-17
2028-08-05 | 31 | 31-17
2028-08-06 | 32 | 32-17
2028-08-07 | 32 | 32-17
2028-08-08 | 32 | 32-17
2028-08-09 | 32 | 32-17
2028-08-10 | 32 | 32-17
2028-08-11 | 32 | 32-17
2028-08-12 | 32 | 32-17
2028-08-13 | 33 | 33-17
2028-08-14 | 33 | 33-17
2028-08-15 | 33 | 33-17
2028-08-16 | 33 | 33-17
2028-08-17 | 33 | 33-17
2028-08-18 | 33 | 33-17
2028-08-19 | 33 | 33-17
2028-08-20 | 34 | 34-17
2028-08-21 | 34 | 34-17
2028-08-22 | 34 | 34-17
2028-08-23 | 34 | 34-17
2028-08-24 | 34 | 34-17
2028-08-25 | 34 | 34-17
2028-08-26 | 34 | 34-17
2028-08-27 | 35 | 35-17
2028-08-28 | 35 | 35-17
2028-08-29 | 35 | 35-17
2028-08-30 | 35 | 35-17
2028-08-31 | 35 | 35-17
2028-09-01 | 35 | 35-17
2028-09-02 | 35 | 35-17
2028-09-03 | 36 | 36-17
2028-09-04 | 36 | 36-17
2028-09-05 | 36 | 36-17
2028-09-06 | 36 | 36-17
2028-09-07 | 36 | 36-17
2028-09-08 | 36 | 36-17
2028-09-09 | 36 | 36-17
2028-09-10 | 37 | 37-17
2028-09-11 | 37 | 37-17
2028-09-12 | 37 | 37-17
2028-09-13 | 37 | 37-17
2028-09-14 | 37 | 37-17
2028-09-15 | 37 | 37-17
2028-09-16 | 37 | 37-17
2028-09-17 | 38 | 38-17
2028-09-18 | 38 | 38-17
2028-09-19 | 38 | 38-17
2028-09-20 | 38 | 38-17
2028-09-21 | 38 | 38-17
2028-09-22 | 38 | 38-17
2028-09-23 | 38 | 38-17
2028-09-24 | 39 | 39-17
2028-09-25 | 39 | 39-17
2028-09-26 | 39 | 39-17
2028-09-27 | 39 | 39-17
2028-09-28 | 39 | 39-17
2028-09-29 | 39 | 39-17
2028-09-30 | 39 | 39-17
2028-10-01 | 40 | 40-17
2028-10-02 | 40 | 40-17
2028-10-03 | 40 | 40-17
2028-10-04 | 40 | 40-17
2028-10-05 | 40 | 40-17
2028-10-06 | 40 | 40-17
2028-10-07 | 40 | 40-17
2028-10-08 | 41 | 41-17
2028-10-09 | 41 | 41-17
2028-10-10 | 41 | 41-17
2028-10-11 | 41 | 41-17
2028-10-12 | 41 | 41-17
2028-10-13 | 41 | 41-17
2028-10-14 | 41 | 41-17
2028-10-15 | 42 | 42-17
2028-10-16 | 42 | 42-17
2028-10-17 | 42 | 42-17
2028-10-18 | 42 | 42-17
2028-10-19 | 42 | 42-17
2028-10-20 | 42 | 42-17
2028-10-21 | 42 | 42-17
2028-10-22 | 43 | 43-17
2028-10-23 | 43 | 43-17
2028-10-24 | 43 | 43-17
2028-10-25 | 43 | 43-17
2028-10-26 | 43 | 43-17
2028-10-27 | 43 | 43-17
2028-10-28 | 43 | 43-17
2028-10-29 | 44 | 44-17
2028-10-30 | 44 | 44-17
2028-10-31 | 44 | 44-17
2028-11-01 | 44 | 44-17
2028-11-02 | 44 | 44-17
2028-11-03 | 44 | 44-17
2028-11-04 | 44 | 44-17
2028-11-05 | 45 | 45-17
2028-11-06 | 45 | 45-17
2028-11-07 | 45 | 45-17
2028-11-08 | 45 | 45-17
2028-11-09 | 45 | 45-17
2028-11-10 | 45 | 45-17
2028-11-11 | 45 | 45-17
2028-11-12 | 46 | 46-17
2028-11-13 | 46 | 46-17
2028-11-14 | 46 | 46-17
2028-11-15 | 46 | 46-17
2028-11-16 | 46 | 46-17
2028-11-17 | 46 | 46-17
2028-11-18 | 46 | 46-17
2028-11-19 | 47 | 47-17
2028-11-20 | 47 | 47-17
2028-11-21 | 47 | 47-17
2028-11-22 | 47 | 47-17
2028-11-23 | 47 | 47-17
2028-11-24 | 47 | 47-17
2028-11-25 | 47 | 47-17
2028-11-26 | 48 | 48-17
2028-11-27 | 48 | 48-17
2028-11-28 | 48 | 48-17
2028-11-29 | 48 | 48-17
2028-11-30 | 48 | 48-17
2028-12-01 | 48 | 48-17
2028-12-02 | 48 | 48-17
2028-12-03 | 49 | 49-17
2028-12-04 | 49 | 49-17
2028-12-05 | 49 | 49-17
2028-12-06 | 49 | 49-17
2028-12-07 | 49 | 49-17
2028-12-08 | 49 | 49-17
2028-12-09 | 49 | 49-17
2028-12-10 | 50 | 50-17
2028-12-11 | 50 | 50-17
2028-12-12 | 50 | 50-17
2028-12-13 | 50 | 50-17
2028-12-14 | 50 | 50-17
2028-12-15 | 50 | 50-17
2028-12-16 | 50 | 50-17
2028-12-17 | 51 | 51-17
2028-12-18 | 51 | 51-17
2028-12-19 | 51 | 51-17
2028-12-20 | 51 | 51-17
2028-12-21 | 51 | 51-17
2028-12-22 | 51 | 51-17
2028-12-23 | 51 | 51-17
2028-12-24 | 52 | 52-17
2028-12-25 | 52 | 52-17
2028-12-26 | 52 | 52-17
2028-12-27 | 52 | 52-17
2028-12-28 | 52 | 52-17
2028-12-29 | 52 | 52-17
2028-12-30 | 52 | 52-17
2028-12-31 | 53 | 53-17
2029-01-01 | 1 | 1-18
2029-01-02 | 1 | 1-18
2029-01-03 | 1 | 1-18
2029-01-04 | 1 | 1-18
2029-01-05 | 1 | 1-18
2029-01-06 | 1 | 1-18
2029-01-07 | 2 | 2-18
2029-01-08 | 2 | 2-18
2029-01-09 | 2 | 2-18
2029-01-10 | 2 | 2-18
2029-01-11 | 2 | 2-18
2029-01-12 | 2 | 2-18
2029-01-13 | 2 | 2-18
2029-01-14 | 3 | 3-18
2029-01-15 | 3 | 3-18
2029-01-16 | 3 | 3-18
2029-01-17 | 3 | 3-18
2029-01-18 | 3 | 3-18
2029-01-19 | 3 | 3-18
2029-01-20 | 3 | 3-18
2029-01-21 | 4 | 4-18
2029-01-22 | 4 | 4-18
2029-01-23 | 4 | 4-18
2029-01-24 | 4 | 4-18
2029-01-25 | 4 | 4-18
2029-01-26 | 4 | 4-18
2029-01-27 | 4 | 4-18
2029-01-28 | 5 | 5-18
2029-01-29 | 5 | 5-18
2029-01-30 | 5 | 5-18
2029-01-31 | 5 | 5-18
2029-02-01 | 5 | 5-18
2029-02-02 | 5 | 5-18
2029-02-03 | 5 | 5-18
2029-02-04 | 6 | 6-18
2029-02-05 | 6 | 6-18
2029-02-06 | 6 | 6-18
2029-02-07 | 6 | 6-18
2029-02-08 | 6 | 6-18
2029-02-09 | 6 | 6-18
2029-02-10 | 6 | 6-18
2029-02-11 | 7 | 7-18
2029-02-12 | 7 | 7-18
2029-02-13 | 7 | 7-18
2029-02-14 | 7 | 7-18
2029-02-15 | 7 | 7-18
2029-02-16 | 7 | 7-18
2029-02-17 | 7 | 7-18
2029-02-18 | 8 | 8-18
2029-02-19 | 8 | 8-18
2029-02-20 | 8 | 8-18
2029-02-21 | 8 | 8-18
2029-02-22 | 8 | 8-18
2029-02-23 | 8 | 8-18
2029-02-24 | 8 | 8-18
2029-02-25 | 9 | 9-18
2029-02-26 | 9 | 9-18
2029-02-27 | 9 | 9-18
2029-02-28 | 9 | 9-18
2029-03-01 | 9 | 9-18
2029-03-02 | 9 | 9-18
2029-03-03 | 9 | 9-18
2029-03-04 | 10 | 10-18
2029-03-05 | 10 | 10-18
2029-03-06 | 10 | 10-18
2029-03-07 | 10 | 10-18
2029-03-08 | 10 | 10-18
2029-03-09 | 10 | 10-18
2029-03-10 | 10 | 10-18
2029-03-11 | 11 | 11-18
2029-03-12 | 11 | 11-18
2029-03-13 | 11 | 11-18
2029-03-14 | 11 | 11-18
2029-03-15 | 11 | 11-18
2029-03-16 | 11 | 11-18
2029-03-17 | 11 | 11-18
2029-03-18 | 12 | 12-18
2029-03-19 | 12 | 12-18
2029-03-20 | 12 | 12-18
2029-03-21 | 12 | 12-18
2029-03-22 | 12 | 12-18
2029-03-23 | 12 | 12-18
2029-03-24 | 12 | 12-18
2029-03-25 | 13 | 13-18
2029-03-26 | 13 | 13-18
2029-03-27 | 13 | 13-18
2029-03-28 | 13 | 13-18
2029-03-29 | 13 | 13-18
2029-03-30 | 13 | 13-18
2029-03-31 | 13 | 13-18
2029-04-01 | 14 | 14-18
2029-04-02 | 14 | 14-18
2029-04-03 | 14 | 14-18
2029-04-04 | 14 | 14-18
2029-04-05 | 14 | 14-18
2029-04-06 | 14 | 14-18
2029-04-07 | 14 | 14-18
2029-04-08 | 15 | 15-18
2029-04-09 | 15 | 15-18
2029-04-10 | 15 | 15-18
2029-04-11 | 15 | 15-18
2029-04-12 | 15 | 15-18
2029-04-13 | 15 | 15-18
2029-04-14 | 15 | 15-18
2029-04-15 | 16 | 16-18
2029-04-16 | 16 | 16-18
2029-04-17 | 16 | 16-18
2029-04-18 | 16 | 16-18
2029-04-19 | 16 | 16-18
2029-04-20 | 16 | 16-18
2029-04-21 | 16 | 16-18
2029-04-22 | 17 | 17-18
2029-04-23 | 17 | 17-18
2029-04-24 | 17 | 17-18
2029-04-25 | 17 | 17-18
2029-04-26 | 17 | 17-18
2029-04-27 | 17 | 17-18
2029-04-28 | 17 | 17-18
2029-04-29 | 18 | 18-18
2029-04-30 | 18 | 18-18
2029-05-01 | 18 | 18-18
2029-05-02 | 18 | 18-18
2029-05-03 | 18 | 18-18
2029-05-04 | 18 | 18-18
2029-05-05 | 18 | 18-18
2029-05-06 | 19 | 19-18
2029-05-07 | 19 | 19-18
2029-05-08 | 19 | 19-18
2029-05-09 | 19 | 19-18
2029-05-10 | 19 | 19-18
2029-05-11 | 19 | 19-18
2029-05-12 | 19 | 19-18
2029-05-13 | 20 | 20-18
2029-05-14 | 20 | 20-18
2029-05-15 | 20 | 20-18
2029-05-16 | 20 | 20-18
2029-05-17 | 20 | 20-18
2029-05-18 | 20 | 20-18
2029-05-19 | 20 | 20-18
2029-05-20 | 21 | 21-18
2029-05-21 | 21 | 21-18
2029-05-22 | 21 | 21-18
2029-05-23 | 21 | 21-18
2029-05-24 | 21 | 21-18
2029-05-25 | 21 | 21-18
2029-05-26 | 21 | 21-18
2029-05-27 | 22 | 22-18
2029-05-28 | 22 | 22-18
2029-05-29 | 22 | 22-18
2029-05-30 | 22 | 22-18
2029-05-31 | 22 | 22-18
2029-06-01 | 22 | 22-18
2029-06-02 | 22 | 22-18
2029-06-03 | 23 | 23-18
2029-06-04 | 23 | 23-18
2029-06-05 | 23 | 23-18
2029-06-06 | 23 | 23-18
2029-06-07 | 23 | 23-18
2029-06-08 | 23 | 23-18
2029-06-09 | 23 | 23-18
2029-06-10 | 24 | 24-18
2029-06-11 | 24 | 24-18
2029-06-12 | 24 | 24-18
2029-06-13 | 24 | 24-18
2029-06-14 | 24 | 24-18
2029-06-15 | 24 | 24-18
2029-06-16 | 24 | 24-18
2029-06-17 | 25 | 25-18
2029-06-18 | 25 | 25-18
2029-06-19 | 25 | 25-18
2029-06-20 | 25 | 25-18
2029-06-21 | 25 | 25-18
2029-06-22 | 25 | 25-18
2029-06-23 | 25 | 25-18
2029-06-24 | 26 | 26-18
2029-06-25 | 26 | 26-18
2029-06-26 | 26 | 26-18
2029-06-27 | 26 | 26-18
2029-06-28 | 26 | 26-18
2029-06-29 | 26 | 26-18
2029-06-30 | 26 | 26-18
2029-07-01 | 27 | 27-18
2029-07-02 | 27 | 27-18
2029-07-03 | 27 | 27-18
2029-07-04 | 27 | 27-18
2029-07-05 | 27 | 27-18
2029-07-06 | 27 | 27-18
2029-07-07 | 27 | 27-18
2029-07-08 | 28 | 28-18
2029-07-09 | 28 | 28-18
2029-07-10 | 28 | 28-18
2029-07-11 | 28 | 28-18
2029-07-12 | 28 | 28-18
2029-07-13 | 28 | 28-18
2029-07-14 | 28 | 28-18
2029-07-15 | 29 | 29-18
2029-07-16 | 29 | 29-18
2029-07-17 | 29 | 29-18
2029-07-18 | 29 | 29-18
2029-07-19 | 29 | 29-18
2029-07-20 | 29 | 29-18
2029-07-21 | 29 | 29-18
2029-07-22 | 30 | 30-18
2029-07-23 | 30 | 30-18
2029-07-24 | 30 | 30-18
2029-07-25 | 30 | 30-18
2029-07-26 | 30 | 30-18
2029-07-27 | 30 | 30-18
2029-07-28 | 30 | 30-18
2029-07-29 | 31 | 31-18
2029-07-30 | 31 | 31-18
2029-07-31 | 31 | 31-18
2029-08-01 | 31 | 31-18
2029-08-02 | 31 | 31-18
2029-08-03 | 31 | 31-18
2029-08-04 | 31 | 31-18
2029-08-05 | 32 | 32-18
2029-08-06 | 32 | 32-18
2029-08-07 | 32 | 32-18
2029-08-08 | 32 | 32-18
2029-08-09 | 32 | 32-18
2029-08-10 | 32 | 32-18
2029-08-11 | 32 | 32-18
2029-08-12 | 33 | 33-18
2029-08-13 | 33 | 33-18
2029-08-14 | 33 | 33-18
2029-08-15 | 33 | 33-18
2029-08-16 | 33 | 33-18
2029-08-17 | 33 | 33-18
2029-08-18 | 33 | 33-18
2029-08-19 | 34 | 34-18
2029-08-20 | 34 | 34-18
2029-08-21 | 34 | 34-18
2029-08-22 | 34 | 34-18
2029-08-23 | 34 | 34-18
2029-08-24 | 34 | 34-18
2029-08-25 | 34 | 34-18
2029-08-26 | 35 | 35-18
2029-08-27 | 35 | 35-18
2029-08-28 | 35 | 35-18
2029-08-29 | 35 | 35-18
2029-08-30 | 35 | 35-18
2029-08-31 | 35 | 35-18
2029-09-01 | 35 | 35-18
2029-09-02 | 36 | 36-18
2029-09-03 | 36 | 36-18
2029-09-04 | 36 | 36-18
2029-09-05 | 36 | 36-18
2029-09-06 | 36 | 36-18
2029-09-07 | 36 | 36-18
2029-09-08 | 36 | 36-18
2029-09-09 | 37 | 37-18
2029-09-10 | 37 | 37-18
2029-09-11 | 37 | 37-18
2029-09-12 | 37 | 37-18
2029-09-13 | 37 | 37-18
2029-09-14 | 37 | 37-18
2029-09-15 | 37 | 37-18
2029-09-16 | 38 | 38-18
2029-09-17 | 38 | 38-18
2029-09-18 | 38 | 38-18
2029-09-19 | 38 | 38-18
2029-09-20 | 38 | 38-18
2029-09-21 | 38 | 38-18
2029-09-22 | 38 | 38-18
2029-09-23 | 39 | 39-18
2029-09-24 | 39 | 39-18
2029-09-25 | 39 | 39-18
2029-09-26 | 39 | 39-18
2029-09-27 | 39 | 39-18
2029-09-28 | 39 | 39-18
2029-09-29 | 39 | 39-18
2029-09-30 | 40 | 40-18
2029-10-01 | 40 | 40-18
2029-10-02 | 40 | 40-18
2029-10-03 | 40 | 40-18
2029-10-04 | 40 | 40-18
2029-10-05 | 40 | 40-18
2029-10-06 | 40 | 40-18
2029-10-07 | 41 | 41-18
2029-10-08 | 41 | 41-18
2029-10-09 | 41 | 41-18
2029-10-10 | 41 | 41-18
2029-10-11 | 41 | 41-18
2029-10-12 | 41 | 41-18
2029-10-13 | 41 | 41-18
2029-10-14 | 42 | 42-18
2029-10-15 | 42 | 42-18
2029-10-16 | 42 | 42-18
2029-10-17 | 42 | 42-18
2029-10-18 | 42 | 42-18
2029-10-19 | 42 | 42-18
2029-10-20 | 42 | 42-18
2029-10-21 | 43 | 43-18
2029-10-22 | 43 | 43-18
2029-10-23 | 43 | 43-18
2029-10-24 | 43 | 43-18
2029-10-25 | 43 | 43-18
2029-10-26 | 43 | 43-18
2029-10-27 | 43 | 43-18
2029-10-28 | 44 | 44-18
2029-10-29 | 44 | 44-18
2029-10-30 | 44 | 44-18
2029-10-31 | 44 | 44-18
2029-11-01 | 44 | 44-18
2029-11-02 | 44 | 44-18
2029-11-03 | 44 | 44-18
2029-11-04 | 45 | 45-18
2029-11-05 | 45 | 45-18
2029-11-06 | 45 | 45-18
2029-11-07 | 45 | 45-18
2029-11-08 | 45 | 45-18
2029-11-09 | 45 | 45-18
2029-11-10 | 45 | 45-18
2029-11-11 | 46 | 46-18
2029-11-12 | 46 | 46-18
2029-11-13 | 46 | 46-18
2029-11-14 | 46 | 46-18
2029-11-15 | 46 | 46-18
2029-11-16 | 46 | 46-18
2029-11-17 | 46 | 46-18
2029-11-18 | 47 | 47-18
2029-11-19 | 47 | 47-18
2029-11-20 | 47 | 47-18
2029-11-21 | 47 | 47-18
2029-11-22 | 47 | 47-18
2029-11-23 | 47 | 47-18
2029-11-24 | 47 | 47-18
2029-11-25 | 48 | 48-18
2029-11-26 | 48 | 48-18
2029-11-27 | 48 | 48-18
2029-11-28 | 48 | 48-18
2029-11-29 | 48 | 48-18
2029-11-30 | 48 | 48-18
2029-12-01 | 48 | 48-18
2029-12-02 | 49 | 49-18
2029-12-03 | 49 | 49-18
2029-12-04 | 49 | 49-18
2029-12-05 | 49 | 49-18
2029-12-06 | 49 | 49-18
2029-12-07 | 49 | 49-18
2029-12-08 | 49 | 49-18
2029-12-09 | 50 | 50-18
2029-12-10 | 50 | 50-18
2029-12-11 | 50 | 50-18
2029-12-12 | 50 | 50-18
2029-12-13 | 50 | 50-18
2029-12-14 | 50 | 50-18
2029-12-15 | 50 | 50-18
2029-12-16 | 51 | 51-18
2029-12-17 | 51 | 51-18
2029-12-18 | 51 | 51-18
2029-12-19 | 51 | 51-18
2029-12-20 | 51 | 51-18
2029-12-21 | 51 | 51-18
2029-12-22 | 51 | 51-18
2029-12-23 | 52 | 52-18
2029-12-24 | 52 | 52-18
2029-12-25 | 52 | 52-18
2029-12-26 | 52 | 52-18
2029-12-27 | 52 | 52-18
2029-12-28 | 52 | 52-18
2029-12-29 | 52 | 52-18
2029-12-30 | 53 | 53-18
2029-12-31 | 53 | 53-18
2030-01-01 | 1 | 1-19
2030-01-02 | 1 | 1-19
2030-01-03 | 1 | 1-19
2030-01-04 | 1 | 1-19
2030-01-05 | 1 | 1-19
2030-01-06 | 2 | 2-19
2030-01-07 | 2 | 2-19
2030-01-08 | 2 | 2-19
2030-01-09 | 2 | 2-19
2030-01-10 | 2 | 2-19
2030-01-11 | 2 | 2-19
2030-01-12 | 2 | 2-19
2030-01-13 | 3 | 3-19
2030-01-14 | 3 | 3-19
2030-01-15 | 3 | 3-19
2030-01-16 | 3 | 3-19
2030-01-17 | 3 | 3-19
2030-01-18 | 3 | 3-19
2030-01-19 | 3 | 3-19
2030-01-20 | 4 | 4-19
2030-01-21 | 4 | 4-19
2030-01-22 | 4 | 4-19
2030-01-23 | 4 | 4-19
2030-01-24 | 4 | 4-19
2030-01-25 | 4 | 4-19
2030-01-26 | 4 | 4-19
2030-01-27 | 5 | 5-19
2030-01-28 | 5 | 5-19
2030-01-29 | 5 | 5-19
2030-01-30 | 5 | 5-19
2030-01-31 | 5 | 5-19
2030-02-01 | 5 | 5-19
2030-02-02 | 5 | 5-19
2030-02-03 | 6 | 6-19
2030-02-04 | 6 | 6-19
2030-02-05 | 6 | 6-19
2030-02-06 | 6 | 6-19
2030-02-07 | 6 | 6-19
2030-02-08 | 6 | 6-19
2030-02-09 | 6 | 6-19
2030-02-10 | 7 | 7-19
2030-02-11 | 7 | 7-19
2030-02-12 | 7 | 7-19
2030-02-13 | 7 | 7-19
2030-02-14 | 7 | 7-19
2030-02-15 | 7 | 7-19
2030-02-16 | 7 | 7-19
2030-02-17 | 8 | 8-19
2030-02-18 | 8 | 8-19
2030-02-19 | 8 | 8-19
2030-02-20 | 8 | 8-19
2030-02-21 | 8 | 8-19
2030-02-22 | 8 | 8-19
2030-02-23 | 8 | 8-19
2030-02-24 | 9 | 9-19
2030-02-25 | 9 | 9-19
2030-02-26 | 9 | 9-19
2030-02-27 | 9 | 9-19
2030-02-28 | 9 | 9-19
2030-03-01 | 9 | 9-19
2030-03-02 | 9 | 9-19
2030-03-03 | 10 | 10-19
2030-03-04 | 10 | 10-19
2030-03-05 | 10 | 10-19
2030-03-06 | 10 | 10-19
2030-03-07 | 10 | 10-19
2030-03-08 | 10 | 10-19
2030-03-09 | 10 | 10-19
2030-03-10 | 11 | 11-19
2030-03-11 | 11 | 11-19
2030-03-12 | 11 | 11-19
2030-03-13 | 11 | 11-19
2030-03-14 | 11 | 11-19
2030-03-15 | 11 | 11-19
2030-03-16 | 11 | 11-19
2030-03-17 | 12 | 12-19
2030-03-18 | 12 | 12-19
2030-03-19 | 12 | 12-19
2030-03-20 | 12 | 12-19
2030-03-21 | 12 | 12-19
2030-03-22 | 12 | 12-19
2030-03-23 | 12 | 12-19
2030-03-24 | 13 | 13-19
2030-03-25 | 13 | 13-19
2030-03-26 | 13 | 13-19
2030-03-27 | 13 | 13-19
2030-03-28 | 13 | 13-19
2030-03-29 | 13 | 13-19
2030-03-30 | 13 | 13-19
2030-03-31 | 14 | 14-19
2030-04-01 | 14 | 14-19
2030-04-02 | 14 | 14-19
2030-04-03 | 14 | 14-19
2030-04-04 | 14 | 14-19
2030-04-05 | 14 | 14-19
2030-04-06 | 14 | 14-19
2030-04-07 | 15 | 15-19
2030-04-08 | 15 | 15-19
2030-04-09 | 15 | 15-19
2030-04-10 | 15 | 15-19
2030-04-11 | 15 | 15-19
2030-04-12 | 15 | 15-19
2030-04-13 | 15 | 15-19
2030-04-14 | 16 | 16-19
2030-04-15 | 16 | 16-19
2030-04-16 | 16 | 16-19
2030-04-17 | 16 | 16-19
2030-04-18 | 16 | 16-19
2030-04-19 | 16 | 16-19
2030-04-20 | 16 | 16-19
2030-04-21 | 17 | 17-19
2030-04-22 | 17 | 17-19
2030-04-23 | 17 | 17-19
2030-04-24 | 17 | 17-19
2030-04-25 | 17 | 17-19
2030-04-26 | 17 | 17-19
2030-04-27 | 17 | 17-19
2030-04-28 | 18 | 18-19
2030-04-29 | 18 | 18-19
2030-04-30 | 18 | 18-19
2030-05-01 | 18 | 18-19
2030-05-02 | 18 | 18-19
2030-05-03 | 18 | 18-19
2030-05-04 | 18 | 18-19
2030-05-05 | 19 | 19-19
2030-05-06 | 19 | 19-19
2030-05-07 | 19 | 19-19
2030-05-08 | 19 | 19-19
2030-05-09 | 19 | 19-19
2030-05-10 | 19 | 19-19
2030-05-11 | 19 | 19-19
2030-05-12 | 20 | 20-19
2030-05-13 | 20 | 20-19
2030-05-14 | 20 | 20-19
2030-05-15 | 20 | 20-19
2030-05-16 | 20 | 20-19
2030-05-17 | 20 | 20-19
2030-05-18 | 20 | 20-19
2030-05-19 | 21 | 21-19
2030-05-20 | 21 | 21-19
2030-05-21 | 21 | 21-19
2030-05-22 | 21 | 21-19
2030-05-23 | 21 | 21-19
2030-05-24 | 21 | 21-19
2030-05-25 | 21 | 21-19
2030-05-26 | 22 | 22-19
2030-05-27 | 22 | 22-19
2030-05-28 | 22 | 22-19
2030-05-29 | 22 | 22-19
2030-05-30 | 22 | 22-19
2030-05-31 | 22 | 22-19
2030-06-01 | 22 | 22-19
2030-06-02 | 23 | 23-19
2030-06-03 | 23 | 23-19
2030-06-04 | 23 | 23-19
2030-06-05 | 23 | 23-19
2030-06-06 | 23 | 23-19
2030-06-07 | 23 | 23-19
2030-06-08 | 23 | 23-19
2030-06-09 | 24 | 24-19
2030-06-10 | 24 | 24-19
2030-06-11 | 24 | 24-19
2030-06-12 | 24 | 24-19
2030-06-13 | 24 | 24-19
2030-06-14 | 24 | 24-19
2030-06-15 | 24 | 24-19
2030-06-16 | 25 | 25-19
2030-06-17 | 25 | 25-19
2030-06-18 | 25 | 25-19
2030-06-19 | 25 | 25-19
2030-06-20 | 25 | 25-19
2030-06-21 | 25 | 25-19
2030-06-22 | 25 | 25-19
2030-06-23 | 26 | 26-19
2030-06-24 | 26 | 26-19
2030-06-25 | 26 | 26-19
2030-06-26 | 26 | 26-19
2030-06-27 | 26 | 26-19
2030-06-28 | 26 | 26-19
2030-06-29 | 26 | 26-19
2030-06-30 | 27 | 27-19
2030-07-01 | 27 | 27-19
2030-07-02 | 27 | 27-19
2030-07-03 | 27 | 27-19
2030-07-04 | 27 | 27-19
2030-07-05 | 27 | 27-19
2030-07-06 | 27 | 27-19
2030-07-07 | 28 | 28-19
2030-07-08 | 28 | 28-19
2030-07-09 | 28 | 28-19
2030-07-10 | 28 | 28-19
2030-07-11 | 28 | 28-19
2030-07-12 | 28 | 28-19
2030-07-13 | 28 | 28-19
2030-07-14 | 29 | 29-19
2030-07-15 | 29 | 29-19
2030-07-16 | 29 | 29-19
2030-07-17 | 29 | 29-19
2030-07-18 | 29 | 29-19
2030-07-19 | 29 | 29-19
2030-07-20 | 29 | 29-19
2030-07-21 | 30 | 30-19
2030-07-22 | 30 | 30-19
2030-07-23 | 30 | 30-19
2030-07-24 | 30 | 30-19
2030-07-25 | 30 | 30-19
2030-07-26 | 30 | 30-19
2030-07-27 | 30 | 30-19
2030-07-28 | 31 | 31-19
2030-07-29 | 31 | 31-19
2030-07-30 | 31 | 31-19
2030-07-31 | 31 | 31-19
2030-08-01 | 31 | 31-19
2030-08-02 | 31 | 31-19
2030-08-03 | 31 | 31-19
2030-08-04 | 32 | 32-19
2030-08-05 | 32 | 32-19
2030-08-06 | 32 | 32-19
2030-08-07 | 32 | 32-19
2030-08-08 | 32 | 32-19
2030-08-09 | 32 | 32-19
2030-08-10 | 32 | 32-19
2030-08-11 | 33 | 33-19
2030-08-12 | 33 | 33-19
2030-08-13 | 33 | 33-19
2030-08-14 | 33 | 33-19
2030-08-15 | 33 | 33-19
2030-08-16 | 33 | 33-19
2030-08-17 | 33 | 33-19
2030-08-18 | 34 | 34-19
2030-08-19 | 34 | 34-19
2030-08-20 | 34 | 34-19
2030-08-21 | 34 | 34-19
2030-08-22 | 34 | 34-19
2030-08-23 | 34 | 34-19
2030-08-24 | 34 | 34-19
2030-08-25 | 35 | 35-19
2030-08-26 | 35 | 35-19
2030-08-27 | 35 | 35-19
2030-08-28 | 35 | 35-19
2030-08-29 | 35 | 35-19
2030-08-30 | 35 | 35-19
2030-08-31 | 35 | 35-19
2030-09-01 | 36 | 36-19
2030-09-02 | 36 | 36-19
2030-09-03 | 36 | 36-19
2030-09-04 | 36 | 36-19
2030-09-05 | 36 | 36-19
2030-09-06 | 36 | 36-19
2030-09-07 | 36 | 36-19
2030-09-08 | 37 | 37-19
2030-09-09 | 37 | 37-19
2030-09-10 | 37 | 37-19
2030-09-11 | 37 | 37-19
2030-09-12 | 37 | 37-19
2030-09-13 | 37 | 37-19
2030-09-14 | 37 | 37-19
2030-09-15 | 38 | 38-19
2030-09-16 | 38 | 38-19
2030-09-17 | 38 | 38-19
2030-09-18 | 38 | 38-19
2030-09-19 | 38 | 38-19
2030-09-20 | 38 | 38-19
2030-09-21 | 38 | 38-19
2030-09-22 | 39 | 39-19
2030-09-23 | 39 | 39-19
2030-09-24 | 39 | 39-19
2030-09-25 | 39 | 39-19
2030-09-26 | 39 | 39-19
2030-09-27 | 39 | 39-19
2030-09-28 | 39 | 39-19
2030-09-29 | 40 | 40-19
2030-09-30 | 40 | 40-19
2030-10-01 | 40 | 40-19
2030-10-02 | 40 | 40-19
2030-10-03 | 40 | 40-19
2030-10-04 | 40 | 40-19
2030-10-05 | 40 | 40-19
2030-10-06 | 41 | 41-19
2030-10-07 | 41 | 41-19
2030-10-08 | 41 | 41-19
2030-10-09 | 41 | 41-19
2030-10-10 | 41 | 41-19
2030-10-11 | 41 | 41-19
2030-10-12 | 41 | 41-19
2030-10-13 | 42 | 42-19
2030-10-14 | 42 | 42-19
2030-10-15 | 42 | 42-19
2030-10-16 | 42 | 42-19
2030-10-17 | 42 | 42-19
2030-10-18 | 42 | 42-19
2030-10-19 | 42 | 42-19
2030-10-20 | 43 | 43-19
2030-10-21 | 43 | 43-19
2030-10-22 | 43 | 43-19
2030-10-23 | 43 | 43-19
2030-10-24 | 43 | 43-19
2030-10-25 | 43 | 43-19
2030-10-26 | 43 | 43-19
2030-10-27 | 44 | 44-19
2030-10-28 | 44 | 44-19
2030-10-29 | 44 | 44-19
2030-10-30 | 44 | 44-19
2030-10-31 | 44 | 44-19
2030-11-01 | 44 | 44-19
2030-11-02 | 44 | 44-19
2030-11-03 | 45 | 45-19
2030-11-04 | 45 | 45-19
2030-11-05 | 45 | 45-19
2030-11-06 | 45 | 45-19
2030-11-07 | 45 | 45-19
2030-11-08 | 45 | 45-19
2030-11-09 | 45 | 45-19
2030-11-10 | 46 | 46-19
2030-11-11 | 46 | 46-19
2030-11-12 | 46 | 46-19
2030-11-13 | 46 | 46-19
2030-11-14 | 46 | 46-19
2030-11-15 | 46 | 46-19
2030-11-16 | 46 | 46-19
2030-11-17 | 47 | 47-19
2030-11-18 | 47 | 47-19
2030-11-19 | 47 | 47-19
2030-11-20 | 47 | 47-19
2030-11-21 | 47 | 47-19
2030-11-22 | 47 | 47-19
2030-11-23 | 47 | 47-19
2030-11-24 | 48 | 48-19
2030-11-25 | 48 | 48-19
2030-11-26 | 48 | 48-19
2030-11-27 | 48 | 48-19
2030-11-28 | 48 | 48-19
2030-11-29 | 48 | 48-19
2030-11-30 | 48 | 48-19
2030-12-01 | 49 | 49-19
2030-12-02 | 49 | 49-19
2030-12-03 | 49 | 49-19
2030-12-04 | 49 | 49-19
2030-12-05 | 49 | 49-19
2030-12-06 | 49 | 49-19
2030-12-07 | 49 | 49-19
2030-12-08 | 50 | 50-19
2030-12-09 | 50 | 50-19
2030-12-10 | 50 | 50-19
2030-12-11 | 50 | 50-19
2030-12-12 | 50 | 50-19
2030-12-13 | 50 | 50-19
2030-12-14 | 50 | 50-19
2030-12-15 | 51 | 51-19
2030-12-16 | 51 | 51-19
2030-12-17 | 51 | 51-19
2030-12-18 | 51 | 51-19
2030-12-19 | 51 | 51-19
2030-12-20 | 51 | 51-19
2030-12-21 | 51 | 51-19
2030-12-22 | 52 | 52-19
2030-12-23 | 52 | 52-19
2030-12-24 | 52 | 52-19
2030-12-25 | 52 | 52-19
2030-12-26 | 52 | 52-19
2030-12-27 | 52 | 52-19
2030-12-28 | 52 | 52-19
2030-12-29 | 53 | 53-19
2030-12-30 | 53 | 53-19
2030-12-31 | 53 | 53-19
2031-01-01 | 1 | 1-20
2031-01-02 | 1 | 1-20
2031-01-03 | 1 | 1-20
2031-01-04 | 1 | 1-20
2031-01-05 | 2 | 2-20
2031-01-06 | 2 | 2-20
2031-01-07 | 2 | 2-20
2031-01-08 | 2 | 2-20
2031-01-09 | 2 | 2-20
2031-01-10 | 2 | 2-20
2031-01-11 | 2 | 2-20
2031-01-12 | 3 | 3-20
2031-01-13 | 3 | 3-20
2031-01-14 | 3 | 3-20
2031-01-15 | 3 | 3-20
2031-01-16 | 3 | 3-20
2031-01-17 | 3 | 3-20
2031-01-18 | 3 | 3-20
2031-01-19 | 4 | 4-20
2031-01-20 | 4 | 4-20
2031-01-21 | 4 | 4-20
2031-01-22 | 4 | 4-20
2031-01-23 | 4 | 4-20
2031-01-24 | 4 | 4-20
2031-01-25 | 4 | 4-20
2031-01-26 | 5 | 5-20
2031-01-27 | 5 | 5-20
2031-01-28 | 5 | 5-20
2031-01-29 | 5 | 5-20
2031-01-30 | 5 | 5-20
2031-01-31 | 5 | 5-20
2031-02-01 | 5 | 5-20
2031-02-02 | 6 | 6-20
2031-02-03 | 6 | 6-20
2031-02-04 | 6 | 6-20
2031-02-05 | 6 | 6-20
2031-02-06 | 6 | 6-20
2031-02-07 | 6 | 6-20
2031-02-08 | 6 | 6-20
2031-02-09 | 7 | 7-20
2031-02-10 | 7 | 7-20
2031-02-11 | 7 | 7-20
2031-02-12 | 7 | 7-20
2031-02-13 | 7 | 7-20
2031-02-14 | 7 | 7-20
2031-02-15 | 7 | 7-20
2031-02-16 | 8 | 8-20
2031-02-17 | 8 | 8-20
2031-02-18 | 8 | 8-20
2031-02-19 | 8 | 8-20
2031-02-20 | 8 | 8-20
2031-02-21 | 8 | 8-20
2031-02-22 | 8 | 8-20
2031-02-23 | 9 | 9-20
2031-02-24 | 9 | 9-20
2031-02-25 | 9 | 9-20
2031-02-26 | 9 | 9-20
2031-02-27 | 9 | 9-20
2031-02-28 | 9 | 9-20
2031-03-01 | 9 | 9-20
2031-03-02 | 10 | 10-20
2031-03-03 | 10 | 10-20
2031-03-04 | 10 | 10-20
2031-03-05 | 10 | 10-20
2031-03-06 | 10 | 10-20
2031-03-07 | 10 | 10-20
2031-03-08 | 10 | 10-20
2031-03-09 | 11 | 11-20
2031-03-10 | 11 | 11-20
2031-03-11 | 11 | 11-20
2031-03-12 | 11 | 11-20
2031-03-13 | 11 | 11-20
2031-03-14 | 11 | 11-20
2031-03-15 | 11 | 11-20
2031-03-16 | 12 | 12-20
2031-03-17 | 12 | 12-20
2031-03-18 | 12 | 12-20
2031-03-19 | 12 | 12-20
2031-03-20 | 12 | 12-20
2031-03-21 | 12 | 12-20
2031-03-22 | 12 | 12-20
2031-03-23 | 13 | 13-20
2031-03-24 | 13 | 13-20
2031-03-25 | 13 | 13-20
2031-03-26 | 13 | 13-20
2031-03-27 | 13 | 13-20
2031-03-28 | 13 | 13-20
2031-03-29 | 13 | 13-20
2031-03-30 | 14 | 14-20
2031-03-31 | 14 | 14-20
2031-04-01 | 14 | 14-20
2031-04-02 | 14 | 14-20
2031-04-03 | 14 | 14-20
2031-04-04 | 14 | 14-20
2031-04-05 | 14 | 14-20
2031-04-06 | 15 | 15-20
2031-04-07 | 15 | 15-20
2031-04-08 | 15 | 15-20
2031-04-09 | 15 | 15-20
2031-04-10 | 15 | 15-20
2031-04-11 | 15 | 15-20
2031-04-12 | 15 | 15-20
2031-04-13 | 16 | 16-20
2031-04-14 | 16 | 16-20
2031-04-15 | 16 | 16-20
2031-04-16 | 16 | 16-20
2031-04-17 | 16 | 16-20
2031-04-18 | 16 | 16-20
2031-04-19 | 16 | 16-20
2031-04-20 | 17 | 17-20
2031-04-21 | 17 | 17-20
2031-04-22 | 17 | 17-20
2031-04-23 | 17 | 17-20
2031-04-24 | 17 | 17-20
2031-04-25 | 17 | 17-20
2031-04-26 | 17 | 17-20
2031-04-27 | 18 | 18-20
2031-04-28 | 18 | 18-20
2031-04-29 | 18 | 18-20
2031-04-30 | 18 | 18-20
2031-05-01 | 18 | 18-20
2031-05-02 | 18 | 18-20
2031-05-03 | 18 | 18-20
2031-05-04 | 19 | 19-20
2031-05-05 | 19 | 19-20
2031-05-06 | 19 | 19-20
2031-05-07 | 19 | 19-20
2031-05-08 | 19 | 19-20
2031-05-09 | 19 | 19-20
2031-05-10 | 19 | 19-20
2031-05-11 | 20 | 20-20
2031-05-12 | 20 | 20-20
2031-05-13 | 20 | 20-20
2031-05-14 | 20 | 20-20
2031-05-15 | 20 | 20-20
2031-05-16 | 20 | 20-20
2031-05-17 | 20 | 20-20
2031-05-18 | 21 | 21-20
2031-05-19 | 21 | 21-20
2031-05-20 | 21 | 21-20
2031-05-21 | 21 | 21-20
2031-05-22 | 21 | 21-20
2031-05-23 | 21 | 21-20
2031-05-24 | 21 | 21-20
2031-05-25 | 22 | 22-20
2031-05-26 | 22 | 22-20
2031-05-27 | 22 | 22-20
2031-05-28 | 22 | 22-20
2031-05-29 | 22 | 22-20
2031-05-30 | 22 | 22-20
2031-05-31 | 22 | 22-20
2031-06-01 | 23 | 23-20
2031-06-02 | 23 | 23-20
2031-06-03 | 23 | 23-20
2031-06-04 | 23 | 23-20
2031-06-05 | 23 | 23-20
2031-06-06 | 23 | 23-20
2031-06-07 | 23 | 23-20
2031-06-08 | 24 | 24-20
2031-06-09 | 24 | 24-20
2031-06-10 | 24 | 24-20
2031-06-11 | 24 | 24-20
2031-06-12 | 24 | 24-20
2031-06-13 | 24 | 24-20
2031-06-14 | 24 | 24-20
2031-06-15 | 25 | 25-20
2031-06-16 | 25 | 25-20
2031-06-17 | 25 | 25-20
2031-06-18 | 25 | 25-20
2031-06-19 | 25 | 25-20
2031-06-20 | 25 | 25-20
2031-06-21 | 25 | 25-20
2031-06-22 | 26 | 26-20
2031-06-23 | 26 | 26-20
2031-06-24 | 26 | 26-20
2031-06-25 | 26 | 26-20
2031-06-26 | 26 | 26-20
2031-06-27 | 26 | 26-20
2031-06-28 | 26 | 26-20
2031-06-29 | 27 | 27-20
2031-06-30 | 27 | 27-20
2031-07-01 | 27 | 27-20
2031-07-02 | 27 | 27-20
2031-07-03 | 27 | 27-20
2031-07-04 | 27 | 27-20
2031-07-05 | 27 | 27-20
2031-07-06 | 28 | 28-20
2031-07-07 | 28 | 28-20
2031-07-08 | 28 | 28-20
2031-07-09 | 28 | 28-20
2031-07-10 | 28 | 28-20
2031-07-11 | 28 | 28-20
2031-07-12 | 28 | 28-20
2031-07-13 | 29 | 29-20
2031-07-14 | 29 | 29-20
2031-07-15 | 29 | 29-20
2031-07-16 | 29 | 29-20
2031-07-17 | 29 | 29-20
2031-07-18 | 29 | 29-20
2031-07-19 | 29 | 29-20
2031-07-20 | 30 | 30-20
2031-07-21 | 30 | 30-20
2031-07-22 | 30 | 30-20
2031-07-23 | 30 | 30-20
2031-07-24 | 30 | 30-20
2031-07-25 | 30 | 30-20
2031-07-26 | 30 | 30-20
2031-07-27 | 31 | 31-20
2031-07-28 | 31 | 31-20
2031-07-29 | 31 | 31-20
2031-07-30 | 31 | 31-20
2031-07-31 | 31 | 31-20
2031-08-01 | 31 | 31-20
2031-08-02 | 31 | 31-20
2031-08-03 | 32 | 32-20
2031-08-04 | 32 | 32-20
2031-08-05 | 32 | 32-20
2031-08-06 | 32 | 32-20
2031-08-07 | 32 | 32-20
2031-08-08 | 32 | 32-20
2031-08-09 | 32 | 32-20
2031-08-10 | 33 | 33-20
2031-08-11 | 33 | 33-20
2031-08-12 | 33 | 33-20
2031-08-13 | 33 | 33-20
2031-08-14 | 33 | 33-20
2031-08-15 | 33 | 33-20
2031-08-16 | 33 | 33-20
2031-08-17 | 34 | 34-20
2031-08-18 | 34 | 34-20
2031-08-19 | 34 | 34-20
2031-08-20 | 34 | 34-20
2031-08-21 | 34 | 34-20
2031-08-22 | 34 | 34-20
2031-08-23 | 34 | 34-20
2031-08-24 | 35 | 35-20
2031-08-25 | 35 | 35-20
2031-08-26 | 35 | 35-20
2031-08-27 | 35 | 35-20
2031-08-28 | 35 | 35-20
2031-08-29 | 35 | 35-20
2031-08-30 | 35 | 35-20
2031-08-31 | 36 | 36-20
2031-09-01 | 36 | 36-20
2031-09-02 | 36 | 36-20
2031-09-03 | 36 | 36-20
2031-09-04 | 36 | 36-20
2031-09-05 | 36 | 36-20
2031-09-06 | 36 | 36-20
2031-09-07 | 37 | 37-20
2031-09-08 | 37 | 37-20
2031-09-09 | 37 | 37-20
2031-09-10 | 37 | 37-20
2031-09-11 | 37 | 37-20
2031-09-12 | 37 | 37-20
2031-09-13 | 37 | 37-20
2031-09-14 | 38 | 38-20
2031-09-15 | 38 | 38-20
2031-09-16 | 38 | 38-20
2031-09-17 | 38 | 38-20
2031-09-18 | 38 | 38-20
2031-09-19 | 38 | 38-20
2031-09-20 | 38 | 38-20
2031-09-21 | 39 | 39-20
2031-09-22 | 39 | 39-20
2031-09-23 | 39 | 39-20
2031-09-24 | 39 | 39-20
2031-09-25 | 39 | 39-20
2031-09-26 | 39 | 39-20
2031-09-27 | 39 | 39-20
2031-09-28 | 40 | 40-20
2031-09-29 | 40 | 40-20
2031-09-30 | 40 | 40-20
2031-10-01 | 40 | 40-20
2031-10-02 | 40 | 40-20
2031-10-03 | 40 | 40-20
2031-10-04 | 40 | 40-20
2031-10-05 | 41 | 41-20
2031-10-06 | 41 | 41-20
2031-10-07 | 41 | 41-20
2031-10-08 | 41 | 41-20
2031-10-09 | 41 | 41-20
2031-10-10 | 41 | 41-20
2031-10-11 | 41 | 41-20
2031-10-12 | 42 | 42-20
2031-10-13 | 42 | 42-20
2031-10-14 | 42 | 42-20
2031-10-15 | 42 | 42-20
2031-10-16 | 42 | 42-20
2031-10-17 | 42 | 42-20
2031-10-18 | 42 | 42-20
2031-10-19 | 43 | 43-20
2031-10-20 | 43 | 43-20
2031-10-21 | 43 | 43-20
2031-10-22 | 43 | 43-20
2031-10-23 | 43 | 43-20
2031-10-24 | 43 | 43-20
2031-10-25 | 43 | 43-20
2031-10-26 | 44 | 44-20
2031-10-27 | 44 | 44-20
2031-10-28 | 44 | 44-20
2031-10-29 | 44 | 44-20
2031-10-30 | 44 | 44-20
2031-10-31 | 44 | 44-20
2031-11-01 | 44 | 44-20
2031-11-02 | 45 | 45-20
2031-11-03 | 45 | 45-20
2031-11-04 | 45 | 45-20
2031-11-05 | 45 | 45-20
2031-11-06 | 45 | 45-20
2031-11-07 | 45 | 45-20
2031-11-08 | 45 | 45-20
2031-11-09 | 46 | 46-20
2031-11-10 | 46 | 46-20
2031-11-11 | 46 | 46-20
2031-11-12 | 46 | 46-20
2031-11-13 | 46 | 46-20
2031-11-14 | 46 | 46-20
2031-11-15 | 46 | 46-20
2031-11-16 | 47 | 47-20
2031-11-17 | 47 | 47-20
2031-11-18 | 47 | 47-20
2031-11-19 | 47 | 47-20
2031-11-20 | 47 | 47-20
2031-11-21 | 47 | 47-20
2031-11-22 | 47 | 47-20
2031-11-23 | 48 | 48-20
2031-11-24 | 48 | 48-20
2031-11-25 | 48 | 48-20
2031-11-26 | 48 | 48-20
2031-11-27 | 48 | 48-20
2031-11-28 | 48 | 48-20
2031-11-29 | 48 | 48-20
2031-11-30 | 49 | 49-20
2031-12-01 | 49 | 49-20
2031-12-02 | 49 | 49-20
2031-12-03 | 49 | 49-20
2031-12-04 | 49 | 49-20
2031-12-05 | 49 | 49-20
2031-12-06 | 49 | 49-20
2031-12-07 | 50 | 50-20
2031-12-08 | 50 | 50-20
2031-12-09 | 50 | 50-20
2031-12-10 | 50 | 50-20
2031-12-11 | 50 | 50-20
2031-12-12 | 50 | 50-20
2031-12-13 | 50 | 50-20
2031-12-14 | 51 | 51-20
2031-12-15 | 51 | 51-20
2031-12-16 | 51 | 51-20
2031-12-17 | 51 | 51-20
2031-12-18 | 51 | 51-20
2031-12-19 | 51 | 51-20
2031-12-20 | 51 | 51-20
2031-12-21 | 52 | 52-20
2031-12-22 | 52 | 52-20
2031-12-23 | 52 | 52-20
2031-12-24 | 52 | 52-20
2031-12-25 | 52 | 52-20
2031-12-26 | 52 | 52-20
2031-12-27 | 52 | 52-20
2031-12-28 | 53 | 53-20
2031-12-29 | 53 | 53-20
2031-12-30 | 53 | 53-20
Formulas:
Week no. = WEEKNUM([Date])