## Weekly Summary
WEEKLY WORK SUMMARY |  |  | Date: | 2026-01-09 | Week No: | 2 | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
Works Completed |  | BEME | Completed Previously | This Week | Project to Date | % Compl.
CONCRETE APRON WORK
• | Preliminaries | 311880000 | 250854911.25 | 0 | 250854911.25 | 80.43%
• | Site Clearance and Earthwork | 1930547160.6 | 951645806.4 | 0 | 951645806.4 | 49.29%
• | Culverts and Drains | 816610932 | 478036260.4 | 0 | 478036260.4 | 58.54%
• | Pavement and Joints | 17457775723.5 | 9136434210 | 267951225 | 9404385435 | 53.87%
• | Pavement Markings | 6973621.875 | 0 | 0 | 0 | 0%
• | Airfield Lighting | 498408386.25 | 52817425 | 0 | 52817425 | 10.6%
• | Underground Fueling System | 408712500 | 0 | 0 | 0 | 0%
• | Fixed Ground Power Supply System | 228034800 | 1750750 | 0 | 1750750 | 0.7678%
SUB-TOTAL |  | 21658943124.225 | 10871539363.05 | 267951225 | 11139490588.05 | 51.43%
Add VAT & State Levies - 7.5% |  | 1624420734.3169 | 815365452.2287 | 20096341.875 | 835461794.1037
Total Works Completed (Incl. VAT) |  | 23283363858.5419 | 11686904815.2787 | 288047566.875 | 11974952382.1537 | 51.43%
Contingency |  | 1082947156.2113 | 543576968.1525 | 13397561.25 | 566332129.4025 | 52.3%
Add VAT & State Levies - 7.5% |  | 81221036.7158 | 40768272.6114 | 1004817.0938 | 42474909.7052
Total Contingency (Incl. VAT) |  | 1164168192.9271 | 584345240.7639 | 14402378.3438 | 608807039.1077 | 52.3%
Total Works Completed (Incl. VAT) |  | 24447532051.469 | 12271250056.0427 | 302449945.2188 | 12583759421.2614 | 1.0373
Costs to Date |  |  | Completed Previously | This Week | Project to Date | % of Total
• | Plant |  | 757492719.12 | 5559764 | 763052483.12 | 12.97%
• | AGO |  | 743352730 | 6131400 | 749484130 | 12.74%
• | Materials |  | 3442751648.9 | 109156865.4688 | 3551908514.3688 | 60.36%
• | Sub Contractors |  | 2820000 | 0 | 2820000 | 0.04792%
• | Local Labour |  | 370345238.5 | 4937420 | 375282658.5 | 6.377%
• | Overheads |  | 105000000 | 1000000 | 106000000 | 1.801%
• | Site Level Expenses |  | 330360489.24 | 5974800 | 336335289.24 | 5.715%
• |  |  | 0 | 0 | 0
• |  |  | 0 | 0 | 0
Total Costs to Date |  |  | 5752122825.76 | 132760249.4688 | 5884883075.2288 | 100%
Net Earnings - Excluding Bill 1 |  |  | 5934781989.5187 | 155287317.4062 | 6090069306.9249
% Net Earnings |  |  | 50.78% | 53.91% | 50.86%
WEEKLY PROGRESS
GENERAL REMARKS

## Contract Summary
CONTRACT SUMMARY |  |  | Date: | 2026-01-09 |  | Week No: | 2 | Instructions
CONTRACT DETAILS
Client: |  | Government of Akwa Ibom State, Ministry of Special Duties
Name of Contract: |  | CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
Short Name: |  | AKWA IBOM AIRPORT APRON
Original Contract Amount: |  | 10621359979.09 | NAIRA
Current Contract Amount: |  | 10621359979.09 | NAIRA | RETC: | No |  |  |  | 10621359979.09 |  | - Check to Detail Sheet
Contract Schedules
• | Date of Contract Award | 2020-11-14 |  | • Works Actually Commenced on Site:
• | Contract Commencement Date: | 2020-12-18
• | Original Contract Duration (Months): | 12 |  | • Duration Already on Site : |  |  | 0
• | Original Contract Completion Date: | 2021-12-18
• | Extension of Time Requested (Months): | 0 |  | • Overdue to Original completion Date: |  |  | -48.7562
• | Extension of Time Granted (Months): | 0
• | Revised Contract Duration (Months) | 12 |  | • Overdue to Revised completion Date: |  |  | -48.7562
• | Revised Completion Date: | 2021-12-18
VALUE OF WORKS TO DATE
CLIENT POSITION (INCL. VAT) - CERTIFICATES
• | Works Vetted & Certified - Payable to Contractor: | 1879930738.36 | 17.7% | [6 empty] | 0 | - Check to Detail Sheet
• | Works submitted and not yet vetted: | 0 | 0% | [6 empty] | 0 | - Check to Detail Sheet
• | Total value of works submitted: | 1879930738.36 | 17.7%
• | Add - Retention Money - Deducted | 203181862.5911
• | Deduct - Retention Money - Released | 0
• | Add -Total Advance Payment Recovered | 0
• | Total Gross Value of Works Completed & Certified: | 2083112600.9511 | 19.61% |  | #VALUE! | #VALUE!
#VALUE!
PW POSITION (INCL. VAT) - WEEKLY PROGRESS REPORTS
• | Add - Bill 1 | 0
• | Permanent Works Completed | 10158750 | 0.09564%
• | Add - Contingencies | 25372651.1115
• | Total Value of Works Done | 35531401.1115 | 0.3345% |  | #VALUE! | #VALUE! |  |  |  | 0 | - Check to Detail Sheet
#VALUE!
Total Work in Progress |  | -2047581199.8396 | - Works Certified is greater than physical works Completed
PAYMENT STATUS
Payments Received to Date |  | Gross | Net Amount |  | % Cont. Value
Advance Payments |  | #VALUE! | #VALUE! |  | #VALUE!
Certficates Paid |  | #VALUE! | #VALUE! |  | #VALUE!
On Account |  | #VALUE! | #VALUE! |  | #VALUE!
Total Payments Received |  | #VALUE! | #VALUE! |  | #VALUE! |  |  |  |  | #VALUE! | - Check to Detail Sheet
Amounts Certified - Not Yet Paid |  | #VALUE!
Advance Payment Guarantee: |  | 1500000000 |  | APG Expiry: | 2018-03-27 | Days Expired: | -2845
Advance Payment Recovered (on submitted Certs): |  | 0 | #VALUE! | Renewal Exp:
Advance Payment yet to be recovered: |  | 1500000000 | #VALUE!
BILL 1
Total Bill 1 Requested by client to date: |  | 49933962 | Total Amount Claimed in Certs: |  |  | 23453874.2667
Total Paid out by PW to date: |  | 43357962 | Total Amount Paid by Client: |  |  | 0
Amount Outstanding from Amounts Requested: |  | 6576000 | Total Amount Outstanding to PW: |  |  | 23453874.2667
Note: All amounts are net of Service Charge: |  |  | Amount rec'd by PW - not paid out: |  |  | -43357962
COST & REVENUE SUMMARY
| Completed Works | BEME | Completed Previously |  | This Week | Project to Date | % Compl.
| CONCRETE APRON WORK | 23283363858.5419 | 11686904815.2787 |  | 288047566.875 | 11974952382.1537 | 51.43%
| Total Contingency (Incl. VAT) | 1164168192.9271 | 584345240.7639 |  | 14402378.3438 | 608807039.1077 | 52.3%
| Tota Completed Works to Date (Incl VAT) | 24447532051.469 | 12271250056.0427 |  | 302449945.2188 | 12583759421.2614 | 51.47%
| Total Costs to Date |  | 5752122825.76 |  | 132760249.4688 | 5884883075.2288
Net Earnings - Excluding Bill 1 |  |  | 6519127230.2827 |  | 169689695.7499 | 6698876346.0326
% Net Earnings |  |  | 53.13% |  | 56.11% | 53.23%
FINANCIAL INFORMATION
|  | Previous Week | This Week |  | Movement
Creditors Balance |  |  |  |  | 0
Bank & Cash Funds Available |  |  |  |  | 0

## BEME & Works Completed Fd
| BEME & Works Completed to date | [11 empty] | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
Updated to the 09 January 2026 - Week No. 2
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
[12 empty] | 0 | 0%
[5 empty] | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 0%
Total Bill No. 1 Carried to Summary | [8 empty] | 0 | 0 | 0 | 0 | 0%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
1 | PRELIMINARIES
1.01 | Allow for mobilization of contractor's equipment and personel to site including demobilization |  | 1 |  |  | 0 | 1 | 69000000 | 69000000 | 50000000 |  | 50000000 | 72.46%
1.02 | Allow for Pavement testing, soil investigation and other laboratory testings |  | 1 |  |  | 0 | 1 | 13800000 | 13800000 | 11500000 |  | 11500000 | 83.33%
1.03 | Allow for Survey and design |  | 1 |  |  | 0 | 1 | 27600000 | 27600000 | 25000000 |  | 25000000 | 90.58%
1.04 | Allow for provision of work safety plan, manual and processing of NCAA Approval including training of project team members on safety requirements according to ICAO standards |  | 1 |  |  | 0 | 1 | 27600000000 | 27600000 | 20000000 |  | 20000000 | 72.46%
1.05 | Allow for environment impact assessment |  | 1 |  |  | 0 | 1 | 6900000 | 6900000 | 2000000 |  | 2000000 | 28.99%
1.06 | Allow for services for the Engineer's Representatives |  | 1 |  |  | 0 | 1 | 20700000 | 20700000 | 17680000 |  | 17680000 | 85.41%
1.07 | Allow for provision of equipment, labour and assistance as may be required by Engineer's Represntative |  | 1 |  |  | 0 | 1 | 20700000 | 20700000 | 18732900.25 |  | 18732900.25 | 90.5%
1.08 | Allow for insurance of work, equipment including security |  | 1 |  |  | 0 | 1 | 11040000 | 11040000 | 8000000 |  | 8000000 | 72.46%
1.09 | Allow for provision of project vehicle, maintenance and running cost |  | 1 |  |  | 0 | 1 | 82800000 | 82800000 | 78435661 |  | 78435661 | 94.73%
1.1 | Allow for removal and relocation of existing services. |  | 1 |  |  | 0 | 1 | 13800000 | 13800000 | 8315000 |  | 8315000 | 60.25%
1.11 | Allow for site meetings and preparations |  | 1 |  |  | 0 | 1 | 13800000 | 13800000 | 8533850 |  | 8533850 | 61.84%
1.12 | Allow for progress photographs |  | 1 |  |  | 0 | 1 | 4140000 | 4140000 | 2657500 |  | 2657500 | 64.19%
Total Bill No. 1 Carried to Summary | [8 empty] | 311880000 | 250854911.25 | 0 | 250854911.25 | 80.43%
2 | SITE CLEARANCE AND EARTHWORKS
2.01 | Clear site on either side of centre line of the proposed Apron up to the limit of construction width of all bushes, shrubs, grasses & trees | Ha | 13 | 12.56 |  | 12.56 | 0.44 | 1800000 | 23400000 | 18978000 | 0 | 18978000 | 81.1%
2.02 | Removal of top soil to a depth not exceeding 500mm | m2 | 105645 | 108673.5 |  | 108673.5 | -3028.5 | 680 | 71838600 | 44636580 | 0 | 44636580 | 62.13%
2.03 | Excavation for cuttings, material other than top soil, rock or artificial hard material, depth not exceeding 6m | m3 | 147223 | 139670.5 |  | 139670.5 | 7552.5 | 7735 | 1138769905 | 602409461.05 | 0 | 602409461.05 | 52.9%
2.04 | Excavate from approved borrow-pits, haul excavated materials any distance, deposit spread in 150mm layers and compact to 100% B. S compaction as filling for embankment and margin, shape formation and trim slopes to required cross section | m3 | 6361 | 8716.33 |  | 8716.33 | -2355.33 | 7650 | 48661650 | 46641735 | 0 | 46641735 | 95.85%
2.05 | Scarify and pulverize existing bituminous surface, shape and compact to 100% B. S compaction as improved sub-base. | m2 | 2400 | 2330 |  | 2330 | 70 | 2983.5 | 7160400 | 4089150 | 0 | 4089150 | 57.11%
2.06 | Dub in grass to slopes of embankment as specified and directed rate to include top-soil 100mm thick. | m2 | 17000 | 0 |  | 0 | 17000 | 3640 | 61880000 | 0 | 0 | 0 | 0%
2.07 | Provide and lay 100mm concrete slope protection to high embankment with BRC wire mesh. | m2 | 8000 | 30.69 |  | 30.69 | 7969.31 | 18870 | 150960000 | 340659 | 0 | 340659 | 0.2257%
2.08 | Clean and desilt culverts, side drains as directed. | m | 1000 | 506 |  | 506 | 494 | 6396 | 6396000 | 2489520 | 0 | 2489520 | 38.92%
2.09 | Excavate, Pulverise, lay and compact to shape, mixture of sharp sand and fill material at subgrade to a depth of 200mm | m2 | 101884 | 99409.25 |  | 99409.25 | 2474.75 | 2553.4 | 260150605.6 | 153439701.35 | 0 | 153439701.35 | 58.98%
2.1 | Provide and install 200mm High Density Pressure pipes for underground drainage | m | 1300 | 1077 |  | 1077 | 223 | 124100 | 161330000 | 78621000 | 0 | 78621000 | 48.73%
2.11 | Provide and install 6 ways 150mm duct line for services, Rate to include Excavation, Blindind Casing and Pipe supply and installation | m |  | 500 |  | 500 | -500 | 118180 |  | 59090000 | 0 | 59090000
Total Bill No. 2 Carried to Summary | [8 empty] | 1930547160.6 | 951645806.4 | 0 | 951645806.4 | 49.29%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
3 | CULVERTS AND DRAINS
3.01 | Excavate for culvert and concrete line drain to any depth including backfilling to 100% B. S compaction and dispose of surplus materials as directed | m3 | 4338.4 | 4036.16 |  | 4036.16 | 302.24 | 7267.5 | 31529322 | 17254584 | 0 | 17254584 | 54.73%
3.02 | Provide, mix and place concrete grade 30 in box culverts as specified inclusive of blinding & formwork. ( reinforcement measured seperately ) | m3 | 85 | 33.25 |  | 33.25 | 51.75 | 242640 | 20624400 | 4033890 | 0 | 4033890 | 19.56%
3.02a | Provide, mix and place concrete grade 40 in box culverts as specified inclusive of blinding & formwork. ( reinforcement measured seperately ) | m3 | 388 | 387.75 |  | 387.75 | 0.25 | 285000 | 110580000 | 54827850 | 0 | 54827850 | 49.58%
3.03 | Provide and fix H.T. Reinforcement in box culverts, headwalls, wingwalls, aprons and toe beams. | Tons | 71 | 69.04 |  | 69.04 | 1.96 | 2400000 | 170400000 | 42114400 | 0 | 42114400 | 24.72%
3.04 | Provide Concrete Lined drains 1.04 m x 0.83 m as specified and directed (Grade 30 concrete), Volume = 0.7525m3/m Rate to include blinding, shuttering and reinforcement | m | 563 | 523 |  | 523 | 40 | 265500 | 149476500 | 69428250 | 0 | 69428250 | 46.45%
3.04a | Provide Concrete Lined drains 1.2 m x 1.0 m as specified and directed (Grade 30 concrete), Volume = 0.525m3/m Rate to include shuttering and reinforcement | m | 524 | 448 |  | 448 | 76 | 176220 | 92339280 | 42116580 | 0 | 42116580 | 45.61%
3.05 | Provide and lay 750mm diameter prcecast concrete pipes for underground storm water drainage Rate to include 150mm sharp sand bedding, concrete surround, shuttering and reinforcement | m | 400 | 298 |  | 298 | 102 | 121500 | 48600000 | 36207000 | 0 | 36207000 | 74.5%
3.06 | Provide and install reinforced concrete chambers 1027mm x 650 mm internal width, 0.23m thick wall and fitted with 75mm x 75mm angle iron for cast iron grattings seating | No | 16 | 16 |  | 16 | 0 | 1445000 | 23120000 | 13600000 | 0 | 13600000 | 58.82%
3.06a | Provide and install reinforced concrete chambers 1027mm x 650 mm internal width, 0.23m thick wall and fitted with 75mm x 75mm angle iron for cast iron grattings seating | No | 9 | 9 |  | 9 | 0 | 1615000 | 14535000 | 8550000 | 0 | 8550000 | 58.82%
3.07 | Provide and install cast iron grattings CHA 002 1027mm x 650mm manufactured by Nigerian Foundries according to BS EN 124 : 2015 international standard and test load 600KN | No | 8 | 8 |  | 8 | 0 | 1275000 | 10200000 | 6000000 | 0 | 6000000 | 58.82%
3.07 | Provide and install cast iron grattings CHA 002 1027mm x 650mm manufactured by Nigerian Foundries according to BS EN 124 : 2015 international standard and test load 600KN | No | 17 | 17 |  | 17 | 0 | 3091790 | 52560430 | 30917900 | 0 | 30917900 | 58.82%
3.08 | Provide and place G30 Concrete in Access Slabs and Cover to Drains | m3 | 200 | 245.09 |  | 245.09 | -45.09 | 242640 | 48528000 | 44769506.4 | 0 | 44769506.4 | 92.26%
3.09 | Provide and fix H.T. Reinforcement in Cover Slab to drain | Tons | 18 | 55.18 |  | 55.18 | -37.18 | 2400000 | 43200000 | 107676300 | 0 | 107676300 | 249.3%
3.1 | Breaking of reinforced concrete manhole on the existing culvert, to be rebuilt to a smaller size of 1027mm x 650mm and reconstruction to be charged under bill nr 3.02 | Nos | 4 | 4 |  | 4 | 0 | 229500 | 918000 | 540000 | 0 | 540000 | 58.82%
Total Bill No. 3 Carried to Summary | [8 empty] | 816610932 | 478036260.4 | 0 | 478036260.4 | 58.54%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
4 | PAVEMENT AND SURFACING
4.01 | Shape and compact formation in cutting to 100% B.S. compaction for the apron, fillets, transition areas and the shoulders | m2 | 90996 | 89993 |  | 89993 | 1003 | 315 | 28663740 | 28347795 | 0 | 28347795 | 98.9%
4.02 | Provide, spread, haul any distance, shape and compact approved crushed rock (wet or dry) in base of Apron, fillets, transition areas and shoulders as specified to a compacted thickness of 250mm of (Haulage inclusive) | m3 | 26345 | 25173.58 |  | 25173.58 | 1171.42 | 61965 | 1632467925 | 941833700.55 | 0 | 941833700.55 | 57.69%
4.03 | Provide and lay insitu dry lean concrete grade 15, 150mm thick in the apron, fillets and transition areas between the apron and taxiway, as may be directed. | m3 | 15487 | 13657.64 |  | 13657.64 | 1829.36 | 130050 | 2014084350 | 1052239545.45 | 0 | 1052239545.45 | 52.24%
4.04 | Provide and install insitu concrete grade 40, 400mm thick in Apron, fillet and transition areas, as may be directed. | m3 | 37912 | 23226.6 | 842 | 24068.6 | 13843.4 | 285000 | 10804920000 | 6103651462.8 | 239970000 | 6343621462.8 | 58.71%
4.04a | Provide and install insitu concrete grade 30, 200mm thick in the Apron shoulders, as may be directed. | m3 | 1687 | 912.43 |  | 912.43 | 774.57 | 242640 | 409333680 | 221392015.2 | 0 | 221392015.2 | 54.09%
4.05 | Provide and install 5.0m by 4.7 m Y8mm Mat, (0.096 ton/mat) bars to be spaced at 200mm centres bothways and installed at 50mm below the finished face of concrete in apron, fillets and transition areas as norminal reinforcement | No | 92.4 | 2366 | 88 | 2454 | -2361.6 | 207000 | 19126800 | 402452220 | 18216000 | 420668220 | 2199%
4.05a | Provide and install 5.0m by 4.45 m Y8mm Mat, (0.091 ton/mat) bars to be spaced at 200mm centres bothways and installed at 50mm below the finished face of concrete in apron, fillets and transition areas as norminal reinforcement | No | 2640 | 0 |  | 0 | 2640 | 196560 | 518918400 | 0 | 0 | 0 | 0%
4.05b | Provide and install 4.20m by 4.80 m Y8mm Mat, (0.0832 ton/mat) bars to be spaced at 200mm centres bothways and installed at 50mm below the finished face of concrete in apron, fillets and transition areas as norminal reinforcement | No | 34.8 | 130 |  | 130 | -95.2 | 179280 | 6238944 | 11901945 | 0 | 11901945 | 190.8%
4.05c | Provide and install 4.7m by 4.7 m Y8mm Mat, (0.089 ton/mat) bars to be spaced at 200mm centres bothways and installed at 50mm below the finished face of concrete in apron, fillets and transition areas as norminal reinforcement | No | 1200 | 0 |  | 0 | 1200 | 192240 | 230688000 | 0 | 0 | 0 | 0%
4.05d | Provide and install 4.5m by 4.8 m Y8mm Mat, (0.088 ton/mat) bars to be spaced at 200mm centres bothways and installed at 50mm below the finished face of concrete in apron, fillets and transition areas as norminal reinforcement | No | 62.4 | 0 |  | 0 | 62.4 | 190080 | 11860992 | 0 | 0 | 0 | 0%
4.05e | Provide and install 3.45m by 4.2m Y8mm Mat, (0.06 ton/mat) bars to be spaced at 200mm centres bothways and installed at 50mm below the finished face of concrete shoulder as norminal reinforcement | No | 240 | 0 |  | 0 | 240 | 129600 | 31104000 | 0 | 0 | 0 | 0%
4.06 | Provide, paint with bitumen and install dowel bars 32mm diameter 600mm length 350mm centers at transverse contraction and longitudinal construction joints . | No | 55200 | 38148 | 851 | 38999 | 16201 | 11475 | 633420000 | 426783600 | 9765225 | 436548825 | 68.92%
4.07 | Provide and fix 20mm thick premolded joint filler board at isolation joints including provision of separation tape or backer rod and seal with self leveling silicone sealant dow coring 890 sl or approved equal | m | 3600 | 755 |  | 755 | 2845 | 81480 | 293328000 | 33295500 | 0 | 33295500 | 11.35%
4.08 | Provide and install 16 mm diameter ribbed bar as 780mm length and 780mm centers at longitudinal joint on the apron shoulders | No | 624 | 0 |  | 0 | 624 | 7020 | 4380480 | 0 | 0 | 0 | 0%
4.09 | Provide longitudinal construction joints depth 400mm on apron and apron transition areas, paint first face of pilot bays with bitumen in compliance with BS 434, instal backer rod and seal joints with self leveling silicone sealant dow coring 890 sl or approved equal | m | 18000 | 2562 |  | 2562 | 15438 | 19584 | 352512000 | 41319936 | 0 | 41319936 | 11.72%
4.09a | Provide longitudinal construction joints depth 200mm on apron and apron shoulder, paint first face of pilot bays with bitumen in compliance with BS 434, instal backer rod and seal joints with self leveling silicone sealant dow coring 890 sl or approved equal | m | 480 | 0 |  | 0 | 480 | 17595 | 8445600 | 0 | 0 | 0 | 0%
4.1 | Provide transverse contraction joints 400mm depth on apron and apron transition areas, saw cut joints, instal backer rod and seal joints with self leveling silicone sealant dow coring 890 sl or approved equal | m | 19200 | 3194.1 |  | 3194.1 | 16005.9 | 22950 | 440640000 | 60368490 | 0 | 60368490 | 13.7%
4.10a | Provide transverse contraction joints 200mm depth on apron shoulder, saw cut joints, instal backer rod and seal joints with self leveling silicone sealant dow coring 890 sl or approved equal | m | 922.5 | 0 |  | 0 | 922.5 | 19125 | 17642812.5 | 0 | 0 | 0 | 0%
Total Bill No. 4 Carried to Summary | [8 empty] | 17457775723.5 | 9136434210 | 267951225 | 9591537435 | 54.94%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
5 | PAVEMENT MARKINGS
5.01 | Taxiway Center Line Markings + lead in | m2 | 375 |  | 0 | 0 | 375 | 8437.5 | 3164062.5 | 0 | 0 | 0 | 0%
5.02 | Taxiway + Apron Edge Markings | m2 | 240 |  |  | 0 | 240 | 8437.5 | 2025000 | 0 | 0 | 0 | 0%
5.03 | Aircraft Stand lead in markings | m2 | 37.5 |  |  | 0 | 37.5 | 8437.5 | 316406.25 | 0 | 0 | 0 | 0%
5.04 | Aircraft Stand Safety markings | m2 | 45 |  |  | 0 | 45 | 9815.625 | 441703.125 | 0 | 0 | 0 | 0%
5.05 | Aircraft Stand Numbering | m2 | 40 |  |  | 0 | 40 | 9956.25 | 398250 | 0 | 0 | 0 | 0%
5.06 | Tranverse Markings Taxiway | m2 | 64 |  |  | 0 | 64 | 9815.625 | 628200 | 0 | 0 | 0 | 0%
Total Bill No. 5 Carried to Summary | [8 empty] | 6973621.875 | 0 | 0 | 0 | 0%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
6 | AIRFIELD LIGHTING SYSTEMS
6.01 | Taxiway Center Line Lights g/y inset | pcs | 50 |  | 0 | 0 | 50 | 1162545 | 58127250 | 0 | 0 | 0 | 0%
6.02 | Taxiway Center Line Lights g/g inset | pcs | 180 |  | 0 | 0 | 180 | 1162545 | 209258100 | 0 | 0 | 0 | 0%
6.03 | Apron Edge Inset Lights | pcs | 20 | 20 |  | 20 | 0 | 475875 | 9517500 | 9517500 | 0 | 9517500 | 100%
6.04 | Taxiway Edge Inset lights | pcs | 20 | 0 |  | 0 | 20 | 475875 | 9517500 | 0 | 0 | 0 | 0%
6.05 | Transformer 20W | pcs | 32 | 0 |  | 0 | 32 | 114562.5 | 3666000 | 0 | 0 | 0 | 0%
6.06 | Transformer 45W | pcs | 230 | 0 |  | 0 | 230 | 119850 | 27565500 | 0 | 0 | 0 | 0%
6.07 | CCR 3KVA | pcs | 1 | 0 |  | 0 | 1 | 13483125 | 13483125 | 0 | 0 | 0 | 0%
6.08 | CCR 4 KVA | pcs | 1 | 0 |  | 0 | 1 | 14158779.375 | 14158779.375 | 0 | 0 | 0 | 0%
6.09 | Secondary Power Cables 2x16mm | m | 17250 | 0 |  | 0 | 17250 | 3348.75 | 57765937.5 | 0 | 0 | 0 | 0%
6.1 | Secondary Power Cables 2x6mm flex | m | 300 | 0 |  | 0 | 300 | 3172.5 | 951750 | 0 | 0 | 0 | 0%
6.11 | Primary Power Cables 5KVA - to switch room | m | 6000 | 0 |  | 0 | 6000 | 3084.375 | 18506250 | 0 | 0 | 0 | 0%
6.12 | Secondary Connector Kits m/f | pcs | 270 | 0 |  | 0 | 270 | 28464.375 | 7685381.25 | 0 | 0 | 0 | 0%
6.13 | Primary Connector Kits KD 500 | pcs | 300 | 0 |  | 0 | 300 | 31775.2313 | 9532569.375 | 0 | 0 | 0 | 0%
6.14 | 8" Bases for inset Lights | pcs | 270 | 240 |  | 240 | 30 | 61423.125 | 16584243.75 | 14741550 | 0 | 14741550 | 88.89%
6.15 | CDS Pouring Concrete for 8" Bases | kg | 1350 | 0 |  | 0 | 1350 | 14981.25 | 20224687.5 | 0 | 0 | 0 | 0%
6.16 | Coring for 8" Bases | pcs | 270 | 0 |  | 0 | 270 | 43768.75 | 11817562.5 | 0 | 0 | 0 | 0%
6.17 | PVC Pipes for Secondary Power Cable ducts | m | 3000 | 3000 |  | 3000 | 0 | 3348.75 | 10046250 | 10046250 | 0 | 10046250 | 100%
6.18 | 4- way cable duct for primary power cables | m | 0 | 0 |  | 0 | 0 | 34368.75 | 0 | 0 | 0 | 0 | 0%
6.19 | 6- way cable duct for primary power cables | m | 800 | 800 |  | 800 |  | 16861.25 | 13489000 | 13489000 | 0 | 13489000
6.2 | Transformer Pits - Type 1 | pcs | 100 | 30 |  | 30 |  | 167437.5 | 16743750 | 5023125 | 0 | 5023125
6.21 | Electrical Service Pits and Manholes - with Cover | pcs | 3 |  | 0 | 0 |  | 8048750 | 24146250 | 0 | 0 | 0
6.22 | Electrical Installation / Project Management | ls | 1 |  | 0 | 0 |  | 27318750 | 27318750 | 0 | 0 | 0
6.23 | Integration of new taxiway in tower remote control system | ls | 0 |  | 0 |  |  | 22031250 | 0 | 0 | 0 | 0
6.24 | Design of the Airfield Lighting System | pcs | 1 |  | 0 |  |  | 29375000 | 29375000 | 0 | 0 | 0
Total Bill No.6 Carried to Summary | [8 empty] | 498408386.25 | 52817425 | 0 | 52817425 | 10.6%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
7 | UNDERGROUND FUELING SYSTEM
7.01 | A1 Fuel Tanks - 100,000 liter each - DIN 6608/2 | pcs | 4 |  |  | 0 | 4 | 56953125 | 227812500 | 0 | 0 | 0 | 0%
7.02 | Fuel Pipes from fuel depot to aircraft stands | m | 3000 |  |  | 0 | 3000 | 8831.25 | 26493750 | 0 | 0 | 0 | 0%
7.03 | Pumps / Pits / Accessories | ls | 1 |  |  | 0 | 1 | 98156250 | 98156250 | 0 | 0 | 0 | 0%
7.04 | Installation / Supervision | ls | 1 |  |  | 0 | 1 | 39375000 | 39375000 | 0 | 0 | 0 | 0%
7.05 | Lightning Protection | ls | 1 |  |  | 0 | 1 | 16875000 | 16875000 | 0 | 0 | 0 | 0%
Total Bill No. 7 Carried to Summary | [8 empty] | 408712500 | 0 | 0 | 0 | 0%
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
8 | FIXED GROUND POWER SUPPLY SYSTEM
8.01 | Power Pits 45kva to 180kva - ground flushing Maxium output power 2,500 Amps / 400 Hz | pcs | 5 |  | 0 | 0 | 5 | 17085960 | 85429800 | 0 | 0 | 0 | 0%
8.02 | Power Inverters | pcs | 5 |  |  | 0 | 5 | 16371000 | 81855000 | 0 | 0 | 0 | 0%
8.03 | PVC Pipes for Power Cables | m | 4000 |  |  | 0 | 4000 | 2812.5 | 11250000 | 0 | 0 | 0 | 0%
8.04 | Power Cables from Main Supply to Pits | m | 2000 |  |  | 0 | 2000 | 14906.25 | 29812500 | 0 | 0 | 0 | 0%
8.05 | Accessories/Grounding System/Installation Materials | pcs | 1 |  |  | 0 | 1 | 8437500 | 8437500 | 0 | 0 | 0 | 0%
8.06 | Installation / Supervision | pcs | 1 |  |  | 0 | 1 | 11250000 | 11250000 | 0 | 0 | 0 | 0%
7.09 | 4 - way ducts for remote parking stands | m |  | 40 |  | 40 |  | 43768.75 |  | 1750750 | 0 | 1750750
Total Bill No. 8 Carried to Summary | [8 empty] | 228034800 | 1750750 | 0 | 1750750 | 0.7678%
Contingency & VOP
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
| Add Contingencies @ 2.5% |  | 1 |  |  | 0 | 1 | 541473578.1056 | 541473578.1056 | 0 | 0 | 0 | 0%
| Add VOP @ 2.5% |  | 1 | 0 |  | 0 | 1 | 541473578.1056 | 541473578.1056 | 0 | 0 | 0 | 0%
Total Contingency & VOP Carried to Summary |  |  | 1 | [5 empty] | 1082947156.2113 | 0 | 0 | 0 | 0%
Summary All
ITEM | DESCRIPTION | UNIT | CONTRACT QTY | PREVIOUS QTY | THIS WEEK QTY | TOTAL QTY COMPLETED | QTY OUTSTANDING | RATE ₦ | CONTRACT AMOUNT | PREVIOUS AMOUNT | THIS WEEK AMOUNT | TOTAL AMOUNT | % OF WORK COMPLETED
1 | Preliminaries | [7 empty] | 311880000 | 250854911.25 | 0 | 250854911.25 | 80.43%
2 | Site Clearance and Earthwork | [7 empty] | 1930547160.6 | 951645806.4 | 0 | 951645806.4 | 49.29%
3 | Culverts and Drains | [7 empty] | 816610932 | 478036260.4 | 0 | 478036260.4 | 58.54%
4 | Pavement and Joints | [7 empty] | 17457775723.5 | 9136434210 | 267951225 | 9591537435 | 54.94%
5 | Pavement Markings | [7 empty] | 6973621.875 | 0 | 0 | 0 | 0%
6 | Airfield Lighting | [7 empty] | 498408386.25 | 52817425 | 0 | 52817425 | 10.6%
7 | Underground Fueling System | [7 empty] | 408712500 | 0 | 0 | 0 | 0%
8 | Fixed Ground Power Supply System | [7 empty] | 228034800 | 1750750 | 0 | 1750750 | 0.7678%
| SUB – TOTAL | [7 empty] | 21658943124.225 | 10871539363.05 | 267951225 | 11326642588.05 | 52.3%
| Contingency & VOP | [7 empty] | 1082947156.2113 | 543576968.1525 | 13397561.25 | 566332129.4025 | 52.3%
| SUB – TOTAL | [7 empty] | 22741890280.4362 | 11415116331.2025 | 281348786.25 | 11892974717.4525 | 52.3%
| Add VAT @ 7.5% | [7 empty] | 1705641771.0327 | 856133724.8402 | 21101158.9688 | 891973103.8089 | 52.3%
| TOTAL | [7 empty] | 24447532051.469 | 12271250056.0427 | 302449945.2188 | 12784947821.2614 | 52.3%

## Certificate Status
CERTIFICATES | [23 empty] | Date: | 2026-01-09 | Week No: | 2 | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
CERTIFICATES
Date Submitted | Cert Number | Gross Value of Works Done | Add Materials on Site | Less Materials on Site | General Bill 1 | Total Value of Work Done | Value of works per Cert | Total Retention Held | Total Net Payment in Respect of works | Add Release of Retention | Add Value of Contingency Used | Less Value of Contingency | Add Fluctuation on Materials | Add Advance Received to date | Total Value of Works Executed | Deduct Advance Recovery | New Total | Less Previously Certified without VAT | Amount Due | Add VAT - 7.5% | Add Stamp Duty | Add WHT -2.5% | Vetting Fee -0.5% | Total Amount Due | Less Recovery of Advance | Less advance Payment Refund per Cert | Total Amount of Payment Certified | Status
| 1 | 292876150 | 210000000 |  | 126536150.25 | 629412300.25 | 629412300.25 | 14643807.5 | 614768492.75 |  | 135841394.5 |  |  |  | 750609887.25 |  |  |  |  | 56295741.5437 |  | 18765247.1813 | 3753049.4363 | 829423925.4112 |  | 0 | 829423925.4112 | Vetted
| 2 | 1304376463.35 | 210000000 | 210000000 | 167136150.25 | 1471512613.6 |  | 65218823.1675 | 1406293790.4325 |  | 135841394.5 | 135841395 |  | 2655339994.77 | 4061633784.7025 | 531067998.95 | 3530565785.7525 | 2343183884.11 | 1187381901.6425 | 89053642.6232 |  |  |  | 1276435544.2657 |  | 0 | 1276435544.2657 | Vetted
| 3 | 2386215683 | 210000000 | 210000000 | 170136150.25 | 2556351833.25 |  | 119310784.15 | 2437041049.1 |  | 0 | 0 | 167387715.06 | 2655339994.77 | 5259768758.93 | 663834998.69 | 4595933760.24 | 3530565786.25 | 1065367973.99 | 79902598.0492 |  |  |  | 1145270572.0392 |  | 0 | 1145270572.0392 | Vetted
| 4 | 3240181777 | 0 |  | 218332411.25 |  |  | 162009088.85 | 3078172688.15 |  | 79288600 | 0 | 167387715.06 | 2655339994.77 | 6198521409.23 | 663834998.69 | 5534686410.54 | 4595933760.24 | 938752650.3 | 70406448.7725 |  |  |  | 1009159099.0725 |  | 0 | 1009159099.0725 | Vetted
| 5 | 3970958517.2 | 0 |  | 250854911.25 |  |  | 198547925.86 | 3772410591.34 |  | 79288600 | 0 | 294597606.16 | 2655339994.77 | 7052491703.52 | 796601998.431 | 6255889705.089 | 5534686410.73 | 721203294.359 | 54090247.0769 |  |  |  | 775293541.4359 |  | 0 | 775293541.4359 | Vetted
| 6 | 4190024367.2 | 0 |  | 250854911.25 |  |  | 209501218.36 | 3980523148.84 |  | 79288600 | 0 | 294597606.16 | 2655339994.77 | 7260604261.02 | 796601998.431 | 6464002262.589 | 6255889705.09 | 208112557.499 | 15608441.8124 |  |  |  | 223720999.3114 |  | 0 | 223720999.3114 | Vetted
| 7 | 5561644626 | 500000000 |  | 250854911.25 |  |  | 278082231.3 | 5283562394.7 |  | 175549464 | 0 | 294597606.16 | 2381470847.33 | 8886035223.44 | 833514796.56 | 8052520426.88 | 6464002262.59 | 1588518164.29 | 119138862.3217 |  |  |  | 1707657026.6117 |  | 0 | 1707657026.6117 | Vetted
| 8 | 6987125226 | 500000000 |  | 250854911.25 |  | 0 | 349356261.3 | 6637768964.7 |  | 175549464 | 0 | 294597606.16 | 2381470847.33 | 10240241793.44 | 952588338.932 | 9287653454.508 | 8052520427.03 | 1235133027.478 | 92634977.0608 |  |  |  | 1327768004.5388 |  | 0 | 1327768004.5388 | Vetted
| 9 | 8387605119.65 | 500000000 | 150000000 | 250854911.25 | 600854911.25 |  | 419380255.98 | 7968224863.67 |  | 175549464 | 0 | 294597606.16 | 2381470847.33 | 11420697692.41 | 1309808966.03 | 10110888726.38 | 9287653454.67 | 823235271.71 | 61742645.3782 |  |  |  | 884977917.0882 |  | 0 | 884977917.0882 | Vetted
| 10 | 9974307555.412 | 500000000 | 250000000 | 250854911.25 | 500854911.25 |  | 498715377.7706 | 9475592177.6414 |  | 175549464 | 175549464 | 294597606.16 | 2381470847.33 | 12652515542.3814 | 1428882508.398 | 11223633033.9834 | 10110888726.38 | 1112744307.6034 | 83455823.0703 |  |  |  | 1196200130.2736 |  | 0 | 1196200130.2736 | Vetted
| 11 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Totals | [7 empty] | 498715377.7706 |  |  |  |  | 294597606.16 |  | 12652515542.3814 | 1428882508.398 |  |  |  | 722329427.7091 | 0 | 18765247.1813 | 3753049.4363 | 10375906760.0485 |  | 0 | 10375906760.0485
[8 empty] | Add VAT - 7.5% | 0 |  | 0 | [13 empty] | Add VAT - 7.5% | 0
[8 empty] | Total Retention Deducted - Inc. VAT: | 0 | Ret. Rel. - Inc VAT: | 0 | [13 empty] | Total Advance Recovered - Including VAT: | 0
SUMMARY CERT STATUS
Vetted |  | 46295315484.812 | 2630000000 | [11 empty] | 73783120056.3239 | [11 empty] | 10375906760.0485
Not Vetted |  | 0 | 0 | [11 empty] | 0 | [11 empty] | 0
|  | 46295315484.812 | 2630000000 | [11 empty] | 73783120056.3239 | [11 empty] | 10375906760.0485

## Payments Recieved
PAYMENTS RECEIVED |  |  |  |  | Date: | 2026-01-09 |  | Week No: | 2 | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
PAYMENT DETAILS |  |  |  | DEDUCTIONS | [6 empty] | Deductions %
Date | Voucher Number | Payment Type | Gross Amount (Including VAT) | WHT | VAT | Vetting Fee | Stamp Duty | Other | Net Amount Payable |  | VAT % | WHT % | State Levy % | Stamp Duty % | Other %
| Advance | Advance | 1593203996.86 | 39830099.9215 | 119490299.7645 | 7966019.9843 | 15932039.9686 | 0 | 1409985537.2211 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2022-08-15 | Cert No 1 | Cert | 829423925.4112 | 20735598.1353 | 62206794.4058 | 4147119.6271 | 8294239.2541 | 0 | 734040173.989 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
| 2nd Advance | Advance | 1062135997.91 | 26553399.9478 | 79660199.8432 | 5310679.9896 | 10621359.9791 | 0 | 939990358.1503 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2023-01-26 | Cert No 2 | Cert | 1000000000 | 25000000 | 75000000 | 5000000 | 10000000 | 0 | 885000000 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2023-04-20 | Cert No 2 | Cert | 276435644 | 6910891.1 | 20732673.3 | 1382178.22 | 2764356.44 | 0 | 244645544.94 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2023-05-18 | Cert No3 | Cert | 500000000 | 12500000 | 37500000 | 2500000 | 5000000 | 0 | 442500000 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2023-09-18 | Cert No3 | Cert | 500000000 | 12500000 | 37500000 | 2500000 | 5000000 | 0 | 442500000 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2023-11-18 | Cert No3/4 | Cert | 500000000 | 12500000 | 37500000 | 2500000 | 5000000 |  | 442500000 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2024-05-07 | Cert No4 | Cert | 500000000 | 12500000 | 37500000 | 2500000 | 5000000 |  | 442500000 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2024-05-10 | Cert No4 | Cert | 57500000 | 1437500 | 4312500 | 287500 | 575000 |  | 50887500 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2024-09-17 | Cert 4/5 | Cert | 869288404 | 21732210.1 | 65196630.3 | 4346442.02 | 8692884.04 |  | 769320237.54 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2024-11-08 | Cert 5/6 | Cert | 130711596 | 3267789.9 | 9803369.7 | 653557.98 | 1307115.96 |  | 115679762.46 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2024-12-09 | Cert 6/7 | Cert | 1576945431.13 | 39423635.7783 | 118270907.3348 | 7884727.1557 | 15769454.3113 |  | 1395596706.5501 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2025-04-08 | Cert 7/8 | Cert | 1327768004.7 | 33194200.1175 | 99582600.3525 | 6638840.0235 | 13277680.047 |  | 1175074684.1595 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2025-07-02 | Cert 9 | Cert | 884977917.26 | 22124447.9315 | 66373343.7945 | 4424889.5863 | 8849779.1726 |  | 783205456.7751 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
2025-07-02 | Cert 10 | Cert | 1196200130.2736 | 29905003.2568 | 89715009.7705 | 5981000.6514 | 11962001.3027 |  | 1058637115.2921 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
[9 empty] | 0 |  | 0% | 0% | 0% | 0% | 0%
Total All: |  |  | 12804591047.5449 | 320114776.1886 | 960344328.5659 | 64022955.2377 | 128045910.4754 | 0 | 11332063077.0772 |  | 2.5% | 7.5% | 0.5% | 1% | 0%
11211387050.6849

## Cost Report
COST REPORT |  |  |  |  | Date: | 2026-01-09 | Week No: | 2 | Instructions
CONSTRUCTION OF BUA LAFIAGI BYPASS ROAD | CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
S/No | Description | Cost Category | Unit | Quantity This Week | Rate N | Amount Previous Week | Amount This Week | Amount Up to Date |  | Source Legend | Source Detail
PLANT DEPARTMENT | [9 empty] | PLANT DEPARTMENT | All information should be obtained from the plant department reports.
1 | Diesel | AGO | Litres | 5574 | 1100 | 743352730 | 6131400 | 749484130 |  | MATERIALS | All information is auto populated from the materials reconcilaition sheet, other than the Amount Previous Week
2 | Diesel (P.W. External Issues) | AGO | Litres |  | 1100 | 0 | 0 | 0 |  | OTHER MATERIALS | Other material not captured on the materails & civils report that may be used on site.
2 | Plant Internal | Plant | N/a |  |  | 603063936 | 4349600 | 607413536 |  | OTHER SITE COSTS | All information is auto populated from the headcount and subcontractors report, other than the Amount Previous Week
3 | Hired Plant/Equipment/Vehicle | Plant | N/a |  |  | 20519699.72 | 174000 | 20693699.72 |  | SITE LEVEL ACCOUNTS | All information is obtained from the site accountant weekly financial report.
4 | Petrol | Plant | Litres | 309.6 | 840 | 23751599.4 | 260064 | 24011663.4 |  | OVERHEADS | Information is provided by the PM other than Bill 1 information which is provided by the Accountant in completing the Bill 1 schedule.
5 | Stores Cost | Plant | Various |  |  |  | 0
6 | Engine Oil | Plant | Litres | 111 | 4500 | 48791240 | 499500 | 49290740
7 | Gear oil | Plant | Litres |  | 4500 | 3286944 | 0 | 3286944
8 | ATF 220 Oil | Plant | Litres | 0 | 0 | 0 | 0 | 0
9 | DTE 26 Oil | Plant | Litres | 0 | 0 | 0 | 0 | 0
10 | Rarius 427 Comp. Oil | Plant | Litres | 0 | 0 | 0 | 0 | 0
11 | Almo 529 | Plant | Litres | 0 | 0 | 0 | 0 | 0
12 | Grease | Plant | Kg |  | 6200 | 1277200 | 0 | 1277200
13 | 6440; Tyres | Plant | Each |  |  | 0 |  | 0
MATERIALS | [5 empty] | 0 | 0 | 0
1 | Cement | Materials | Bags | 0 | 9525 | 188791150 | 0 | 188791150
2 | Cement (Bulk) | Materials | Tonnes | 358 | 200500 | 1590597565 | 71779000 | 1662376565
3 | Reinforcement Y 8 (Local) | Materials | Tonnes | 8.448 | 960000 | 187551368 | 8110080 | 195661448
4 | Reinforcement Y 12 (Local) | Materials | Tonnes | 0 | 1100000 | 45897100 | 0 | 45897100
5 | Reinforcement Y 16 (Local) | Materials | Tonnes | 0 | 400150 | 5017881 | 0 | 5017881
6 | Reinforcement Y 12 (Foreign) | Materials | Tonnes | 0 | 295000 | 0 | 0 | 0
7 | Reinforcement Y 20 (Foreign) | Materials | Tonnes | 0 | 295000 | 0 | 0 | 0
8 | Reinforcement Y 24 (Foreign) | Materials | Tonnes | 0 | 550000 | 23171500 | 0 | 23171500
9 | Reinforcement Y 32 (Foreign) | Materials | Tonnes | 3.226 | 2080000 | 151122743.4 | 6710125.4688 | 157832868.8688
10 | Binding Wire | Materials | Rolls | 0 | 6500 | 0 | 0 | 0
11 | Sharp Sand | Materials | Tonnes | 0 | 3250 | 0 | 0 | 0
12 | Blocks 9" | Materials | Each | 0 | 500 | 0 | 0 | 0
13 | Geotextile | Materials | M2 | 0 | 1200000 | 0 | 0 | 0
14 | UPVC Pipe(300mm) | Materials | Each |  | 12500 | 19375000 | 0 | 19375000
15 | UPVC Pipe(100mm) | Materials | Each |  | 6500 | 1950000 | 0 | 1950000
16 | Interlocking Paving Stone | Materials | m2 | 0 | 3600 | 0 | 0 | 0
17 | Precast Units | Materials | LM | 0 | 25000 | 0 | 0 | 0
18 | 0 | Materials | 0 | 0 | 0 | 0 | 0 | 0
19 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
QUARRY MATERIALS |  |  | 0
21 | Sand | Materials | Tonnes | 547.3 | 11000 | 182101130 | 6020300 | 188121430
22 | 3/4" Aggregates | Materials | Tonnes | 926.2 | 16300 | 640006282.5 | 15097060 | 655103342.5
23 | 1/2" Aggregates | Materials | Tonnes | 0 | 4000 | 0 | 0 | 0
24 | 3/8" Aggregates | Materials | Tonnes | 0 | 4000 | 0 | 0 | 0
25 | Stone Base | Materials | Tonnes | 0 | 13300 | 331973446 | 0 | 331973446
26 | MC1 | Materials | Tonne | 0 | 225000 | 0 | 0 | 0
27 | Tack Coat (MC1) | Materials | Litres | 0 | 260 | 0 | 0 | 0
28 | S125 | Materials | Litres | 0 | 280 | 0 | 0 | 0
29 | Wearing Course Asphalt | Materials | Tonnes | 0 | 33500 | 0 | 0 | 0
30 | Binder Course Asphalt | Materials | Tonnes | 0 | 30000 | 0 | 0 | 0
31 | Hardcore | Materials | Tonne | 0 | 2500 | 0 | 0 | 0
32 | Borrow Pit | Materials | m2 | 0 | 300 | 0 | 0 | 0
33 | 0 | Materials | 0 | 0 | 0 | 0 | 0 | 0
34 | 0 | Materials | 0 | 0 | 0 | 0 | 0 | 0
35 | 0 | Materials | 0 | 0 | 0 | 0 | 0 | 0
36 | 0 | Materials | 0 | 0 | 0 | 0 | 0 | 0
OTHER MATERIALS
1 | 6400; Timber | Materials |  |  |  | 406700 |  | 406700
2 | Diesel (P.W. External Issues) | AGO | Litre |  | 238 | 0 | 0 | 0
3 | [5 empty] | 0 |  | 0
OTHER SITE COSTS | [5 empty] | 0 |  | 0
1 | Sub-Contractor's Expenses | Sub Contractors |  |  |  | 2820000 |  | 2820000
2 | Labour | Local Labour | No. | 59 | 40000 | 256300000 | 2360000 | 258660000
[6 empty] | 0 |  | 0
SITE LEVEL ACCOUNTS | [5 empty] | 0 |  | 0
1 | 6320; Spare Parts | Plant |  |  |  | 46471780 | 276600 | 46748380
2 | 1041; Building & Site Development | Site Level Expenses |  |  |  | 1956600 |  | 1956600
2 | 6021; P.W. Tippers (Haulage-fees) | Materials |  |  |  | 55971700 | 1388300 | 57360000
| 6100; Compensation (Borrow Pit) | Site Level Expenses |  |  |  | 1936000 |  | 1936000
3 | 6230; Security Expenses | Site Level Expenses |  |  |  | 2060000 |  | 2060000
4 | 6300; Steel Plate/Reinforcement | Plant |  |  |  | 10330320 |  | 10330320
5 | 6350; Materials Civil | Materials |  |  |  | 18818083 | 52000 | 18870083
6 | 6420; Tools and Consumables | Site Level Expenses |  |  |  | 116028384 | 4624400 | 120652784
7 | 6220; External Labour | Local Labour |  |  |  | 114045238.5 | 2577420 | 116622658.5
8 | 6540; Sundry Expenses | Site Level Expenses |  |  |  | 65097460 | 299300 | 65396760
9 | 7020; Miscellaneous Running Costs/Expenses | Site Level Expenses |  |  |  | 67347650 |  | 67347650
10 | 7220; Expatriate Living Costs | Site Level Expenses |  |  |  | 35510698 | 514000 | 36024698
11 | 7340; Office Equipment Maintenance | Site Level Expenses |  |  |  | 273600 |  | 273600
12 | 7350; I.T. Costs - Internet | Site Level Expenses |  |  |  | 597000 | 20000 | 617000
13 | 7351; I.T. Costs - Software / Maint. Costs | Site Level Expenses |  |  |  | 60000 |  | 60000
14 | 7320; Medical Expenses | Site Level Expenses |  |  |  | 6018190 | 150000 | 6168190
15 | 7460; Rent | Site Level Expenses |  |  |  | 3703500 |  | 3703500
16 | 7500; Stationary | Site Level Expenses |  |  |  | 1410840 | 79600 | 1490440
17 | 7560; Telephone | Site Level Expenses |  |  |  | 3594250 | 59500 | 3653750
18 | 7620; Travelling | Site Level Expenses |  |  |  | 18006811 | 228000 | 18234811
19 | 7622: Outstation | Site Level Expenses |  |  |  | 5054700 |  | 5054700
20 | 8020; Bank Charges | Site Level Expenses |  |  |  | 1704806.24 |  | 1704806.24
21
22 | [5 empty] | 0 |  | 0
OVERHEADS | [5 empty] | 0 |  | 0
1 | Administration | Overheads | No. | 1 | 1000000 | 105000000 | 1000000 | 106000000
| Total |  |  |  |  | 5752122825.76 | 132760249.4688 | 5884883075.2288

## Diesel Consumption
WEEKLY DIESEL CONSUMPTION | [5 empty] | Date: | 2026-01-09 | [5 empty] | Week No: | 2 |  |  | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
|  | Opening Stock: | 0 |  |  |  | Received this Week: | 0 |  |  | Used This Week: | 6731 |  |  | Closing Stock: | -6731
Fleet No. | Description | Plant Category | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Total Fuel Taken | Standard Ltrs/Hour | Standard Usage | Variance | Variance Value | Usage Value | Remarks
AC163 | STATIC COMPRESSOR |  |  |  | 15 | 10 | 10 | 10 | 15 | 60 |  | 0 | 60 | 66000 | 66000
AC175 | MOBILE COMPRESSOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
BB4 | BAR BENDER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
CMB 4 | Cement Blower |  | 20 | 20 |  |  |  | 20 |  | 60 |  | 0 | 60 | 66000 | 66000
BP6 | DRY BATCHER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
BP 9 | DRY BATCHER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
BS20 | BENCH SAW | [8 empty] | 0 |  | 0 | 0 | 0 | 0
C 13 | COMPACTOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
D67 | DOZER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
D70 | DOZER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
D69 | DOZER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
E 82 | EXCAVATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
E 87 | EXCAVATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
E 88 | EXCAVATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
EG 95 | GENERATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
EG172 | GENERATOR |  | 50 |  | 100 | 100 | 100 | 80 | 120 | 550 |  | 0 | 550 | 605000 | 605000
EG177 | GENERATOR |  | 60 | 30 | 70 | 70 | 70 | 70 | 70 | 440 |  | 0 | 440 | 484000 | 484000
EG207 | GENERATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
EG261 | GENERATOR |  |  |  | 200 |  |  |  |  | 200 |  | 0 | 200 | 220000 | 220000
EG236 | GENERATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
EG278 | GENERATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
EG286 | GENERATOR | [8 empty] | 0 |  | 0 | 0 | 0 | 0
FBT 3 | FLAT BED TRAILER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
FBT18 | FLAT BED TRAILER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
G 38 | GRADER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
G 54 | GRADER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
G 56 | GRADER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
IC35 | IRON CUTTER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
IC36 | IRON CUTTER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
L 48 | PAY LOADER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
L 63 | PAY LOADER |  | 30 |  | 80 | 80 | 90 | 60 | 100 | 440 |  | 0 | 440 | 484000 | 484000
L 68 | PAY LOADER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
LT 6 | LUXURIOUS TRAILER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
MCM 10 | MOBILE CAR MIXER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
MCM 14 | MOBILE CAR MIXER |  |  |  | 0 |  |  |  |  | 0
MCM 18 | MOBILE CAR MIXER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P351 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P352 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P403 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P405 | PICKUP | [6 empty] | 155 |  | 155 |  | 0 | 155 | 170500 | 170500
P431 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P415 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P369 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
P440 | PICKUP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
RT19 | GROVE CRANE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T228 | WATER TANKER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T229 | WATER TANKER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T265 | workers transport | [10 empty] | 0 | 0 | 0 | 0
T273 | WATER TANKER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T344>LL12 | TRACTOR UNIT | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T551 | TRACTOR UNIT | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T388 | WATER TANKER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T343 | TIPPER |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0
T481 | TRUCK MIXER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T438 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T476 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T482 | MERCEDES MAN CARRIER |  | 60 |  | 30 | 30 | 30 | 30 | 30 | 210 |  | 0 | 210 | 231000 | 231000
T481 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T490 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T500 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T504 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T507 | Water Tanker |  | 20 |  | 20 | 20 | 20 | 20 | 20 | 120 |  | 0 | 120 | 132000 | 132000
T514 | HIAB |  |  |  | 20 | 20 |  | 20 | 20 | 80 |  | 0 | 80 | 88000 | 88000
T531 | TRUCK MIXER |  |  |  | 40 | 40 | 50 | 25 | 65 | 220 |  | 0 | 220 | 242000 | 242000
T566 | TIPPER |  |  | 135 | 135 |  | 135 | 135 | 135 | 675 |  | 0 | 675 | 742500 | 742500
T577 | TRUCK MIXER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T579 | TRUCK MIXER |  |  |  | 40 | 40 | 50 | 25 | 65 | 220 |  | 0 | 220 | 242000 | 242000
T580 | TRUCK MIXER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T557 | TIPPER |  |  | 135 | 135 |  | 135 | 135 | 135 | 675 |  | 0 | 675 | 742500 | 742500
T558 | TIPPER |  |  | 135 |  | 135 | 135 | 135 | 135 | 675 |  | 0 | 675 | 742500 | 742500
T560 | TIPPER |  |  | 135 | 135 |  | 135 | 135 | 135 | 675 |  | 0 | 675 | 742500 | 742500
T561 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T565 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T571 | FUEL BOWSER |  |  | 15 |  | 15 |  | 15 |  | 45 |  | 0 | 45 | 49500 | 49500
T589 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T603 | TIPPER |  |  | 125 | 125 |  | 125 | 125 |  | 500 |  | 0 | 500 | 550000 | 550000
T604 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
T609 | TIPPER |  |  | 125 | 125 |  | 125 | 125 |  | 500 |  | 0 | 500 | 550000 | 550000
T610 | TIPPER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
TT43 | TIPPING TRAILER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
TT44 | TIPPING TRAILER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
TT52 | TIPPING TRAILER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE180 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE191 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE251 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE261 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE272 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE273 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VPE286 | VIBRATING PORKER ENGINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VR 81 | VIBRATING ROLLER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VR125 | VIBRATING ROLLER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VR122 | VIBRATING ROLLER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VR131 | VIBRATING ROLLER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
VR132 | VIBRATING ROLLER | [10 empty] | 0 | 0 | 0 | 0
VR143 | VIBRATING ROLLER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
W 74 | WELDER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
W109 | WELDER | [8 empty] | 0 |  | 0 | 0 | 0 | 0
W150 | WELDER |  | 10 |  | 10 | 10 | 10 | 10 | 10 | 60 |  | 0 | 60 | 66000 | 66000
WM 96 | WASHING MACHINE | [8 empty] | 0 |  | 0 | 0 | 0 | 0
WP109 | WATER PUMP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
Wm96 | WATER PUMP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
WP260 | WATER PUMP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
WP432 | WATER PUMP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
WP419 | 2'' WATER PUMP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
WP | WATER PUMP | [8 empty] | 0 |  | 0 | 0 | 0 | 0
| TOTAL All : |  | 250 | 855 | 1280 | 570 | 1220 | 1330 | 1055 | 5574 | 0 | 0 | 6560 | 7216000 | 7216000
OTHER DIESEL USAGE | [12 empty] | 0 |  | 0
AE 926 HER | [6 empty] | 50 |  |  | 50 |  |  | 50 |  | 55000
T615 | [9 empty] | 0 |  |  | 0 |  | 0
T369 | [9 empty] | 0 |  |  | 0 |  | 0
CIVIL | [9 empty] | 0 |  |  | 0 |  | 0
T 345 | [9 empty] | 0 |  |  | 0 |  | 0
MECHANICS |  |  |  |  | 2 | 6 |  |  |  | 8 |  |  | 8 |  | 8800
BUA | [9 empty] | 0 |  |  | 0 |  | 0
BUA | [9 empty] | 0 |  |  | 0 |  | 0
DRUM | [9 empty] | 0 |  |  | 0 |  | 0
BUA |  | ` | [7 empty] | 0 |  |  | 0 |  | 0
P369 | PICKUP ABUJA | [8 empty] | 0 |  |  | 0 |  | 0
HIRED CRANE | [9 empty] | 0 |  |  | 0 |  | 0
T600 | [9 empty] | 0 |  |  | 0 |  | 0
LAB/PRECAST |  |  | 13 | 30 | 10 | 25 | 5 | 30 |  | 113 |  |  | 113 |  | 124300
T600/LL16 | LOW LOADER TO ABUJA | [8 empty] | 0 |  |  | 0 |  | 0
[10 empty] | 0 |  |  | 0 |  | 0
[10 empty] | 0 |  |  | 0 |  | 0
[10 empty] | 0 |  |  | 0 |  | 0
Sub Total Other Used |  |  | 13 | 30 | 12 | 31 | 55 | 30 | 0 | 171 |  | 0 | 171 |  | 188100
0
Total All Diesel Used |  |  | 263 | 885 | 1292 | 601 | 1275 | 1360 | 1055 | 6731 |  | 0 | 6731 | 7216000 | 7404100
[5 empty] | % Allocated to the project |  |  |  |  | 100%
[5 empty] | Total Internal Plant cost Allocated |  |  |  |  | 6731

## Plant Return
WEEKLY PLANT RETURNS | [6 empty] | Date: | 2026-01-09 | Week No: | 2 | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
Fleet No. | Description | Plant Category | Hours Worked | S/B Hours | B/D Hours | Rate (N) | Plant Cost | Transfered From | Current Location | Remarks
AC163 | STATIC COMPRESSOR |  | 0 | 0 | 63 | 300 | 0
AC175 | STATIC COMPRESSOR |  | 50 | 10 | 3 | 300 | 15000
AC186 | STATIC COMPRESSOR |  | 50 | 13 | 0 | 300 | 15000
AC165 | MOBILE COMPRESSOR |  | 0 | 0 | 0 | 2500 | 0
AC180 | MOBILE COMPRESSOR |  | 0 | 0 | 0 | 2500 | 0
ASC11 | MOBILE COMPRESSOR |  | 50 | 13 | 0 | 2500 | 125000
BB4 | BAR BENDER |  | 0 | 63 | 0 | 500 | 0
BP4 | ELBA BATCHING PLANT |  | 50 | 13 | 0 | 500 | 25000
CMB 4 | Cement Blower |  | 30 | 25 | 8 | 500 | 15000
BP6 | DRY BATCHER |  | 0 | 0 | 0 | 500 | 0
BP 9 | DRY BATCHER |  | 0 | 63 | 0 | 6100 | 0
BS20 | BENCH SAW |  | 0 | 63 | 0 | 300 | 0
C 13 | COMPACTOR |  | 0 | 0 | 0 | 12300 | 0
D67 | DOZER |  | 0 | 0 | 0 | 16900 | 0
D70 | DOZER |  | 0 | 0 | 0 | 8200 | 0
D69 | DOZER |  | 0 | 0 | 63 | 8200 | 0
E 82 | EXCAVATOR |  | 0 | 0 | 0 | 5600 | 0
E 87 | EXCAVATOR |  | 0 | 0 | 0 | 8200 | 0
E 88 | EXCAVATOR |  | 0 | 0 | 0 | 8200 | 0
EG 95 | GENERATOR |  | 0 | 0 | 0 | 8200 | 0
EG172 | GENERATOR |  | 58 | 5 | 0 | 8200 | 475600
EG177 | GENERATOR |  | 63 | 8 | 0 | 1300 | 81900
EG184 | GENERATOR |  | 0 | 63 | 0 | 1300 | 0
EG207 | GENERATOR |  | 0 | 0 | 0 | 1300 | 0
EG261 | GENERATOR |  | 50 | 13 | 0 | 1300 | 65000
EG236 | GENERATOR |  | 0 | 63 | 0 | 1300 | 0
EG278 | GENERATOR |  | 0 | 0 | 0 | 1000 | 0
EG286 | GENERATOR |  | 50 | 13 | 0 | 1000 | 50000
FBT 3 | FLAT BED TRAILER |  | 0 | 0 | 0 | 1600 | 0
FBT18 | FLAT BED TRAILER |  | 0 | 0 | 0 | 1600 | 0
G 38 | GRADER |  | 0 | 0 | 0 | 9100 | 0
G 54 | GRADER |  | 0 | 0 | 0 | 9100 | 0
G 56 | GRADER |  | 0 | 0 | 0 | 9100 | 0
IC35 | IRON CUTTER |  | 40 | 43 | 0 | 500 | 20000
IC36 | IRON CUTTER |  | 0 | 63 | 0 | 500 | 0
L 48 | PAY LOADER |  | 0 | 63 | 0 | 8200 | 0
L 63 | PAY LOADER |  | 55 | 5 | 0 | 8200 | 451000
L 68 | PAY LOADER |  | 0 | 0 | 63 | 8200 | 0
LT 6 | LUXURIOUS TRAILER |  | 58 | 13 | 0 | 1600 | 92800
MCM 10 | MOBILE CAR MIXER |  | 0 | 0 | 0 | 2000 | 0
MCM 14 | MOBILE CAR MIXER |  | 0 | 0 | 0 | 2000 | 0
MCM 18 | MOBILE CAR MIXER |  | 0 | 0 | 0 | 2000 | 0
P351 | PICKUP |  | 0 | 0 | 0 | 1000 | 0
P352 | PICKUP |  | 0 | 0 | 0 | 1000 | 0
P403 | PICKUP |  | 0 | 0 | 0 | 1000 | 0
P405 | PICKUP |  | 63 | 0 | 13 | 1000 | 63000
P431 | PICKUP |  | 10 | 5 | 0 | 1000 | 10000
P415 | PICKUP |  | 0 | 0 | 0 | 1000 | 0
P369 | PICKUP |  | 0 | 0 | 0 | 1000 | 0
P438 | PICKUP |  | 33 | 63 | 0 | 1000 | 33000
P440 | PICKUP |  | 0 | 63 | 0 | 1000 | 0
RT19 | GROVE CRANE |  | 0 | 0 | 0 | 13200 | 0
T228 | WATER TANKER |  | 0 | 0 | 0 | 4100 | 0
T229 | WATER TANKER |  | 0 | 0 | 0 | 4100 | 0
T265 | workers transport |  | 0 | 0 | 63 | 4900 | 0
T273 | WATER TANKER |  | 0 | 0 | 0 | 4100 | 0
T344>LL12 | TRACTOR UNIT |  | 0 | 0 | 0 | 5800 | 0
T364 | TRACTOR UNIT |  | 0 | 0 | 0 | 4900 | 0
T388 | WATER TANKER |  | 0 | 0 | 0 | 4100 | 0
T343 | TIPPER |  | 0 | 0 | 0 | 5800 | 0
T481 | TRUCK MIXER |  | 0 | 0 | 0 | 5800 | 0
T438 | TIPPER |  | 0 | 0 | 0 | 5800 | 0
T476 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T482 | MERCEDES MAN CARRIER |  | 58 | 13 | 0 | 5800 | 336400
T464 | TIPPER |  | 0 | 0 | 0 | 5800 | 0
T490 | TIPPER |  | 0 | 0 | 0 | 5800 | 0
T500 | TIPPER |  | 0 | 0 | 0 | 5800 | 0
T504 | TIPPER |  | 0 | 0 | 0 | 4900 | 0
T507 | Water Tanker |  | 50 | 13 | 0 | 4900 | 245000
T514 | HIAB |  | 50 | 0 | 13 | 4900 | 245000
T531 | TRUCK MIXER |  | 50 | 13 | 0 | 5800 | 290000
T532 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T566 | TIPPER |  | 50 | 10 | 3 | 4900 | 245000
T538 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T551 | TIPPER |  | 10 | 0 | 63 | 5800 | 58000
T553 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T544 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T557 | TIPPER |  | 50 | 63 | 0 | 5800 | 290000
T558 | TIPPER |  | 50 | 63 | 0 | 5800 | 290000
T560 | TIPPER |  | 50 | 63 | 0 | 5800 | 290000
T561 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T569 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T571 | FUEL BOWSER |  | 50 | 23 | 0 | 5800 | 290000
T577 | TRUCK MIXER |  | 0 | 0 | 0 | 5800 | 0
T579 | TRUCK MIXER |  | 50 | 13 | 0 | 5800 | 290000
T580 | TRUCK MIXER |  | 0 | 63 | 0 | 5800 | 0
T565 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T588 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T589 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T592 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T603 | TIPPER |  | 40 | 10 | 13 | 5800 | 232000
T604 | TIPPER |  | 0 | 0 | 0 | 5800 | 0
T605 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
T609 | TIPPER |  | 20 | 43 | 0 | 5800 | 116000
T610 | TIPPER |  | 0 | 0 | 63 | 5800 | 0
TT41 | TIPPING TRAILER |  | 0 | 0 | 63 | 1600 | 0
TT43 | TIPPING TRAILER |  | 0 | 0 | 63 | 1600 | 0
TT44 | TIPPING TRAILER |  | 50 | 13 | 0 | 1600 | 80000
TT52 | TIPPING TRAILER |  | 50 | 13 | 0 | 1600 | 80000
TT46 | TIPPING TRAILER |  | 10 | 63 | 0 | 1600 | 16000
TT47 | TIPPING TRAILER |  | 50 | 13 | 0 | 1600 | 80000
TT49 | TIPPING TRAILER |  | 50 | 13 | 0 | 1600 | 80000
VPE180 | VIBRATING PORKER ENGINE |  | 0 | 0 | 0 | 100 | 0
VPE191 | VIBRATING PORKER ENGINE |  | 0 | 0 | 0 | 100 | 0
VPE251 | VIBRATING PORKER ENGINE |  | 50 | 13 | 0 | 100 | 5000
VPE261 | VIBRATING PORKER ENGINE |  | 0 | 0 | 0 | 100 | 0
VPE272 | VIBRATING PORKER ENGINE |  | 0 | 63 | 0 | 100 | 0
VPE273 | VIBRATING PORKER ENGINE |  | 0 | 0 | 63 | 100 | 0
VPE286 | VIBRATING PORKER ENGINE |  | 0 | 0 | 63 | 100 | 0
VR 81 | VIBRATING ROLLER |  | 0 | 0 | 0 | 2900 | 0
VR 95 | VIBRATING ROLLER |  | 0 | 0 | 0 |  | 0
VR122 | VIBRATING ROLLER |  | 0 | 63 | 0 | 2900 | 0
VR125 | VIBRATING ROLLER |  | 0 | 63 | 0 | 2900 | 0
VR131 | VIBRATING ROLLER |  | 0 | 63 | 0 | 2900 | 0
VR132 | VIBRATING ROLLER |  | 0 | 0 | 0 | 2900 | 0
VR143 | VIBRATING ROLLER |  | 0 | 0 | 0 | 2900 | 0
W 74 | WELDER |  | 0 | 0 | 0 | 500 | 0
W109 | WELDER |  | 0 | 0 | 63 | 500 | 0
W150 | WELDER |  | 50 | 10 | 13 | 500 | 25000
WM 96 | WASHING MACHINE |  | 0 | 63 | 0 | 500 | 0
WP109 | WATER PUMP |  | 0 | 0 | 63 | 500 | 0
Wm96 | WATER PUMP |  | 0 | 63 | 0 | 100 | 0
WP260 | WATER PUMP |  | 0 | 63 | 0 | 100 | 0
WP432 | WATER PUMP |  | 0 | 63 | 0 | 100 | 0
WP419 | 2'' WATER PUMP |  | 50 | 13 | 0 | 100 | 5000
WP | WATER PUMP
| TOTAL All : |  | 1648 | 1791 | 1578 |  | 5125700
|  |  |  | % Allocated to the project |  |  | 100%
|  |  |  | Total Internal Plant cost Allocated |  |  | 5125700
Internal Plant Cost Adjusted for
|  |  |  | Engine Oil |  |  | 499500
|  |  |  | Gear oil |  |  | 0
|  |  |  | ATF 220 Oil |  |  | 0
|  |  |  | DTE 26 Oil |  |  | 0
|  |  |  | Rarius 427 Comp. Oil |  |  | 0
|  |  |  | Almo 529 |  |  | 0
|  |  |  | Grease |  |  | 0
|  |  |  | 6440; Tyres |  |  | 0
|  |  |  | 6320; Spare Parts |  |  | 276600
|  |  |  | Tota All Adjusted |  |  | 776100
|  |  |  | Net Plant Cost Cost Report |  |  | 4349600

## Hired Vehicles
HIRED VEHICLES |  |  |  |  | Date: | 2026-01-09 | Week No: | 2 | Instructions
#REF! | CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
S/No. | Reg. No | Description | Section | Owners | Days Worked | Rate (N) | Amount (N) | Remarks
1 |  | Car | Engineer | engr. | 0 | 4000 | 0
|  | Bus | Engineer | engr. | 6 | 15000 | 90000
2 |  |  | Acct | accountant |  | 2000 | 0
3 |  | Bus | Workers |  | 6 | 10000 | 60000
4 |  | Crane | Plant | Frekon Engineering | 0 | 1000000 | 0
5 |  |  | Mechanic | Mechanic |  | 2000 | 0
6 |  | Pick Up | Mechanic | Mechanic | 6 | 4000 | 24000
7 |  |  | Mechanic | Mechanic |  | 2500 | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0
|  |  |  | Total |  |  | 174000

## Labour Strength
LABOUR STRENGTH |  | Date: | 2026-01-09 | Week No: | 2 | Instructions
CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
S/No | Department | Manning This Week | Manning Previous Week | Movement | Comment
1 | Senior Staff | 1 | 1 | 0
2 | Civil Engineers | 2 | 2 | 0
3 | Civil - Surveyors | 3 | 3 | 0
4 | Administration | 5 | 5 | 0
5 | Lab | 4 | 4 | 0
6 | Domestics | 2 | 2 | 0
7 | Security | 2 | 2 | 0
8 | Plant | 15 | 15
9 | Transport | 12 | 12 | 0
10 | Earthworks | 2 | 2 | 0
11 | Quarry | 0 | 0 | 0
12 | Asphalt |  |  | 0
13 | Marini | 0 | 0 | 0
14 | Civil | 11 | 11 | 0
15 | Electrical |  |  | 0
| Total Head Count | 59 | 59 | 0
CASUAL STAFF
S/No | Department | Manning This Week | Manning Previous Week | Movement | Comment
1 | Transport & Earthworks |  |  | 0
2 | Engr, Survey, civil store & Batching plant |  |  | 0
3 | Security |  |  | 0
4 | Lab |  |  | 0
5 | Quarry | 0 | 0 | 0
6 | Civil | 0 | 0 | 0
| Total Casual Head Count | 0 |  | 0

## Subcontractors
SUBCONTRACTORS | [12 empty] | Date: | 2026-01-09 | Week No: | 2 | Instructions
#REF! | CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
Item | Subcontractor | Description | Location | Unit | Agreed Rate | Assigned Qty | Previous Qty | Qty Executed for Week | Total Qty Executed To-Date | Balance to Complete | Subcontract Value This Week | Previous Value Completed | Value Completed this week | Total Value Completed | Value to Completion | Remarks
1 | PASCHAL GENERAL CONTRACTOR | CASTING, PACKING & LOADING OF 9'' SANDCRETE BLOCKS |  |  | 130 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | CUT, BEND & FIX REBAR |  |  | 15000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | REINFORCED CONCRETE CASTING |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | FORMWORK |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | BLOCK LAYING |  |  | 700 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | BLOCK LAYING & INFILL |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | ROOFING |  |  | 300 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | DAY WORKS (3 No LABOUR) BY 90 DAY) |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAY WORK (FOREMAN) |  |  | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DOOR FIXING |  |  | 1700 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WINDOW FIXING |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| JIDE MOMOH | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FORMWORK IN ST1 to ST8 PAD FOUNDATION BLINDING |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 15 CONCRETE BLINDING IN ST1 to ST8 PAD FOUNDATION |  |  | 250 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLOCK LAYING & INFILL WITH CONCRETE IN ST1 to ST8 PAD FOUNDATION BASE |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FORMWORK IN GROUND BOTTOM BEAM FOUNDATION BLINDING |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 15 CONCRETE BLINDING IN GROUND BOTTOM BEAM FOUNDATION |  |  | 250 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLOCK LAYING & INFILL WITH CONCRETE IN GROUND BOTTOM BEAM FOUNDATION |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FORMWORK IN DRUM DRYER FOUNDATION BLINDING |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 15 CONCRETE BLINDING IN DRUM DRYER FOUNDATION |  |  | 250 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLOCK LAYING & INFILL WITH CONCRETE IN DRUM DRYER FOUNDATION |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLOCK LAYING & INFILL WITH CONCRETE IN PERIMETER WALL |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PLASTERING IN PERIMETER WALL |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OFFLOADING OF CEMENT (STORE TO SILO) |  |  | 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BATCHING OF CEMENT |  |  | 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAYWORK - 2 LABOUR BY 30 DAYS |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAYWORK - FOREMAN |  |  | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ABBAS GLOBAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 15 CONCRETE CASTING IN BATCHING PLANT |  |  | 500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE CASTING IN BATCHING PLANT |  |  | 1000 |  | 117.7 |  | 117.7 | -117.7 | 0 | 117700 | 0 | 117700 | -117700
|  | CONCRETE BISCUIT |  |  | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FORMWORK |  |  | 750 |  | 363 |  | 363 | -363 | 0 | 272250 | 0 | 272250 | -272250
|  | BLOCK LAYING |  |  | 700 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLOCK LAYING & INFILL |  |  | 1000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ROOFING |  |  | 300 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAY WORKS (3 No WORKMEN) BY 4 DAY) |  |  | 2500 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
|  | DAY WORK (FOREMAN) |  |  | 3000 |  | 39 |  | 39 |  |  | 117000 | 0 | 117000 | -117000
|  | LAYING OF PRECAST UNIT |  |  | 1700 |  | 135 |  | 135 | -135 | 0 | 229500 | 0 | 229500 | -229500
|  | PRECAST DRAIN UNIT |  |  | 400 |  | 360 |  | 360 | -360 | 0 | 144000 | 0 | 144000 | -144000
|  | PRECAST SLAB |  |  | 750 |  | 148 |  | 148 | -148 | 0 | 111000 | 0 | 111000 | -111000
|  | PLACE PRECAST SLAB |  |  | 600 |  | 36 |  | 36 | -36 | 0 | 21600 | 0 | 21600 | -21600
|  | REIN. CONCRETE IN PLANT WORKSHOP & STAFF CANTEEN |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PLASTERING IN PLANT WORKSHOP & STAFF CANTEEN |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Godwin | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CUT & BEND REBAR |  |  | 11000 |  | 9.59 |  | 9.59 | -9.59 | 0 | 105490 | 0 | 105490 | -105490
|  | FIX REBAR |  |  | 8000 |  | 12.32 |  | 12.32 | -12.32 | 0 | 98560 | 0 | 98560 | -98560
|  | CUT & BEND REBAR IN ST2 (7) PAD FOUNDATION |  |  | 9000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FIX REBAR IN ST2 (7) PAD FOUNDATION |  |  | 6000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CUT & BEND REBAR IN ST3 (11) PAD FOUNDATION |  |  | 9000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FIX REBAR IN ST3 (11) PAD FOUNDATION |  |  | 6000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CUT & BEND REBAR IN ST4 (2) PAD FOUNDATION |  |  | 9000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FIX REBAR IN ST4 (2) PAD FOUNDATION |  |  | 6000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CUT & BEND REBAR IN ST5 (5) PAD FOUNDATION |  |  | 9000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FIX REBAR IN ST5 (5) PAD FOUNDATION |  |  | 6000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CUT & BEND REBAR IN ST6 (2) PAD FOUNDATION |  |  | 9000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FIX REBAR IN ST6 (2) PAD FOUNDATION |  |  | 6000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DOMNIC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST1 (5) PAD FOUNDATION BASE & COLUMN |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST2 (7) PAD FOUNDATION BASE & COLUMN |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST3 (11) PAD FOUNDATION BASE & COLUMN |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST4 (2) PAD FOUNDATION BASE |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST5 (5) PAD FOUNDATION BASE |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST6 (2) PAD FOUNDATION BASE |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST7 (6) PAD FOUNDATION BASE |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN ST8 (4) PAD FOUNDATION BASE |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN GROUND BOTTOM BEAM |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN GROUND TOP BEAM |  |  | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GRADE 30 REINFORCED CONCRETE IN DRYER BASE |  |  | 1001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fixing of anchor bolts, Engineering details refers (Fix Only) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST1 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST2 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST3 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST4 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST5 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST6 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST7 and columns |  |  | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FORMWORK | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST1 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST2 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST3 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST4 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST5 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST6 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST7 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pad Foundation ST8 and columns |  |  | 750 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAY WORKS (4 No LABOUR) BY 90 DAY) |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAY WORK (FOREMAN) |  |  | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | -1181.61 | 0 | 1217100 | 0 | 1217100 | -1217100

## Precast
MATERIAL STOCKS | [9 empty] | Date: | 2026-01-09 |  | Week No: | 2
#REF!
S/No | DESCRIPTION | SIZE | UOM | BEME Amount | Previous Cast Amount | Cast This week | Total Cast to Date | Balance Required | Used Previous | Used This week | Total Used | Balance Available | Closing Stock | Variance | REMARKS
1 | Drain Unit |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
5 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
6 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
7 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
8 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
9 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
10 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
11 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
12 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
13 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 |  | 0
0

## Materials & Civils
MATERIAL STOCKS | [9 empty] | Date: | 2026-01-09 |  | Week No: | 2 | 2
#REF! | CONSTRUCTION OF PROPOSED CONCRETE APRON FOR THE NEW TERMINAL BUILDING AT VICTOR ATTAH INTERNATIONAL AIRPORT UYO, AKWA IBOM STATE
USED IN THE WEEK
# | Description | Unit | Current Price | Opening Stock | Received / Purchased | Closing Stock | Available for Use | On Site Works | Precast | Mobilsation | Other Uses | Total Used | Variance Qty | Variance Value | Comments
1 | Cement (Bags) | Bags | 4750 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
2 | Cement (Bulk) | Tonne | 75000 | 12.925 | 352.06 |  | 123.16 | 358 |  |  |  | 0 | 123.16 | 9237000
3 | Rebar (8mm) Local | Tonne | 425000 | 0 |  |  | 0 | 8.448 |  |  |  | 8.448 | -8.448 | -3590400
4 | Rebar (12mm) Local | Tonne | 425000 | [8 empty] | 0 | 0 | 0
5 | Rebar (16mm) Local | Tonne | 425000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
6 | Rebar (12mm) Imported | Tonne | 475000 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0
7 | Rebar (16mm) Imported | Tonne | 475000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
8 | Rebar (20mm) Imported | Tonne | 475000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
9 | Rebar (25mm) Imported | Tonne | 475000 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
10 | Rebar (32mm) Imported | Tonne | 475000 | 0 |  |  | 0 | 3.226 |  |  |  | 3.226 | -3.226 | -1532360.3835
11 | Binding Wire | Roll | 4500 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
12 | Sharp Sand | Tonne | 5500 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
13 | Blocks 9" | Each | 300 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
14 | Blocks 6" | Each | 300 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
15 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
16 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
17 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
18 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
19 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
20 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
QUARRY MATERIALS |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
25 | 3/4" | Tonne | 16300 |  |  |  |  | 926.2 |  |  |  | 926.2 | -926.2 | -15097060
26 | 1/2'' | Tonne | 16300 | 0 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0
27 | sand | Tonne | 11000 |  |  | 0 |  | 547.3 |  |  |  | 547.3 | -547.3 | -6020300
28 | 3/8" | Tonne | 10800 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
29 | Stonebase | Tonne | 13300 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
30 | Hardcore | Tonne | 6500 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
31 | MC1 Priming | Tonne | 341200 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
32 | S125 Surface Dressing | Tonne | 346200 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
33 | RSII Colas Tack Coat | Tonne | 329200 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
34 | Crack Relief Layer CRL | Tonne | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
35 | Asphalt Binder Course | Tonne | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
36 | Asphalt Wearing Course | Tonne | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
37 | 60/70 Bitumen | Tonne | 384709 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
38 | Kerosine | Litres |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
39 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
40 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
| Total All: | [5 empty] | 0 |  |  |  |  | 1485.174 | -1362.014 | -17003120.3835

## Bill 1 Summary
BILL 1 SCHEDULE | [5 empty] | Date: | 2026-01-09 | Week No: | 2 | Instructions
#REF! | [7 empty] | Service Charge: | 2.5% |  | CLAIMED IN CERTS (Inclusive of Service Charge)
Item NO. | DESCRIPTION | REQUESTED BY MINISTRY | PAID to date by P.W. | OUTSTANDING By P.W. | CLAIMED IN CERTS (Net of 2.50%) | PAID BY CLIENT (Net of 2.50%) | PAYMENT RECIVED, OUTSTANDING BY PW | Ministry Letter Reference | Request Date |  | Cert 1 | Cert 2 | Cert 3 | Cert 4 | Cert 5 | Cert 6 | Cert 7 | Cert 8 | Cert 9 | Cert 10 | Cert 11 | Cert 12 | Cert 13 | Cert 14 | Cert 15 | Cert 16 | Cert 17 | Cert 18 | Cert 19 | Cert 20 | Cert 21 | Cert 22 | Cert 23 | Total
[10 empty] | Cert Status: |  | Not Paid | [21 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 10250000 | [21 empty] | 10250000
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 10506250 | [21 empty] | 10506250
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 3703453.125 | [21 empty] | 3703453.125
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 10506250 | [21 empty] | 10506250
|  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 8942484.375 | [21 empty] | 8942484.375
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  |  | 0 | 0 | 0 | 0 | 0 | [26 empty] | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 43908437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43908437.5

## Bill 1 Payments
DETAIL SCHEDULE BILL 1 PAYMENTS |  |  | Date: | 2026-01-09 | Week No: | Instructions
#REF!
Date | Payee | Bank | Chq No. / Ref | Bill 1 Item | Amount |  | Wk- YR
|  |  |  | Total All Bill 1 Items to date: | 0
0

## Lists
Date | Week no. | Wk & Year | UOM | Description | Cost Categories | Plant Categories | Cost Assumption | Rate | Basis | Contract Bank Details |  | CONCRETE CLASS: | 15N/mm² |  |  | 20N/mm² |  |  | 25N/mm² |  |  | 30N/mm² |  |  | 40N/mm² |  |  | P.W. NIGERIA LIMITED |  |  |  | NOVEMBER 2015
2020-01-01 | 1 | 1-20 | m3 | Cubic Metre | Plant | Lowloader | Employer Pension Rate | 10% | % | Bank Name: | First Bank of Nigeria Limited | Bill of Quanties for Design Mix of concrete | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume | Batch by wt. |  | Batch by volume
2020-01-02 | 1 | 1-20 | m2 | Metre Squared | AGO | Tippers | Administration Cost | 1400000 | Per Expat | Account Name: | P.W. NIGERIA LIMITED | [16 empty] | STANDARD APPROVED RATES FOR SUBCONTRACTS
2020-01-03 | 1 | 1-20 | Lm | Linear Metre | Materials | Tipping Trailers | VAT (Value Added Tax) | 7.5% | % | Account Number: | 2001507098 |  | kg/m³ | % | m³ | kg/m³ | % | m³ | kg/m³ | % | m³ | kg/m³ | % | m³ | kg/m³ | % | m³
2020-01-04 | 1 | 1-20 | Litre | Litres | Sub Contractors | Trucks | Local Staff Cost | 40000 | Per Week | Sort Code: | 001084060 | 20mm (3/4 Inch) | 785 | 33.05% | 0.586 | 733 | 30.54% | 0.547 | 726 | 30.26% | 0.542 |  | 0% |  |  | 0% |  | S/NO | DESCRIPTION |  | UNIT | APROVED | COMMENTS
2020-01-05 | 2 | 2-20 | Tonne | Metric Tonnes | Local Labour | Flat Bed Trailers | Bill 1 Service Charge | 2.5% |  |  |  | 10mm (1/2 Inch) | 391 | 16.46% | 0.294 | 383 | 15.96% | 0.288 | 365 | 15.21% | 0.275 |  | 0% |  |  | 0% | [5 empty] | RATE (N)
2020-01-06 | 2 | 2-20 | Roll | Roll | Overheads | Lorries | Withholding Tax | 7.5% |  |  |  | 12.5mm (3/8 Inch) |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | EXCAVATION
2020-01-07 | 2 | 2-20 | Each | Per Unit | Site Level Expenses | Tractor Units | [5 empty] | River Sand | 717 | 30.19% | 0.496 | 748 | 31.17% | 0.517 | 753 | 31.39% | 0.52 |  | 0% |  |  | 0% |  |  |  | General excavation including any necessary trimming, levelling & compaction of excavated ground surface | m3 | 500 | This is for excavation works carried out solely by the subcontractor. It is not applicable to their attendance on PW excavator.
2020-01-08 | 2 | 2-20 | Bags | Per Bag | Bill 1 | Water Tanker Trucks | [5 empty] | Quarry Dust |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  |  | Backfilling & compaction | m3 | 200
2020-01-09 | 2 | 2-20 | Kgs | Per Kg |  | Water Tanker - Trailers | [5 empty] | Free water Ltrs | 175 | 7.368% | 0.175 | 174 | 7.25% | 0.174 | 180 | 7.503% | 0.18 |  | 0% |  |  | 0% |  |  |  | Ground Preparation | m2 |  | Trimming, levelling & compaction of previously excavated ground
2020-01-10 | 2 | 2-20 | Loads | Per Load |  | Fuel Bowsers | [5 empty] | Complast Admixture |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
2020-01-11 | 2 | 2-20 | Litres | Litres |  | Lube Tankers | [5 empty] | Cement | 307 | 12.93% | 0.249 | 362 | 15.08% | 0.294 | 375 | 15.63% | 0.304 |  | 0% |  |  | 0% |  |  | BLOCK DRAINS, 450MM INTERNAL WIDTH - NO REINFORCEMENT - ALL INCLUSIVE RATE
2020-01-12 | 3 | 3-20 | N/a |  |  | Service Trucks | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  |  | 1 course full block drain | Lm |  | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-13 | 3 | 3-20 |  |  |  | Luxurious | [6 empty] | 2375 | 100% | 1.8 | 2400 | 100% | 1.82 | 2399 | 100% | 1.821 | 0 | 0% | 0 | 0 | 0% | 0 |  |  | 2 courses full block drain | Lm |  | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-14 | 3 | 3-20 |  |  |  | Hiab
2020-01-15 | 3 | 3-20 |  |  |  | Bulk Cement Trucks | [22 empty] | BLOCK DRAINS, 450MM INTERNAL WIDTH - REINFORCED - ALL INCLUSIVE RATE
2020-01-16 | 3 | 3-20 |  |  |  | Ambulance | [23 empty] | 1 course full block drain | Lm | 10100 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-17 | 3 | 3-20 |  |  |  | 4 X 4 Suvs | [23 empty] | 2 courses full block drain | Lm | 12300 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-18 | 3 | 3-20 |  |  |  | Pickups | [23 empty] | 3 courses full block drain | Lm | 13500 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-19 | 4 | 4-20 |  |  |  | Saloon Cars | [23 empty] | 4 courses full block drain | Lm | 15700 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-20 | 4 | 4-20 |  |  |  | Motor Bikes
2020-01-21 | 4 | 4-20 |  |  |  | Dump Truck - Rigid (Cat) | [22 empty] | PRE-CAST DRAINS - LABOUR ONLY
2020-01-22 | 4 | 4-20 |  |  |  | Dump Truck - Articulated (Volvo) | [23 empty] | Casting drain units | Lm | 500 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard other than loading onto flatbed
2020-01-23 | 4 | 4-20 |  |  |  | Scrapers | [23 empty] | Loading & offloading drain units | Lm | 50 | This is specifically for loading the precast units onto the flatbed in the precast yard and offloading at site. This should be paid for once only. All other handling of precast units in the precast yard is covered under casting drain units
2020-01-24 | 4 | 4-20 |  |  |  | Dozers | [23 empty] | Laying & stitching both sides of L drain | Lm | 1550 | Rate includes laying both roadside and kerbside units. Fixing rebar and placing concrete in gap to be stitched.
2020-01-25 | 4 | 4-20 |  |  |  | Excavators | [23 empty] | Casting cover slabs | no. | 600 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard
2020-01-26 | 5 | 5-20 |  |  |  | Hammer Breakers | [23 empty] | Lay cover slabs, including loading & unloading | no. | 500
2020-01-27 | 5 | 5-20 |  |  |  | Payloaders
2020-01-28 | 5 | 5-20 |  |  |  | Graders | [22 empty] | CULVERTS - ALL INCLUSIVE RATE
2020-01-29 | 5 | 5-20 |  |  |  | Dumpers | [23 empty] | 450mm Diam. Culverts | Lm |  | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-30 | 5 | 5-20 |  |  |  | Piling Rigs | [23 empty] | 600mm Diam. Culverts | Lm | 26500 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-01-31 | 5 | 5-20 |  |  |  | Compactors | [23 empty] | 750mm Diam. Culverts | Lm | 32000 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-02-01 | 5 | 5-20 |  |  |  | Rollers | [23 empty] | 900mm Diam. Culverts | Lm | 42000 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-02-02 | 6 | 6-20 |  |  |  | Vibrating Plates | [23 empty] | Supply & place concrete in culvert headwalls, wingwalls and aprons, including formwork | m3 | 31500 | Rates include, excavation, backfilling & compaction, supply of all labour and materials
2020-02-03 | 6 | 6-20 |  |  |  | Cranes - Mobile
2020-02-04 | 6 | 6-20 |  |  |  | Cranes - Tower | [22 empty] | DEMOLITION OF EXISTING DRAINS / CULVERTS
2020-02-05 | 6 | 6-20 |  |  |  | Slip Form Paver (Gomaco) | [23 empty] | Drainage demolition - Labour only | Lm | 300
2020-02-06 | 6 | 6-20 |  |  |  | Concrete Batching Plants (Static Type) - Wetmix | [23 empty] | Culvert Demolition, including removal | m3 | 1800
2020-02-07 | 6 | 6-20 |  |  |  | Concrete Batching Plants (Static Type) - Drymix | [23 empty] | Concrete demolition - Labour only | m3 | 2750
2020-02-08 | 6 | 6-20 |  |  |  | Concrete Mixer - Mobile (Carmixer Type) | [23 empty] | Drainage Cleaning | Lm | 200
2020-02-09 | 7 | 7-20 |  |  |  | Concrete Mixer - Small (Winget Type) | [23 empty] | Culvert Cleaning | Lm | 200
2020-02-10 | 7 | 7-20 |  |  |  | Concrete Pump - Truck Mounted
2020-02-11 | 7 | 7-20 |  |  |  | Concrete Pump - Static | [22 empty] | CONCRETE BATCHING
2020-02-12 | 7 | 7-20 |  |  |  | Concrete Mixer Trucks | [23 empty] | Batching of Grade 25 Concrete | m3 | 400 | Rate is for all labour required to operate static batching plant in precast yard provided by PW, includes handling of all raw materials and loading concrete onto mixer trucks. PW to provide all materials, payloader for loading aggregates, water tanker if necessary for water.
2020-02-13 | 7 | 7-20 |  |  |  | Vibrating Poker Engines | [22 empty] | CONCRETE SUPPLY & PLACEMENT
2020-02-14 | 7 | 7-20 |  |  |  | Concrete Power Float Machines | [23 empty] | Supply and place Gr. 25 concrete to headwalls, wingwalls and aprons etc into existing formwork | m3 |  | Rate is for supplying and mixing all concrete materials, placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-15 | 7 | 7-20 |  |  |  | Asphalt Batching Plant | [23 empty] | Supply and place Gr. 25 concrete to headwalls, wingwalls and aprons etc including supplying & installing formwork | m3 |  | Rate is for supplying and mixing all concrete materials, placing, vibrating and finishing concrete including supplying and fixing all formwork
2020-02-16 | 8 | 8-20 |  |  |  | Heating Plant
2020-02-17 | 8 | 8-20 |  |  |  | Tar Sprayer - Truck | [22 empty] | CONCRETE PLACEMENT - LABOUR ONLY
2020-02-18 | 8 | 8-20 |  |  |  | Tar Sprayer - Trailer Only | [23 empty] | Blinding Concrete | m3 | 125
2020-02-19 | 8 | 8-20 |  |  |  | Planing Machines | [23 empty] | Mass concrete | m3 | 250
2020-02-20 | 8 | 8-20 |  |  |  | Asphalt Finishers (Pavers) | [23 empty] | Reinforced concrete placement - General | m3 | 300 | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-21 | 8 | 8-20 |  |  |  | Asphalt Cutting Machines | [23 empty] | Reinforced concrete placement - Bridge Substructure - In-situ (not including filling of piles) | m3 |  | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-22 | 8 | 8-20 |  |  |  | Farm Tractors | [23 empty] | Reinforced concrete placement - Bridge Superstructure - In-situ | m3 |  | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-23 | 9 | 9-20 |  |  |  | Road Brushes | [23 empty] | Pre-casting of main longitudinal bridge beams | m3 |  | Rate is for placing, vibrating and finishing concrete within formwork containing reinforcement bars already fixed in place
2020-02-24 | 9 | 9-20 |  |  |  | Chiiping Spreaders | [23 empty] | Pre-casting of bridge deck slabs (2.1m X 1.4 X 0.07) | no. | 750 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard
2020-02-25 | 9 | 9-20 |  |  |  | Generators | [23 empty] | Pre-casting of bridge parapet walls (2.1m long) | no. | 2100 | Rate includes, assembling / striking / cleaning moulds, fixing rebar, pouring concrete, curing concrete, removing units from moulds, stacking precast units and all other handling required in precast yard
2020-02-26 | 9 | 9-20 |  |  |  | Compressors | [23 empty] | Placement and fixing of pre-cast bridge parapet walls (2.1m long) | no. |  | Rate includes loading the precast units onto the flatbed in the precast yard and offloading at site. This should be paid for once only. All other handling of precast units in the precast yard is covered under casting pre-cast units
2020-02-27 | 9 | 9-20 |  |  |  | Cement Blowers
2020-02-28 | 9 | 9-20 |  |  |  | Fuel Meter Pumps | [22 empty] | REINFORCEMENT - LABOUR ONLY
2020-02-29 | 9 | 9-20 |  |  |  | Weigh Bridges | [23 empty] | Cutting & bending | ton | 9000
2020-03-01 | 10 | 10-20 |  |  |  | Telehandlers / Fork Lifts | [23 empty] | Fixing | ton | 6000
2020-03-02 | 10 | 10-20 |  |  |  | Block Moulding Machines
2020-03-03 | 10 | 10-20 |  |  |  | Welding Sets | [22 empty] | REINFORCEMENT - ALL INCLUSIVE RATE
2020-03-04 | 10 | 10-20 |  |  |  | Bending & Cutting Machines | [23 empty] | Supply, cutting, bending & fixing | ton |  | Rate includes, material supply (including tie wire), delivery, cutting, bending and fixing.
2020-03-05 | 10 | 10-20 |  |  |  | Turning Machines
2020-03-06 | 10 | 10-20 |  |  |  | Sand Blaster
2020-03-07 | 10 | 10-20 |  |  |  | Washing Machines | [22 empty] | FORMWORK - LABOUR ONLY
2020-03-08 | 11 | 11-20 |  |  |  | Grass Cutting Machines | [23 empty] | Placing formwork - generally | m2 | 750
2020-03-09 | 11 | 11-20 |  |  |  | Line Painting Machines
2020-03-10 | 11 | 11-20 |  |  |  | Mobile Lighting Sets | [22 empty] | STONE PITCHING
2020-03-11 | 11 | 11-20 |  |  |  | Water Pumps | [23 empty] | 150mm Stone pitching including trimming, levelling & preparation of ground surface. Materials supplied by PW | m2 | 750
2020-03-12 | 11 | 11-20 |  |  |  | Crusher - Static | [23 empty] | 150mm Stone pitching. Materials by subcontractor - All in rate | m2 | 4200
2020-03-13 | 11 | 11-20 |  |  |  | Crusher - Mobile
2020-03-14 | 11 | 11-20 |  |  |  | Mobile Screen | [22 empty] | KERBING
2020-03-15 | 12 | 12-20 |  |  |  | Vertical Shaft Impactor (Vsi) | [23 empty] | Removal of existing kerbs | Lm |  | Rate includes removal of base & haunch and loading onto trucks for disposal.
2020-03-16 | 12 | 12-20 |  |  |  | Crawler Drill | [23 empty] | Casting kerbs & handling | Lm | 350
2020-03-17 | 12 | 12-20 | [27 empty] | Excavate, blind, lay & haunch | Lm | 900
2020-03-18 | 12 | 12-20
2020-03-19 | 12 | 12-20 | [26 empty] | BLOCKS - CASTING
2020-03-20 | 12 | 12-20 | [27 empty] | 6" Blocks, cast, water & stack - Labour only | no. | 30
2020-03-21 | 12 | 12-20 | [27 empty] | 9" Blocks, cast, water & stack - Labour only | no. | 50
2020-03-22 | 13 | 13-20
2020-03-23 | 13 | 13-20 | [26 empty] | SANDCRETE BLOCKS - LAYING - LABOUR ONLY
2020-03-24 | 13 | 13-20 | [27 empty] | Laying 6" blocks (labour only) | m2 | 500
2020-03-25 | 13 | 13-20 | [27 empty] | Laying 9" blocks (labour only) | m2 | 700
2020-03-26 | 13 | 13-20 | [27 empty] | Filling of block with concrete | m2 | 300
2020-03-27 | 13 | 13-20
2020-03-28 | 13 | 13-20 | [26 empty] | SANDCRETE BLOCKS - ALL INCLUSIVE RATE
2020-03-29 | 14 | 14-20 | [27 empty] | Supply & Laying 6" blocks | m2 |  | Rate includes supply & mixing of all mortar
2020-03-30 | 14 | 14-20 | [27 empty] | Supply & Laying 9" blocks | m2 |  | Rate includes supply & mixing of all mortar
2020-03-31 | 14 | 14-20 | [27 empty] | Filling of block with concrete | m2 |  | Rate includes supply & mixing of all concrete
2020-04-01 | 14 | 14-20
2020-04-02 | 14 | 14-20 | [26 empty] | INTERLOCKING CONCRETE PAVING - 80MM THK
2020-04-03 | 14 | 14-20 | [27 empty] | Place Interlocking Tiles and bedding sand, including filling joints with sand - Labour only | m2 | 500
2020-04-04 | 14 | 14-20 | [27 empty] | Supply & place Interlocking Tiles - All inclusive rate including supply of bedding sand | m2 | 4500
2020-04-05 | 15 | 15-20
2020-04-06 | 15 | 15-20 | [26 empty] | MISCELLANEOUS OTHERS
2020-04-07 | 15 | 15-20 | [27 empty] | Grassing - including supply & placement of topsoil | m2 | 500
2020-04-08 | 15 | 15-20 | [27 empty] | Plastering - Labour only | m2 | 500
2020-04-09 | 15 | 15-20 | [27 empty] | Plastering - All inclusive rate | m2 |  | Rate includes supplying and mixing of all required materials
2020-04-10 | 15 | 15-20 | [27 empty] | Placing of uPVC ducts in excavated trenches - Labour only | Lm |  | Rate includes all handling, cutting & jointing
2020-04-11 | 15 | 15-20
2020-04-12 | 16 | 16-20 | [26 empty] | DAYWORKS - LABOUR SUPPLY
2020-04-13 | 16 | 16-20 | [27 empty] | General Labourer - Daily Rate | day
2020-04-14 | 16 | 16-20 | [27 empty] | Artisan - Daily Rate | day
2020-04-15 | 16 | 16-20
2020-04-16 | 16 | 16-20
2020-04-17 | 16 | 16-20
2020-04-18 | 16 | 16-20
2020-04-19 | 17 | 17-20
2020-04-20 | 17 | 17-20
2020-04-21 | 17 | 17-20
2020-04-22 | 17 | 17-20
2020-04-23 | 17 | 17-20
2020-04-24 | 17 | 17-20
2020-04-25 | 17 | 17-20
2020-04-26 | 18 | 18-20
2020-04-27 | 18 | 18-20
2020-04-28 | 18 | 18-20
2020-04-29 | 18 | 18-20
2020-04-30 | 18 | 18-20
2020-05-01 | 18 | 18-20
2020-05-02 | 18 | 18-20
2020-05-03 | 19 | 19-20
2020-05-04 | 19 | 19-20
2020-05-05 | 19 | 19-20
2020-05-06 | 19 | 19-20
2020-05-07 | 19 | 19-20
2020-05-08 | 19 | 19-20
2020-05-09 | 19 | 19-20
2020-05-10 | 20 | 20-20
2020-05-11 | 20 | 20-20
2020-05-12 | 20 | 20-20
2020-05-13 | 20 | 20-20
2020-05-14 | 20 | 20-20
2020-05-15 | 20 | 20-20
2020-05-16 | 20 | 20-20
2020-05-17 | 21 | 21-20
2020-05-18 | 21 | 21-20
2020-05-19 | 21 | 21-20
2020-05-20 | 21 | 21-20
2020-05-21 | 21 | 21-20
2020-05-22 | 21 | 21-20
2020-05-23 | 21 | 21-20
2020-05-24 | 22 | 22-20
2020-05-25 | 22 | 22-20
2020-05-26 | 22 | 22-20
2020-05-27 | 22 | 22-20
2020-05-28 | 22 | 22-20
2020-05-29 | 22 | 22-20
2020-05-30 | 22 | 22-20
2020-05-31 | 23 | 23-20
2020-06-01 | 23 | 23-20
2020-06-02 | 23 | 23-20
2020-06-03 | 23 | 23-20
2020-06-04 | 23 | 23-20
2020-06-05 | 23 | 23-20
2020-06-06 | 23 | 23-20
2020-06-07 | 24 | 24-20
2020-06-08 | 24 | 24-20
2020-06-09 | 24 | 24-20
2020-06-10 | 24 | 24-20
2020-06-11 | 24 | 24-20
2020-06-12 | 24 | 24-20
2020-06-13 | 24 | 24-20
2020-06-14 | 25 | 25-20
2020-06-15 | 25 | 25-20
2020-06-16 | 25 | 25-20
2020-06-17 | 25 | 25-20
2020-06-18 | 25 | 25-20
2020-06-19 | 25 | 25-20
2020-06-20 | 25 | 25-20
2020-06-21 | 26 | 26-20
2020-06-22 | 26 | 26-20
2020-06-23 | 26 | 26-20
2020-06-24 | 26 | 26-20
2020-06-25 | 26 | 26-20
2020-06-26 | 26 | 26-20
2020-06-27 | 26 | 26-20
2020-06-28 | 27 | 27-20
2020-06-29 | 27 | 27-20
2020-06-30 | 27 | 27-20
2020-07-01 | 27 | 27-20
2020-07-02 | 27 | 27-20
2020-07-03 | 27 | 27-20
2020-07-04 | 27 | 27-20
2020-07-05 | 28 | 28-20
2020-07-06 | 28 | 28-20
2020-07-07 | 28 | 28-20
2020-07-08 | 28 | 28-20
2020-07-09 | 28 | 28-20
2020-07-10 | 28 | 28-20
2020-07-11 | 28 | 28-20
2020-07-12 | 29 | 29-20
2020-07-13 | 29 | 29-20
2020-07-14 | 29 | 29-20
2020-07-15 | 29 | 29-20
2020-07-16 | 29 | 29-20
2020-07-17 | 29 | 29-20
2020-07-18 | 29 | 29-20
2020-07-19 | 30 | 30-20
2020-07-20 | 30 | 30-20
2020-07-21 | 30 | 30-20
2020-07-22 | 30 | 30-20
2020-07-23 | 30 | 30-20
2020-07-24 | 30 | 30-20
2020-07-25 | 30 | 30-20
2020-07-26 | 31 | 31-20
2020-07-27 | 31 | 31-20
2020-07-28 | 31 | 31-20
2020-07-29 | 31 | 31-20
2020-07-30 | 31 | 31-20
2020-07-31 | 31 | 31-20
2020-08-01 | 31 | 31-20
2020-08-02 | 32 | 32-20
2020-08-03 | 32 | 32-20
2020-08-04 | 32 | 32-20
2020-08-05 | 32 | 32-20
2020-08-06 | 32 | 32-20
2020-08-07 | 32 | 32-20
2020-08-08 | 32 | 32-20
2020-08-09 | 33 | 33-20
2020-08-10 | 33 | 33-20
2020-08-11 | 33 | 33-20
2020-08-12 | 33 | 33-20
2020-08-13 | 33 | 33-20
2020-08-14 | 33 | 33-20
2020-08-15 | 33 | 33-20
2020-08-16 | 34 | 34-20
2020-08-17 | 34 | 34-20
2020-08-18 | 34 | 34-20
2020-08-19 | 34 | 34-20
2020-08-20 | 34 | 34-20
2020-08-21 | 34 | 34-20
2020-08-22 | 34 | 34-20
2020-08-23 | 35 | 35-20
2020-08-24 | 35 | 35-20
2020-08-25 | 35 | 35-20
2020-08-26 | 35 | 35-20
2020-08-27 | 35 | 35-20
2020-08-28 | 35 | 35-20
2020-08-29 | 35 | 35-20
2020-08-30 | 36 | 36-20
2020-08-31 | 36 | 36-20
2020-09-01 | 36 | 36-20
2020-09-02 | 36 | 36-20
2020-09-03 | 36 | 36-20
2020-09-04 | 36 | 36-20
2020-09-05 | 36 | 36-20
2020-09-06 | 37 | 37-20
2020-09-07 | 37 | 37-20
2020-09-08 | 37 | 37-20
2020-09-09 | 37 | 37-20
2020-09-10 | 37 | 37-20
2020-09-11 | 37 | 37-20
2020-09-12 | 37 | 37-20
2020-09-13 | 38 | 38-20
2020-09-14 | 38 | 38-20
2020-09-15 | 38 | 38-20
2020-09-16 | 38 | 38-20
2020-09-17 | 38 | 38-20
2020-09-18 | 38 | 38-20
2020-09-19 | 38 | 38-20
2020-09-20 | 39 | 39-20
2020-09-21 | 39 | 39-20
2020-09-22 | 39 | 39-20
2020-09-23 | 39 | 39-20
2020-09-24 | 39 | 39-20
2020-09-25 | 39 | 39-20
2020-09-26 | 39 | 39-20
2020-09-27 | 40 | 40-20
2020-09-28 | 40 | 40-20
2020-09-29 | 40 | 40-20
2020-09-30 | 40 | 40-20
2020-10-01 | 40 | 40-20
2020-10-02 | 40 | 40-20
2020-10-03 | 40 | 40-20
2020-10-04 | 41 | 41-20
2020-10-05 | 41 | 41-20
2020-10-06 | 41 | 41-20
2020-10-07 | 41 | 41-20
2020-10-08 | 41 | 41-20
2020-10-09 | 41 | 41-20
2020-10-10 | 41 | 41-20
2020-10-11 | 42 | 42-20
2020-10-12 | 42 | 42-20
2020-10-13 | 42 | 42-20
2020-10-14 | 42 | 42-20
2020-10-15 | 42 | 42-20
2020-10-16 | 42 | 42-20
2020-10-17 | 42 | 42-20
2020-10-18 | 43 | 43-20
2020-10-19 | 43 | 43-20
2020-10-20 | 43 | 43-20
2020-10-21 | 43 | 43-20
2020-10-22 | 43 | 43-20
2020-10-23 | 43 | 43-20
2020-10-24 | 43 | 43-20
2020-10-25 | 44 | 44-20
2020-10-26 | 44 | 44-20
2020-10-27 | 44 | 44-20
2020-10-28 | 44 | 44-20
2020-10-29 | 44 | 44-20
2020-10-30 | 44 | 44-20
2020-10-31 | 44 | 44-20
2020-11-01 | 45 | 45-20
2020-11-02 | 45 | 45-20
2020-11-03 | 45 | 45-20
2020-11-04 | 45 | 45-20
2020-11-05 | 45 | 45-20
2020-11-06 | 45 | 45-20
2020-11-07 | 45 | 45-20
2020-11-08 | 46 | 46-20
2020-11-09 | 46 | 46-20
2020-11-10 | 46 | 46-20
2020-11-11 | 46 | 46-20
2020-11-12 | 46 | 46-20
2020-11-13 | 46 | 46-20
2020-11-14 | 46 | 46-20
2020-11-15 | 47 | 47-20
2020-11-16 | 47 | 47-20
2020-11-17 | 47 | 47-20
2020-11-18 | 47 | 47-20
2020-11-19 | 47 | 47-20
2020-11-20 | 47 | 47-20
2020-11-21 | 47 | 47-20
2020-11-22 | 48 | 48-20
2020-11-23 | 48 | 48-20
2020-11-24 | 48 | 48-20
2020-11-25 | 48 | 48-20
2020-11-26 | 48 | 48-20
2020-11-27 | 48 | 48-20
2020-11-28 | 48 | 48-20
2020-11-29 | 49 | 49-20
2020-11-30 | 49 | 49-20
2020-12-01 | 49 | 49-20
2020-12-02 | 49 | 49-20
2020-12-03 | 49 | 49-20
2020-12-04 | 49 | 49-20
2020-12-05 | 49 | 49-20
2020-12-06 | 50 | 50-20
2020-12-07 | 50 | 50-20
2020-12-08 | 50 | 50-20
2020-12-09 | 50 | 50-20
2020-12-10 | 50 | 50-20
2020-12-11 | 50 | 50-20
2020-12-12 | 50 | 50-20
2020-12-13 | 51 | 51-20
2020-12-14 | 51 | 51-20
2020-12-15 | 51 | 51-20
2020-12-16 | 51 | 51-20
2020-12-17 | 51 | 51-20
2020-12-18 | 51 | 51-20
2020-12-19 | 51 | 51-20
2020-12-20 | 52 | 52-20
2020-12-21 | 52 | 52-20
2020-12-22 | 52 | 52-20
2020-12-23 | 52 | 52-20
2020-12-24 | 52 | 52-20
2020-12-25 | 52 | 52-20
2020-12-26 | 52 | 52-20
2020-12-27 | 53 | 53-20
2020-12-28 | 53 | 53-20
2020-12-29 | 53 | 53-20
2020-12-30 | 53 | 53-20
2020-12-31 | 53 | 53-20
2021-01-01 | 1 | 53-21
2021-01-02 | 1 | 2-10
2021-01-03 | 2 | 2-10
2021-01-04 | 2 | 2-10
2021-01-05 | 2 | 2-10
2021-01-06 | 2 | 2-10
2021-01-07 | 2 | 2-10
2021-01-08 | 2 | 2-10
2021-01-09 | 2 | 3-10
2021-01-10 | 3 | 3-10
2021-01-11 | 3 | 3-10
2021-01-12 | 3 | 3-10
2021-01-13 | 3 | 3-10
2021-01-14 | 3 | 3-10
2021-01-15 | 3 | 3-10
2021-01-16 | 3 | 4-10
2021-01-17 | 4 | 4-10
2021-01-18 | 4 | 4-10
2021-01-19 | 4 | 4-10
2021-01-20 | 4 | 4-10
2021-01-21 | 4 | 4-10
2021-01-22 | 4 | 4-10
2021-01-23 | 4 | 5-10
2021-01-24 | 5 | 5-10
2021-01-25 | 5 | 5-10
2021-01-26 | 5 | 5-10
2021-01-27 | 5 | 5-10
2021-01-28 | 5 | 5-10
2021-01-29 | 5 | 5-10
2021-01-30 | 5 | 6-10
2021-01-31 | 6 | 6-10
2021-02-01 | 6 | 6-10
2021-02-02 | 6 | 6-10
2021-02-03 | 6 | 6-10
2021-02-04 | 6 | 6-10
2021-02-05 | 6 | 6-10
2021-02-06 | 6 | 7-10
2021-02-07 | 7 | 7-10
2021-02-08 | 7 | 7-10
2021-02-09 | 7 | 7-10
2021-02-10 | 7 | 7-10
2021-02-11 | 7 | 7-10
2021-02-12 | 7 | 7-10
2021-02-13 | 7 | 8-10
2021-02-14 | 8 | 8-10
2021-02-15 | 8 | 8-10
2021-02-16 | 8 | 8-10
2021-02-17 | 8 | 8-10
2021-02-18 | 8 | 8-10
2021-02-19 | 8 | 8-10
2021-02-20 | 8 | 9-10
2021-02-21 | 9 | 9-10
2021-02-22 | 9 | 9-10
2021-02-23 | 9 | 9-10
2021-02-24 | 9 | 9-10
2021-02-25 | 9 | 9-10
2021-02-26 | 9 | 9-10
2021-02-27 | 9 | 10-10
2021-02-28 | 10 | 10-10
2021-03-01 | 10 | 10-10
2021-03-02 | 10 | 10-10
2021-03-03 | 10 | 10-10
2021-03-04 | 10 | 10-10
2021-03-05 | 10 | 10-10
2021-03-06 | 10 | 11-10
2021-03-07 | 11 | 11-10
2021-03-08 | 11 | 11-10
2021-03-09 | 11 | 11-10
2021-03-10 | 11 | 11-10
2021-03-11 | 11 | 11-10
2021-03-12 | 11 | 11-10
2021-03-13 | 11 | 12-10
2021-03-14 | 12 | 12-10
2021-03-15 | 12 | 12-10
2021-03-16 | 12 | 12-10
2021-03-17 | 12 | 12-10
2021-03-18 | 12 | 12-10
2021-03-19 | 12 | 12-10
2021-03-20 | 12 | 13-10
2021-03-21 | 13 | 13-10
2021-03-22 | 13 | 13-10
2021-03-23 | 13 | 13-10
2021-03-24 | 13 | 13-10
2021-03-25 | 13 | 13-10
2021-03-26 | 13 | 13-10
2021-03-27 | 13 | 14-10
2021-03-28 | 14 | 14-10
2021-03-29 | 14 | 14-10
2021-03-30 | 14 | 14-10
2021-03-31 | 14 | 14-10
2021-04-01 | 14 | 14-10
2021-04-02 | 14 | 14-10
2021-04-03 | 14 | 15-10
2021-04-04 | 15 | 15-10
2021-04-05 | 15 | 15-10
2021-04-06 | 15 | 15-10
2021-04-07 | 15 | 15-10
2021-04-08 | 15 | 15-10
2021-04-09 | 15 | 15-10
2021-04-10 | 15 | 16-10
2021-04-11 | 16 | 16-10
2021-04-12 | 16 | 16-10
2021-04-13 | 16 | 16-10
2021-04-14 | 16 | 16-10
2021-04-15 | 16 | 16-10
2021-04-16 | 16 | 16-10
2021-04-17 | 16 | 17-10
2021-04-18 | 17 | 17-10
2021-04-19 | 17 | 17-10
2021-04-20 | 17 | 17-10
2021-04-21 | 17 | 17-10
2021-04-22 | 17 | 17-10
2021-04-23 | 17 | 17-10
2021-04-24 | 17 | 18-10
2021-04-25 | 18 | 18-10
2021-04-26 | 18 | 18-10
2021-04-27 | 18 | 18-10
2021-04-28 | 18 | 18-10
2021-04-29 | 18 | 18-10
2021-04-30 | 18 | 18-10
2021-05-01 | 18 | 19-10
2021-05-02 | 19 | 19-10
2021-05-03 | 19 | 19-10
2021-05-04 | 19 | 19-10
2021-05-05 | 19 | 19-10
2021-05-06 | 19 | 19-10
2021-05-07 | 19 | 19-10
2021-05-08 | 19 | 20-10
2021-05-09 | 20 | 20-10
2021-05-10 | 20 | 20-10
2021-05-11 | 20 | 20-10
2021-05-12 | 20 | 20-10
2021-05-13 | 20 | 20-10
2021-05-14 | 20 | 20-10
2021-05-15 | 20 | 21-10
2021-05-16 | 21 | 21-10
2021-05-17 | 21 | 21-10
2021-05-18 | 21 | 21-10
2021-05-19 | 21 | 21-10
2021-05-20 | 21 | 21-10
2021-05-21 | 21 | 21-10
2021-05-22 | 21 | 22-10
2021-05-23 | 22 | 22-10
2021-05-24 | 22 | 22-10
2021-05-25 | 22 | 22-10
2021-05-26 | 22 | 22-10
2021-05-27 | 22 | 22-10
2021-05-28 | 22 | 22-10
2021-05-29 | 22 | 23-10
2021-05-30 | 23 | 23-10
2021-05-31 | 23 | 23-10
2021-06-01 | 23 | 23-10
2021-06-02 | 23 | 23-10
2021-06-03 | 23 | 23-10
2021-06-04 | 23 | 23-10
2021-06-05 | 23 | 24-10
2021-06-06 | 24 | 24-10
2021-06-07 | 24 | 24-10
2021-06-08 | 24 | 24-10
2021-06-09 | 24 | 24-10
2021-06-10 | 24 | 24-10
2021-06-11 | 24 | 24-10
2021-06-12 | 24 | 25-10
2021-06-13 | 25 | 25-10
2021-06-14 | 25 | 25-10
2021-06-15 | 25 | 25-10
2021-06-16 | 25 | 25-10
2021-06-17 | 25 | 25-10
2021-06-18 | 25 | 25-10
2021-06-19 | 25 | 26-10
2021-06-20 | 26 | 26-10
2021-06-21 | 26 | 26-10
2021-06-22 | 26 | 26-10
2021-06-23 | 26 | 26-10
2021-06-24 | 26 | 26-10
2021-06-25 | 26 | 26-10
2021-06-26 | 26 | 27-10
2021-06-27 | 27 | 27-10
2021-06-28 | 27 | 27-10
2021-06-29 | 27 | 27-10
2021-06-30 | 27 | 27-10
2021-07-01 | 27 | 27-10
2021-07-02 | 27 | 27-10
2021-07-03 | 27 | 28-10
2021-07-04 | 28 | 28-10
2021-07-05 | 28 | 28-10
2021-07-06 | 28 | 28-10
2021-07-07 | 28 | 28-10
2021-07-08 | 28 | 28-10
2021-07-09 | 28 | 28-10
2021-07-10 | 28 | 29-10
2021-07-11 | 29 | 29-10
2021-07-12 | 29 | 29-10
2021-07-13 | 29 | 29-10
2021-07-14 | 29 | 29-10
2021-07-15 | 29 | 29-10
2021-07-16 | 29 | 29-10
2021-07-17 | 29 | 30-10
2021-07-18 | 30 | 30-10
2021-07-19 | 30 | 30-10
2021-07-20 | 30 | 30-10
2021-07-21 | 30 | 30-10
2021-07-22 | 30 | 30-10
2021-07-23 | 30 | 30-10
2021-07-24 | 30 | 31-10
2021-07-25 | 31 | 31-10
2021-07-26 | 31 | 31-10
2021-07-27 | 31 | 31-10
2021-07-28 | 31 | 31-10
2021-07-29 | 31 | 31-10
2021-07-30 | 31 | 31-10
2021-07-31 | 31 | 32-10
2021-08-01 | 32 | 32-10
2021-08-02 | 32 | 32-10
2021-08-03 | 32 | 32-10
2021-08-04 | 32 | 32-10
2021-08-05 | 32 | 32-10
2021-08-06 | 32 | 32-10
2021-08-07 | 32 | 33-10
2021-08-08 | 33 | 33-10
2021-08-09 | 33 | 33-10
2021-08-10 | 33 | 33-10
2021-08-11 | 33 | 33-10
2021-08-12 | 33 | 33-10
2021-08-13 | 33 | 33-10
2021-08-14 | 33 | 34-10
2021-08-15 | 34 | 34-10
2021-08-16 | 34 | 34-10
2021-08-17 | 34 | 34-10
2021-08-18 | 34 | 34-10
2021-08-19 | 34 | 34-10
2021-08-20 | 34 | 34-10
2021-08-21 | 34 | 35-10
2021-08-22 | 35 | 35-10
2021-08-23 | 35 | 35-10
2021-08-24 | 35 | 35-10
2021-08-25 | 35 | 35-10
2021-08-26 | 35 | 35-10
2021-08-27 | 35 | 35-10
2021-08-28 | 35 | 36-10
2021-08-29 | 36 | 36-10
2021-08-30 | 36 | 36-10
2021-08-31 | 36 | 36-10
2021-09-01 | 36 | 36-10
2021-09-02 | 36 | 36-10
2021-09-03 | 36 | 36-10
2021-09-04 | 36 | 37-10
2021-09-05 | 37 | 37-10
2021-09-06 | 37 | 37-10
2021-09-07 | 37 | 37-10
2021-09-08 | 37 | 37-10
2021-09-09 | 37 | 37-10
2021-09-10 | 37 | 37-10
2021-09-11 | 37 | 38-10
2021-09-12 | 38 | 38-10
2021-09-13 | 38 | 38-10
2021-09-14 | 38 | 38-10
2021-09-15 | 38 | 38-10
2021-09-16 | 38 | 38-10
2021-09-17 | 38 | 38-10
2021-09-18 | 38 | 39-10
2021-09-19 | 39 | 39-10
2021-09-20 | 39 | 39-10
2021-09-21 | 39 | 39-10
2021-09-22 | 39 | 39-10
2021-09-23 | 39 | 39-10
2021-09-24 | 39 | 39-10
2021-09-25 | 39 | 40-10
2021-09-26 | 40 | 40-10
2021-09-27 | 40 | 40-10
2021-09-28 | 40 | 40-10
2021-09-29 | 40 | 40-10
2021-09-30 | 40 | 40-10
2021-10-01 | 40 | 40-10
2021-10-02 | 40 | 41-10
2021-10-03 | 41 | 41-10
2021-10-04 | 41 | 41-10
2021-10-05 | 41 | 41-10
2021-10-06 | 41 | 41-10
2021-10-07 | 41 | 41-10
2021-10-08 | 41 | 41-10
2021-10-09 | 41 | 42-10
2021-10-10 | 42 | 42-10
2021-10-11 | 42 | 42-10
2021-10-12 | 42 | 42-10
2021-10-13 | 42 | 42-10
2021-10-14 | 42 | 42-10
2021-10-15 | 42 | 42-10
2021-10-16 | 42 | 43-10
2021-10-17 | 43 | 43-10
2021-10-18 | 43 | 43-10
2021-10-19 | 43 | 43-10
2021-10-20 | 43 | 43-10
2021-10-21 | 43 | 43-10
2021-10-22 | 43 | 43-10
2021-10-23 | 43 | 44-10
2021-10-24 | 44 | 44-10
2021-10-25 | 44 | 44-10
2021-10-26 | 44 | 44-10
2021-10-27 | 44 | 44-10
2021-10-28 | 44 | 44-10
2021-10-29 | 44 | 44-10
2021-10-30 | 44 | 45-10
2021-10-31 | 45 | 45-10
2021-11-01 | 45 | 45-10
2021-11-02 | 45 | 45-10
2021-11-03 | 45 | 45-10
2021-11-04 | 45 | 45-10
2021-11-05 | 45 | 45-10
2021-11-06 | 45 | 46-10
2021-11-07 | 46 | 46-10
2021-11-08 | 46 | 46-10
2021-11-09 | 46 | 46-10
2021-11-10 | 46 | 46-10
2021-11-11 | 46 | 46-10
2021-11-12 | 46 | 46-10
2021-11-13 | 46 | 47-10
2021-11-14 | 47 | 47-10
2021-11-15 | 47 | 47-10
2021-11-16 | 47 | 47-10
2021-11-17 | 47 | 47-10
2021-11-18 | 47 | 47-10
2021-11-19 | 47 | 47-10
2021-11-20 | 47 | 48-10
2021-11-21 | 48 | 48-10
2021-11-22 | 48 | 48-10
2021-11-23 | 48 | 48-10
2021-11-24 | 48 | 48-10
2021-11-25 | 48 | 48-10
2021-11-26 | 48 | 48-10
2021-11-27 | 48 | 49-10
2021-11-28 | 49 | 49-10
2021-11-29 | 49 | 49-10
2021-11-30 | 49 | 49-10
2021-12-01 | 49 | 49-10
2021-12-02 | 49 | 49-10
2021-12-03 | 49 | 49-10
2021-12-04 | 49 | 50-10
2021-12-05 | 50 | 50-10
2021-12-06 | 50 | 50-10
2021-12-07 | 50 | 50-10
2021-12-08 | 50 | 50-10
2021-12-09 | 50 | 50-10
2021-12-10 | 50 | 50-10
2021-12-11 | 50 | 51-10
2021-12-12 | 51 | 51-10
2021-12-13 | 51 | 51-10
2021-12-14 | 51 | 51-10
2021-12-15 | 51 | 51-10
2021-12-16 | 51 | 51-10
2021-12-17 | 51 | 51-10
2021-12-18 | 51 | 52-10
2021-12-19 | 52 | 52-10
2021-12-20 | 52 | 52-10
2021-12-21 | 52 | 52-10
2021-12-22 | 52 | 52-10
2021-12-23 | 52 | 52-10
2021-12-24 | 52 | 52-10
2021-12-25 | 52 | 53-10
2021-12-26 | 53 | 53-10
2021-12-27 | 53 | 53-10
2021-12-28 | 53 | 53-10
2021-12-29 | 53 | 53-10
2021-12-30 | 53 | 53-10
2021-12-31 | 53 | 1-11
2022-01-01 | 1 | 2-11
2022-01-02 | 2 | 2-11
2022-01-03 | 2 | 2-11
2022-01-04 | 2 | 2-11
2022-01-05 | 2 | 2-11
2022-01-06 | 2 | 2-11
2022-01-07 | 2 | 2-11
2022-01-08 | 2 | 3-11
2022-01-09 | 3 | 3-11
2022-01-10 | 3 | 3-11
2022-01-11 | 3 | 3-11
2022-01-12 | 3 | 3-11
2022-01-13 | 3 | 3-11
2022-01-14 | 3 | 3-11
2022-01-15 | 3 | 4-11
2022-01-16 | 4 | 4-11
2022-01-17 | 4 | 4-11
2022-01-18 | 4 | 4-11
2022-01-19 | 4 | 4-11
2022-01-20 | 4 | 4-11
2022-01-21 | 4 | 4-11
2022-01-22 | 4 | 5-11
2022-01-23 | 5 | 5-11
2022-01-24 | 5 | 5-11
2022-01-25 | 5 | 5-11
2022-01-26 | 5 | 5-11
2022-01-27 | 5 | 5-11
2022-01-28 | 5 | 5-11
2022-01-29 | 5 | 6-11
2022-01-30 | 6 | 6-11
2022-01-31 | 6 | 6-11
2022-02-01 | 6 | 6-11
2022-02-02 | 6 | 6-11
2022-02-03 | 6 | 6-11
2022-02-04 | 6 | 6-11
2022-02-05 | 6 | 7-11
2022-02-06 | 7 | 7-11
2022-02-07 | 7 | 7-11
2022-02-08 | 7 | 7-11
2022-02-09 | 7 | 7-11
2022-02-10 | 7 | 7-11
2022-02-11 | 7 | 7-11
2022-02-12 | 7 | 8-11
2022-02-13 | 8 | 8-11
2022-02-14 | 8 | 8-11
2022-02-15 | 8 | 8-11
2022-02-16 | 8 | 8-11
2022-02-17 | 8 | 8-11
2022-02-18 | 8 | 8-11
2022-02-19 | 8 | 9-11
2022-02-20 | 9 | 9-11
2022-02-21 | 9 | 9-11
2022-02-22 | 9 | 9-11
2022-02-23 | 9 | 9-11
2022-02-24 | 9 | 9-11
2022-02-25 | 9 | 9-11
2022-02-26 | 9 | 10-11
2022-02-27 | 10 | 10-11
2022-02-28 | 10 | 10-11
2022-03-01 | 10 | 10-11
2022-03-02 | 10 | 10-11
2022-03-03 | 10 | 10-11
2022-03-04 | 10 | 10-11
2022-03-05 | 10 | 11-11
2022-03-06 | 11 | 11-11
2022-03-07 | 11 | 11-11
2022-03-08 | 11 | 11-11
2022-03-09 | 11 | 11-11
2022-03-10 | 11 | 11-11
2022-03-11 | 11 | 11-11
2022-03-12 | 11 | 12-11
2022-03-13 | 12 | 12-11
2022-03-14 | 12 | 12-11
2022-03-15 | 12 | 12-11
2022-03-16 | 12 | 12-11
2022-03-17 | 12 | 12-11
2022-03-18 | 12 | 12-11
2022-03-19 | 12 | 13-11
2022-03-20 | 13 | 13-11
2022-03-21 | 13 | 13-11
2022-03-22 | 13 | 13-11
2022-03-23 | 13 | 13-11
2022-03-24 | 13 | 13-11
2022-03-25 | 13 | 13-11
2022-03-26 | 13 | 14-11
2022-03-27 | 14 | 14-11
2022-03-28 | 14 | 14-11
2022-03-29 | 14 | 14-11
2022-03-30 | 14 | 14-11
2022-03-31 | 14 | 14-11
2022-04-01 | 14 | 14-11
2022-04-02 | 14 | 15-11
2022-04-03 | 15 | 15-11
2022-04-04 | 15 | 15-11
2022-04-05 | 15 | 15-11
2022-04-06 | 15 | 15-11
2022-04-07 | 15 | 15-11
2022-04-08 | 15 | 15-11
2022-04-09 | 15 | 16-11
2022-04-10 | 16 | 16-11
2022-04-11 | 16 | 16-11
2022-04-12 | 16 | 16-11
2022-04-13 | 16 | 16-11
2022-04-14 | 16 | 16-11
2022-04-15 | 16 | 16-11
2022-04-16 | 16 | 17-11
2022-04-17 | 17 | 17-11
2022-04-18 | 17 | 17-11
2022-04-19 | 17 | 17-11
2022-04-20 | 17 | 17-11
2022-04-21 | 17 | 17-11
2022-04-22 | 17 | 17-11
2022-04-23 | 17 | 18-11
2022-04-24 | 18 | 18-11
2022-04-25 | 18 | 18-11
2022-04-26 | 18 | 18-11
2022-04-27 | 18 | 18-11
2022-04-28 | 18 | 18-11
2022-04-29 | 18 | 18-11
2022-04-30 | 18 | 19-11
2022-05-01 | 19 | 19-11
2022-05-02 | 19 | 19-11
2022-05-03 | 19 | 19-11
2022-05-04 | 19 | 19-11
2022-05-05 | 19 | 19-11
2022-05-06 | 19 | 19-11
2022-05-07 | 19 | 20-11
2022-05-08 | 20 | 20-11
2022-05-09 | 20 | 20-11
2022-05-10 | 20 | 20-11
2022-05-11 | 20 | 20-11
2022-05-12 | 20 | 20-11
2022-05-13 | 20 | 20-11
2022-05-14 | 20 | 21-11
2022-05-15 | 21 | 21-11
2022-05-16 | 21 | 21-11
2022-05-17 | 21 | 21-11
2022-05-18 | 21 | 21-11
2022-05-19 | 21 | 21-11
2022-05-20 | 21 | 21-11
2022-05-21 | 21 | 22-11
2022-05-22 | 22 | 22-11
2022-05-23 | 22 | 22-11
2022-05-24 | 22 | 22-11
2022-05-25 | 22 | 22-11
2022-05-26 | 22 | 22-11
2022-05-27 | 22 | 22-11
2022-05-28 | 22 | 23-11
2022-05-29 | 23 | 23-11
2022-05-30 | 23 | 23-11
2022-05-31 | 23 | 23-11
2022-06-01 | 23 | 23-11
2022-06-02 | 23 | 23-11
2022-06-03 | 23 | 23-11
2022-06-04 | 23 | 24-11
2022-06-05 | 24 | 24-11
2022-06-06 | 24 | 24-11
2022-06-07 | 24 | 24-11
2022-06-08 | 24 | 24-11
2022-06-09 | 24 | 24-11
2022-06-10 | 24 | 24-11
2022-06-11 | 24 | 25-11
2022-06-12 | 25 | 25-11
2022-06-13 | 25 | 25-11
2022-06-14 | 25 | 25-11
2022-06-15 | 25 | 25-11
2022-06-16 | 25 | 25-11
2022-06-17 | 25 | 25-11
2022-06-18 | 25 | 26-11
2022-06-19 | 26 | 26-11
2022-06-20 | 26 | 26-11
2022-06-21 | 26 | 26-11
2022-06-22 | 26 | 26-11
2022-06-23 | 26 | 26-11
2022-06-24 | 26 | 26-11
2022-06-25 | 26 | 27-11
2022-06-26 | 27 | 27-11
2022-06-27 | 27 | 27-11
2022-06-28 | 27 | 27-11
2022-06-29 | 27 | 27-11
2022-06-30 | 27 | 27-11
2022-07-01 | 27 | 27-11
2022-07-02 | 27 | 28-11
2022-07-03 | 28 | 28-11
2022-07-04 | 28 | 28-11
2022-07-05 | 28 | 28-11
2022-07-06 | 28 | 28-11
2022-07-07 | 28 | 28-11
2022-07-08 | 28 | 28-11
2022-07-09 | 28 | 29-11
2022-07-10 | 29 | 29-11
2022-07-11 | 29 | 29-11
2022-07-12 | 29 | 29-11
2022-07-13 | 29 | 29-11
2022-07-14 | 29 | 29-11
2022-07-15 | 29 | 29-11
2022-07-16 | 29 | 30-11
2022-07-17 | 30 | 30-11
2022-07-18 | 30 | 30-11
2022-07-19 | 30 | 30-11
2022-07-20 | 30 | 30-11
2022-07-21 | 30 | 30-11
2022-07-22 | 30 | 30-11
2022-07-23 | 30 | 31-11
2022-07-24 | 31 | 31-11
2022-07-25 | 31 | 31-11
2022-07-26 | 31 | 31-11
2022-07-27 | 31 | 31-11
2022-07-28 | 31 | 31-11
2022-07-29 | 31 | 31-11
2022-07-30 | 31 | 32-11
2022-07-31 | 32 | 32-11
2022-08-01 | 32 | 32-11
2022-08-02 | 32 | 32-11
2022-08-03 | 32 | 32-11
2022-08-04 | 32 | 32-11
2022-08-05 | 32 | 32-11
2022-08-06 | 32 | 33-11
2022-08-07 | 33 | 33-11
2022-08-08 | 33 | 33-11
2022-08-09 | 33 | 33-11
2022-08-10 | 33 | 33-11
2022-08-11 | 33 | 33-11
2022-08-12 | 33 | 33-11
2022-08-13 | 33 | 34-11
2022-08-14 | 34 | 34-11
2022-08-15 | 34 | 34-11
2022-08-16 | 34 | 34-11
2022-08-17 | 34 | 34-11
2022-08-18 | 34 | 34-11
2022-08-19 | 34 | 34-11
2022-08-20 | 34 | 35-11
2022-08-21 | 35 | 35-11
2022-08-22 | 35 | 35-11
2022-08-23 | 35 | 35-11
2022-08-24 | 35 | 35-11
2022-08-25 | 35 | 35-11
2022-08-26 | 35 | 35-11
2022-08-27 | 35 | 36-11
2022-08-28 | 36 | 36-11
2022-08-29 | 36 | 36-11
2022-08-30 | 36 | 36-11
2022-08-31 | 36 | 36-11
2022-09-01 | 36 | 36-11
2022-09-02 | 36 | 36-11
2022-09-03 | 36 | 37-11
2022-09-04 | 37 | 37-11
2022-09-05 | 37 | 37-11
2022-09-06 | 37 | 37-11
2022-09-07 | 37 | 37-11
2022-09-08 | 37 | 37-11
2022-09-09 | 37 | 37-11
2022-09-10 | 37 | 38-11
2022-09-11 | 38 | 38-11
2022-09-12 | 38 | 38-11
2022-09-13 | 38 | 38-11
2022-09-14 | 38 | 38-11
2022-09-15 | 38 | 38-11
2022-09-16 | 38 | 38-11
2022-09-17 | 38 | 39-11
2022-09-18 | 39 | 39-11
2022-09-19 | 39 | 39-11
2022-09-20 | 39 | 39-11
2022-09-21 | 39 | 39-11
2022-09-22 | 39 | 39-11
2022-09-23 | 39 | 39-11
2022-09-24 | 39 | 40-11
2022-09-25 | 40 | 40-11
2022-09-26 | 40 | 40-11
2022-09-27 | 40 | 40-11
2022-09-28 | 40 | 40-11
2022-09-29 | 40 | 40-11
2022-09-30 | 40 | 40-11
2022-10-01 | 40 | 41-11
2022-10-02 | 41 | 41-11
2022-10-03 | 41 | 41-11
2022-10-04 | 41 | 41-11
2022-10-05 | 41 | 41-11
2022-10-06 | 41 | 41-11
2022-10-07 | 41 | 41-11
2022-10-08 | 41 | 42-11
2022-10-09 | 42 | 42-11
2022-10-10 | 42 | 42-11
2022-10-11 | 42 | 42-11
2022-10-12 | 42 | 42-11
2022-10-13 | 42 | 42-11
2022-10-14 | 42 | 42-11
2022-10-15 | 42 | 43-11
2022-10-16 | 43 | 43-11
2022-10-17 | 43 | 43-11
2022-10-18 | 43 | 43-11
2022-10-19 | 43 | 43-11
2022-10-20 | 43 | 43-11
2022-10-21 | 43 | 43-11
2022-10-22 | 43 | 44-11
2022-10-23 | 44 | 44-11
2022-10-24 | 44 | 44-11
2022-10-25 | 44 | 44-11
2022-10-26 | 44 | 44-11
2022-10-27 | 44 | 44-11
2022-10-28 | 44 | 44-11
2022-10-29 | 44 | 45-11
2022-10-30 | 45 | 45-11
2022-10-31 | 45 | 45-11
2022-11-01 | 45 | 45-11
2022-11-02 | 45 | 45-11
2022-11-03 | 45 | 45-11
2022-11-04 | 45 | 45-11
2022-11-05 | 45 | 46-11
2022-11-06 | 46 | 46-11
2022-11-07 | 46 | 46-11
2022-11-08 | 46 | 46-11
2022-11-09 | 46 | 46-11
2022-11-10 | 46 | 46-11
2022-11-11 | 46 | 46-11
2022-11-12 | 46 | 47-11
2022-11-13 | 47 | 47-11
2022-11-14 | 47 | 47-11
2022-11-15 | 47 | 47-11
2022-11-16 | 47 | 47-11
2022-11-17 | 47 | 47-11
2022-11-18 | 47 | 47-11
2022-11-19 | 47 | 48-11
2022-11-20 | 48 | 48-11
2022-11-21 | 48 | 48-11
2022-11-22 | 48 | 48-11
2022-11-23 | 48 | 48-11
2022-11-24 | 48 | 48-11
2022-11-25 | 48 | 48-11
2022-11-26 | 48 | 49-11
2022-11-27 | 49 | 49-11
2022-11-28 | 49 | 49-11
2022-11-29 | 49 | 49-11
2022-11-30 | 49 | 49-11
2022-12-01 | 49 | 49-11
2022-12-02 | 49 | 49-11
2022-12-03 | 49 | 50-11
2022-12-04 | 50 | 50-11
2022-12-05 | 50 | 50-11
2022-12-06 | 50 | 50-11
2022-12-07 | 50 | 50-11
2022-12-08 | 50 | 50-11
2022-12-09 | 50 | 50-11
2022-12-10 | 50 | 51-11
2022-12-11 | 51 | 51-11
2022-12-12 | 51 | 51-11
2022-12-13 | 51 | 51-11
2022-12-14 | 51 | 51-11
2022-12-15 | 51 | 51-11
2022-12-16 | 51 | 51-11
2022-12-17 | 51 | 52-11
2022-12-18 | 52 | 52-11
2022-12-19 | 52 | 52-11
2022-12-20 | 52 | 52-11
2022-12-21 | 52 | 52-11
2022-12-22 | 52 | 52-11
2022-12-23 | 52 | 52-11
2022-12-24 | 52 | 53-11
2022-12-25 | 53 | 53-11
2022-12-26 | 53 | 53-11
2022-12-27 | 53 | 53-11
2022-12-28 | 53 | 53-11
2022-12-29 | 53 | 53-11
2022-12-30 | 53 | 53-11
2022-12-31 | 53 | 1-12
2023-01-01 | 1 | 1-12
2023-01-02 | 1 | 1-12
2023-01-03 | 1 | 1-12
2023-01-04 | 1 | 1-12
2023-01-05 | 1 | 1-12
2023-01-06 | 1 | 1-12
2023-01-07 | 1 | 2-12
2023-01-08 | 2 | 2-12
2023-01-09 | 2 | 2-12
2023-01-10 | 2 | 2-12
2023-01-11 | 2 | 2-12
2023-01-12 | 2 | 2-12
2023-01-13 | 2 | 2-12
2023-01-14 | 2 | 3-12
2023-01-15 | 3 | 3-12
2023-01-16 | 3 | 3-12
2023-01-17 | 3 | 3-12
2023-01-18 | 3 | 3-12
2023-01-19 | 3 | 3-12
2023-01-20 | 3 | 3-12
2023-01-21 | 3 | 4-12
2023-01-22 | 4 | 4-12
2023-01-23 | 4 | 4-12
2023-01-24 | 4 | 4-12
2023-01-25 | 4 | 4-12
2023-01-26 | 4 | 4-12
2023-01-27 | 4 | 4-12
2023-01-28 | 4 | 5-12
2023-01-29 | 5 | 5-12
2023-01-30 | 5 | 5-12
2023-01-31 | 5 | 5-12
2023-02-01 | 5 | 5-12
2023-02-02 | 5 | 5-12
2023-02-03 | 5 | 5-12
2023-02-04 | 5 | 6-12
2023-02-05 | 6 | 6-12
2023-02-06 | 6 | 6-12
2023-02-07 | 6 | 6-12
2023-02-08 | 6 | 6-12
2023-02-09 | 6 | 6-12
2023-02-10 | 6 | 6-12
2023-02-11 | 6 | 7-12
2023-02-12 | 7 | 7-12
2023-02-13 | 7 | 7-12
2023-02-14 | 7 | 7-12
2023-02-15 | 7 | 7-12
2023-02-16 | 7 | 7-12
2023-02-17 | 7 | 7-12
2023-02-18 | 7 | 8-12
2023-02-19 | 8 | 8-12
2023-02-20 | 8 | 8-12
2023-02-21 | 8 | 8-12
2023-02-22 | 8 | 8-12
2023-02-23 | 8 | 8-12
2023-02-24 | 8 | 8-12
2023-02-25 | 8 | 9-12
2023-02-26 | 9 | 9-12
2023-02-27 | 9 | 9-12
2023-02-28 | 9 | 9-12
2023-03-01 | 9 | 9-12
2023-03-02 | 9 | 9-12
2023-03-03 | 9 | 9-12
2023-03-04 | 9 | 10-12
2023-03-05 | 10 | 10-12
2023-03-06 | 10 | 10-12
2023-03-07 | 10 | 10-12
2023-03-08 | 10 | 10-12
2023-03-09 | 10 | 10-12
2023-03-10 | 10 | 10-12
2023-03-11 | 10 | 11-12
2023-03-12 | 11 | 11-12
2023-03-13 | 11 | 11-12
2023-03-14 | 11 | 11-12
2023-03-15 | 11 | 11-12
2023-03-16 | 11 | 11-12
2023-03-17 | 11 | 11-12
2023-03-18 | 11 | 12-12
2023-03-19 | 12 | 12-12
2023-03-20 | 12 | 12-12
2023-03-21 | 12 | 12-12
2023-03-22 | 12 | 12-12
2023-03-23 | 12 | 12-12
2023-03-24 | 12 | 12-12
2023-03-25 | 12 | 13-12
2023-03-26 | 13 | 13-12
2023-03-27 | 13 | 13-12
2023-03-28 | 13 | 13-12
2023-03-29 | 13 | 13-12
2023-03-30 | 13 | 13-12
2023-03-31 | 13 | 13-12
2023-04-01 | 13 | 14-12
2023-04-02 | 14 | 14-12
2023-04-03 | 14 | 14-12
2023-04-04 | 14 | 14-12
2023-04-05 | 14 | 14-12
2023-04-06 | 14 | 14-12
2023-04-07 | 14 | 14-12
2023-04-08 | 14 | 15-12
2023-04-09 | 15 | 15-12
2023-04-10 | 15 | 15-12
2023-04-11 | 15 | 15-12
2023-04-12 | 15 | 15-12
2023-04-13 | 15 | 15-12
2023-04-14 | 15 | 15-12
2023-04-15 | 15 | 16-12
2023-04-16 | 16 | 16-12
2023-04-17 | 16 | 16-12
2023-04-18 | 16 | 16-12
2023-04-19 | 16 | 16-12
2023-04-20 | 16 | 16-12
2023-04-21 | 16 | 16-12
2023-04-22 | 16 | 17-12
2023-04-23 | 17 | 17-12
2023-04-24 | 17 | 17-12
2023-04-25 | 17 | 17-12
2023-04-26 | 17 | 17-12
2023-04-27 | 17 | 17-12
2023-04-28 | 17 | 17-12
2023-04-29 | 17 | 18-12
2023-04-30 | 18 | 18-12
2023-05-01 | 18 | 18-12
2023-05-02 | 18 | 18-12
2023-05-03 | 18 | 18-12
2023-05-04 | 18 | 18-12
2023-05-05 | 18 | 18-12
2023-05-06 | 18 | 19-12
2023-05-07 | 19 | 19-12
2023-05-08 | 19 | 19-12
2023-05-09 | 19 | 19-12
2023-05-10 | 19 | 19-12
2023-05-11 | 19 | 19-12
2023-05-12 | 19 | 19-12
2023-05-13 | 19 | 20-12
2023-05-14 | 20 | 20-12
2023-05-15 | 20 | 20-12
2023-05-16 | 20 | 20-12
2023-05-17 | 20 | 20-12
2023-05-18 | 20 | 20-12
2023-05-19 | 20 | 20-12
2023-05-20 | 20 | 21-12
2023-05-21 | 21 | 21-12
2023-05-22 | 21 | 21-12
2023-05-23 | 21 | 21-12
2023-05-24 | 21 | 21-12
2023-05-25 | 21 | 21-12
2023-05-26 | 21 | 21-12
2023-05-27 | 21 | 22-12
2023-05-28 | 22 | 22-12
2023-05-29 | 22 | 22-12
2023-05-30 | 22 | 22-12
2023-05-31 | 22 | 22-12
2023-06-01 | 22 | 22-12
2023-06-02 | 22 | 22-12
2023-06-03 | 22 | 23-12
2023-06-04 | 23 | 23-12
2023-06-05 | 23 | 23-12
2023-06-06 | 23 | 23-12
2023-06-07 | 23 | 23-12
2023-06-08 | 23 | 23-12
2023-06-09 | 23 | 23-12
2023-06-10 | 23 | 24-12
2023-06-11 | 24 | 24-12
2023-06-12 | 24 | 24-12
2023-06-13 | 24 | 24-12
2023-06-14 | 24 | 24-12
2023-06-15 | 24 | 24-12
2023-06-16 | 24 | 24-12
2023-06-17 | 24 | 25-12
2023-06-18 | 25 | 25-12
2023-06-19 | 25 | 25-12
2023-06-20 | 25 | 25-12
2023-06-21 | 25 | 25-12
2023-06-22 | 25 | 25-12
2023-06-23 | 25 | 25-12
2023-06-24 | 25 | 26-12
2023-06-25 | 26 | 26-12
2023-06-26 | 26 | 26-12
2023-06-27 | 26 | 26-12
2023-06-28 | 26 | 26-12
2023-06-29 | 26 | 26-12
2023-06-30 | 26 | 26-12
2023-07-01 | 26 | 27-12
2023-07-02 | 27 | 27-12
2023-07-03 | 27 | 27-12
2023-07-04 | 27 | 27-12
2023-07-05 | 27 | 27-12
2023-07-06 | 27 | 27-12
2023-07-07 | 27 | 27-12
2023-07-08 | 27 | 28-12
2023-07-09 | 28 | 28-12
2023-07-10 | 28 | 28-12
2023-07-11 | 28 | 28-12
2023-07-12 | 28 | 28-12
2023-07-13 | 28 | 28-12
2023-07-14 | 28 | 28-12
2023-07-15 | 28 | 29-12
2023-07-16 | 29 | 29-12
2023-07-17 | 29 | 29-12
2023-07-18 | 29 | 29-12
2023-07-19 | 29 | 29-12
2023-07-20 | 29 | 29-12
2023-07-21 | 29 | 29-12
2023-07-22 | 29 | 30-12
2023-07-23 | 30 | 30-12
2023-07-24 | 30 | 30-12
2023-07-25 | 30 | 30-12
2023-07-26 | 30 | 30-12
2023-07-27 | 30 | 30-12
2023-07-28 | 30 | 30-12
2023-07-29 | 30 | 31-12
2023-07-30 | 31 | 31-12
2023-07-31 | 31 | 31-12
2023-08-01 | 31 | 31-12
2023-08-02 | 31 | 31-12
2023-08-03 | 31 | 31-12
2023-08-04 | 31 | 31-12
2023-08-05 | 31 | 32-12
2023-08-06 | 32 | 32-12
2023-08-07 | 32 | 32-12
2023-08-08 | 32 | 32-12
2023-08-09 | 32 | 32-12
2023-08-10 | 32 | 32-12
2023-08-11 | 32 | 32-12
2023-08-12 | 32 | 33-12
2023-08-13 | 33 | 33-12
2023-08-14 | 33 | 33-12
2023-08-15 | 33 | 33-12
2023-08-16 | 33 | 33-12
2023-08-17 | 33 | 33-12
2023-08-18 | 33 | 33-12
2023-08-19 | 33 | 34-12
2023-08-20 | 34 | 34-12
2023-08-21 | 34 | 34-12
2023-08-22 | 34 | 34-12
2023-08-23 | 34 | 34-12
2023-08-24 | 34 | 34-12
2023-08-25 | 34 | 34-12
2023-08-26 | 34 | 35-12
2023-08-27 | 35 | 35-12
2023-08-28 | 35 | 35-12
2023-08-29 | 35 | 35-12
2023-08-30 | 35 | 35-12
2023-08-31 | 35 | 35-12
2023-09-01 | 35 | 35-12
2023-09-02 | 35 | 36-12
2023-09-03 | 36 | 36-12
2023-09-04 | 36 | 36-12
2023-09-05 | 36 | 36-12
2023-09-06 | 36 | 36-12
2023-09-07 | 36 | 36-12
2023-09-08 | 36 | 36-12
2023-09-09 | 36 | 37-12
2023-09-10 | 37 | 37-12
2023-09-11 | 37 | 37-12
2023-09-12 | 37 | 37-12
2023-09-13 | 37 | 37-12
2023-09-14 | 37 | 37-12
2023-09-15 | 37 | 37-12
2023-09-16 | 37 | 38-12
2023-09-17 | 38 | 38-12
2023-09-18 | 38 | 38-12
2023-09-19 | 38 | 38-12
2023-09-20 | 38 | 38-12
2023-09-21 | 38 | 38-12
2023-09-22 | 38 | 38-12
2023-09-23 | 38 | 39-12
2023-09-24 | 39 | 39-12
2023-09-25 | 39 | 39-12
2023-09-26 | 39 | 39-12
2023-09-27 | 39 | 39-12
2023-09-28 | 39 | 39-12
2023-09-29 | 39 | 39-12
2023-09-30 | 39 | 40-12
2023-10-01 | 40 | 40-12
2023-10-02 | 40 | 40-12
2023-10-03 | 40 | 40-12
2023-10-04 | 40 | 40-12
2023-10-05 | 40 | 40-12
2023-10-06 | 40 | 40-12
2023-10-07 | 40 | 41-12
2023-10-08 | 41 | 41-12
2023-10-09 | 41 | 41-12
2023-10-10 | 41 | 41-12
2023-10-11 | 41 | 41-12
2023-10-12 | 41 | 41-12
2023-10-13 | 41 | 41-12
2023-10-14 | 41 | 42-12
2023-10-15 | 42 | 42-12
2023-10-16 | 42 | 42-12
2023-10-17 | 42 | 42-12
2023-10-18 | 42 | 42-12
2023-10-19 | 42 | 42-12
2023-10-20 | 42 | 42-12
2023-10-21 | 42 | 43-12
2023-10-22 | 43 | 43-12
2023-10-23 | 43 | 43-12
2023-10-24 | 43 | 43-12
2023-10-25 | 43 | 43-12
2023-10-26 | 43 | 43-12
2023-10-27 | 43 | 43-12
2023-10-28 | 43 | 44-12
2023-10-29 | 44 | 44-12
2023-10-30 | 44 | 44-12
2023-10-31 | 44 | 44-12
2023-11-01 | 44 | 44-12
2023-11-02 | 44 | 44-12
2023-11-03 | 44 | 44-12
2023-11-04 | 44 | 45-12
2023-11-05 | 45 | 45-12
2023-11-06 | 45 | 45-12
2023-11-07 | 45 | 45-12
2023-11-08 | 45 | 45-12
2023-11-09 | 45 | 45-12
2023-11-10 | 45 | 45-12
2023-11-11 | 45 | 46-12
2023-11-12 | 46 | 46-12
2023-11-13 | 46 | 46-12
2023-11-14 | 46 | 46-12
2023-11-15 | 46 | 46-12
2023-11-16 | 46 | 46-12
2023-11-17 | 46 | 46-12
2023-11-18 | 46 | 47-12
2023-11-19 | 47 | 47-12
2023-11-20 | 47 | 47-12
2023-11-21 | 47 | 47-12
2023-11-22 | 47 | 47-12
2023-11-23 | 47 | 47-12
2023-11-24 | 47 | 47-12
2023-11-25 | 47 | 48-12
2023-11-26 | 48 | 48-12
2023-11-27 | 48 | 48-12
2023-11-28 | 48 | 48-12
2023-11-29 | 48 | 48-12
2023-11-30 | 48 | 48-12
2023-12-01 | 48 | 48-12
2023-12-02 | 48 | 49-12
2023-12-03 | 49 | 49-12
2023-12-04 | 49 | 49-12
2023-12-05 | 49 | 49-12
2023-12-06 | 49 | 49-12
2023-12-07 | 49 | 49-12
2023-12-08 | 49 | 49-12
2023-12-09 | 49 | 50-12
2023-12-10 | 50 | 50-12
2023-12-11 | 50 | 50-12
2023-12-12 | 50 | 50-12
2023-12-13 | 50 | 50-12
2023-12-14 | 50 | 50-12
2023-12-15 | 50 | 50-12
2023-12-16 | 50 | 51-12
2023-12-17 | 51 | 51-12
2023-12-18 | 51 | 51-12
2023-12-19 | 51 | 51-12
2023-12-20 | 51 | 51-12
2023-12-21 | 51 | 51-12
2023-12-22 | 51 | 51-12
2023-12-23 | 51 | 52-12
2023-12-24 | 52 | 52-12
2023-12-25 | 52 | 52-12
2023-12-26 | 52 | 52-12
2023-12-27 | 52 | 52-12
2023-12-28 | 52 | 52-12
2023-12-29 | 52 | 52-12
2023-12-30 | 52 | 53-12
2023-12-31 | 53 | 53-12
2024-01-01 | 1 | 1-13
2024-01-02 | 1 | 1-13
2024-01-03 | 1 | 1-13
2024-01-04 | 1 | 1-13
2024-01-05 | 1 | 1-13
2024-01-06 | 1 | 2-13
2024-01-07 | 2 | 2-13
2024-01-08 | 2 | 2-13
2024-01-09 | 2 | 2-13
2024-01-10 | 2 | 2-13
2024-01-11 | 2 | 2-13
2024-01-12 | 2 | 2-13
2024-01-13 | 2 | 3-13
2024-01-14 | 3 | 3-13
2024-01-15 | 3 | 3-13
2024-01-16 | 3 | 3-13
2024-01-17 | 3 | 3-13
2024-01-18 | 3 | 3-13
2024-01-19 | 3 | 3-13
2024-01-20 | 3 | 4-13
2024-01-21 | 4 | 4-13
2024-01-22 | 4 | 4-13
2024-01-23 | 4 | 4-13
2024-01-24 | 4 | 4-13
2024-01-25 | 4 | 4-13
2024-01-26 | 4 | 4-13
2024-01-27 | 4 | 5-13
2024-01-28 | 5 | 5-13
2024-01-29 | 5 | 5-13
2024-01-30 | 5 | 5-13
2024-01-31 | 5 | 5-13
2024-02-01 | 5 | 5-13
2024-02-02 | 5 | 5-13
2024-02-03 | 5 | 6-13
2024-02-04 | 6 | 6-13
2024-02-05 | 6 | 6-13
2024-02-06 | 6 | 6-13
2024-02-07 | 6 | 6-13
2024-02-08 | 6 | 6-13
2024-02-09 | 6 | 6-13
2024-02-10 | 6 | 7-13
2024-02-11 | 7 | 7-13
2024-02-12 | 7 | 7-13
2024-02-13 | 7 | 7-13
2024-02-14 | 7 | 7-13
2024-02-15 | 7 | 7-13
2024-02-16 | 7 | 7-13
2024-02-17 | 7 | 8-13
2024-02-18 | 8 | 8-13
2024-02-19 | 8 | 8-13
2024-02-20 | 8 | 8-13
2024-02-21 | 8 | 8-13
2024-02-22 | 8 | 8-13
2024-02-23 | 8 | 8-13
2024-02-24 | 8 | 9-13
2024-02-25 | 9 | 9-13
2024-02-26 | 9 | 9-13
2024-02-27 | 9 | 9-13
2024-02-28 | 9 | 9-13
2024-02-29 | 9 | 9-13
2024-03-01 | 9 | 9-13
2024-03-02 | 9 | 10-13
2024-03-03 | 10 | 10-13
2024-03-04 | 10 | 10-13
2024-03-05 | 10 | 10-13
2024-03-06 | 10 | 10-13
2024-03-07 | 10 | 10-13
2024-03-08 | 10 | 10-13
2024-03-09 | 10 | 11-13
2024-03-10 | 11 | 11-13
2024-03-11 | 11 | 11-13
2024-03-12 | 11 | 11-13
2024-03-13 | 11 | 11-13
2024-03-14 | 11 | 11-13
2024-03-15 | 11 | 11-13
2024-03-16 | 11 | 12-13
2024-03-17 | 12 | 12-13
2024-03-18 | 12 | 12-13
2024-03-19 | 12 | 12-13
2024-03-20 | 12 | 12-13
2024-03-21 | 12 | 12-13
2024-03-22 | 12 | 12-13
2024-03-23 | 12 | 13-13
2024-03-24 | 13 | 13-13
2024-03-25 | 13 | 13-13
2024-03-26 | 13 | 13-13
2024-03-27 | 13 | 13-13
2024-03-28 | 13 | 13-13
2024-03-29 | 13 | 13-13
2024-03-30 | 13 | 14-13
2024-03-31 | 14 | 14-13
2024-04-01 | 14 | 14-13
2024-04-02 | 14 | 14-13
2024-04-03 | 14 | 14-13
2024-04-04 | 14 | 14-13
2024-04-05 | 14 | 14-13
2024-04-06 | 14 | 15-13
2024-04-07 | 15 | 15-13
2024-04-08 | 15 | 15-13
2024-04-09 | 15 | 15-13
2024-04-10 | 15 | 15-13
2024-04-11 | 15 | 15-13
2024-04-12 | 15 | 15-13
2024-04-13 | 15 | 16-13
2024-04-14 | 16 | 16-13
2024-04-15 | 16 | 16-13
2024-04-16 | 16 | 16-13
2024-04-17 | 16 | 16-13
2024-04-18 | 16 | 16-13
2024-04-19 | 16 | 16-13
2024-04-20 | 16 | 17-13
2024-04-21 | 17 | 17-13
2024-04-22 | 17 | 17-13
2024-04-23 | 17 | 17-13
2024-04-24 | 17 | 17-13
2024-04-25 | 17 | 17-13
2024-04-26 | 17 | 17-13
2024-04-27 | 17 | 18-13
2024-04-28 | 18 | 18-13
2024-04-29 | 18 | 18-13
2024-04-30 | 18 | 18-13
2024-05-01 | 18 | 18-13
2024-05-02 | 18 | 18-13
2024-05-03 | 18 | 18-13
2024-05-04 | 18 | 19-13
2024-05-05 | 19 | 19-13
2024-05-06 | 19 | 19-13
2024-05-07 | 19 | 19-13
2024-05-08 | 19 | 19-13
2024-05-09 | 19 | 19-13
2024-05-10 | 19 | 19-13
2024-05-11 | 19 | 20-13
2024-05-12 | 20 | 20-13
2024-05-13 | 20 | 20-13
2024-05-14 | 20 | 20-13
2024-05-15 | 20 | 20-13
2024-05-16 | 20 | 20-13
2024-05-17 | 20 | 20-13
2024-05-18 | 20 | 21-13
2024-05-19 | 21 | 21-13
2024-05-20 | 21 | 21-13
2024-05-21 | 21 | 21-13
2024-05-22 | 21 | 21-13
2024-05-23 | 21 | 21-13
2024-05-24 | 21 | 21-13
2024-05-25 | 21 | 22-13
2024-05-26 | 22 | 22-13
2024-05-27 | 22 | 22-13
2024-05-28 | 22 | 22-13
2024-05-29 | 22 | 22-13
2024-05-30 | 22 | 22-13
2024-05-31 | 22 | 22-13
2024-06-01 | 22 | 23-13
2024-06-02 | 23 | 23-13
2024-06-03 | 23 | 23-13
2024-06-04 | 23 | 23-13
2024-06-05 | 23 | 23-13
2024-06-06 | 23 | 23-13
2024-06-07 | 23 | 23-13
2024-06-08 | 23 | 24-13
2024-06-09 | 24 | 24-13
2024-06-10 | 24 | 24-13
2024-06-11 | 24 | 24-13
2024-06-12 | 24 | 24-13
2024-06-13 | 24 | 24-13
2024-06-14 | 24 | 24-13
2024-06-15 | 24 | 25-13
2024-06-16 | 25 | 25-13
2024-06-17 | 25 | 25-13
2024-06-18 | 25 | 25-13
2024-06-19 | 25 | 25-13
2024-06-20 | 25 | 25-13
2024-06-21 | 25 | 25-13
2024-06-22 | 25 | 26-13
2024-06-23 | 26 | 26-13
2024-06-24 | 26 | 26-13
2024-06-25 | 26 | 26-13
2024-06-26 | 26 | 26-13
2024-06-27 | 26 | 26-13
2024-06-28 | 26 | 26-13
2024-06-29 | 26 | 27-13
2024-06-30 | 27 | 27-13
2024-07-01 | 27 | 27-13
2024-07-02 | 27 | 27-13
2024-07-03 | 27 | 27-13
2024-07-04 | 27 | 27-13
2024-07-05 | 27 | 27-13
2024-07-06 | 27 | 28-13
2024-07-07 | 28 | 28-13
2024-07-08 | 28 | 28-13
2024-07-09 | 28 | 28-13
2024-07-10 | 28 | 28-13
2024-07-11 | 28 | 28-13
2024-07-12 | 28 | 28-13
2024-07-13 | 28 | 29-13
2024-07-14 | 29 | 29-13
2024-07-15 | 29 | 29-13
2024-07-16 | 29 | 29-13
2024-07-17 | 29 | 29-13
2024-07-18 | 29 | 29-13
2024-07-19 | 29 | 29-13
2024-07-20 | 29 | 30-13
2024-07-21 | 30 | 30-13
2024-07-22 | 30 | 30-13
2024-07-23 | 30 | 30-13
2024-07-24 | 30 | 30-13
2024-07-25 | 30 | 30-13
2024-07-26 | 30 | 30-13
2024-07-27 | 30 | 31-13
2024-07-28 | 31 | 31-13
2024-07-29 | 31 | 31-13
2024-07-30 | 31 | 31-13
2024-07-31 | 31 | 31-13
2024-08-01 | 31 | 31-13
2024-08-02 | 31 | 31-13
2024-08-03 | 31 | 32-13
2024-08-04 | 32 | 32-13
2024-08-05 | 32 | 32-13
2024-08-06 | 32 | 32-13
2024-08-07 | 32 | 32-13
2024-08-08 | 32 | 32-13
2024-08-09 | 32 | 32-13
2024-08-10 | 32 | 33-13
2024-08-11 | 33 | 33-13
2024-08-12 | 33 | 33-13
2024-08-13 | 33 | 33-13
2024-08-14 | 33 | 33-13
2024-08-15 | 33 | 33-13
2024-08-16 | 33 | 33-13
2024-08-17 | 33 | 34-13
2024-08-18 | 34 | 34-13
2024-08-19 | 34 | 34-13
2024-08-20 | 34 | 34-13
2024-08-21 | 34 | 34-13
2024-08-22 | 34 | 34-13
2024-08-23 | 34 | 34-13
2024-08-24 | 34 | 35-13
2024-08-25 | 35 | 35-13
2024-08-26 | 35 | 35-13
2024-08-27 | 35 | 35-13
2024-08-28 | 35 | 35-13
2024-08-29 | 35 | 35-13
2024-08-30 | 35 | 35-13
2024-08-31 | 35 | 36-13
2024-09-01 | 36 | 36-13
2024-09-02 | 36 | 36-13
2024-09-03 | 36 | 36-13
2024-09-04 | 36 | 36-13
2024-09-05 | 36 | 36-13
2024-09-06 | 36 | 36-13
2024-09-07 | 36 | 37-13
2024-09-08 | 37 | 37-13
2024-09-09 | 37 | 37-13
2024-09-10 | 37 | 37-13
2024-09-11 | 37 | 37-13
2024-09-12 | 37 | 37-13
2024-09-13 | 37 | 37-13
2024-09-14 | 37 | 38-13
2024-09-15 | 38 | 38-13
2024-09-16 | 38 | 38-13
2024-09-17 | 38 | 38-13
2024-09-18 | 38 | 38-13
2024-09-19 | 38 | 38-13
2024-09-20 | 38 | 38-13
2024-09-21 | 38 | 39-13
2024-09-22 | 39 | 39-13
2024-09-23 | 39 | 39-13
2024-09-24 | 39 | 39-13
2024-09-25 | 39 | 39-13
2024-09-26 | 39 | 39-13
2024-09-27 | 39 | 39-13
2024-09-28 | 39 | 40-13
2024-09-29 | 40 | 40-13
2024-09-30 | 40 | 40-13
2024-10-01 | 40 | 40-13
2024-10-02 | 40 | 40-13
2024-10-03 | 40 | 40-13
2024-10-04 | 40 | 40-13
2024-10-05 | 40 | 41-13
2024-10-06 | 41 | 41-13
2024-10-07 | 41 | 41-13
2024-10-08 | 41 | 41-13
2024-10-09 | 41 | 41-13
2024-10-10 | 41 | 41-13
2024-10-11 | 41 | 41-13
2024-10-12 | 41 | 42-13
2024-10-13 | 42 | 42-13
2024-10-14 | 42 | 42-13
2024-10-15 | 42 | 42-13
2024-10-16 | 42 | 42-13
2024-10-17 | 42 | 42-13
2024-10-18 | 42 | 42-13
2024-10-19 | 42 | 43-13
2024-10-20 | 43 | 43-13
2024-10-21 | 43 | 43-13
2024-10-22 | 43 | 43-13
2024-10-23 | 43 | 43-13
2024-10-24 | 43 | 43-13
2024-10-25 | 43 | 43-13
2024-10-26 | 43 | 44-13
2024-10-27 | 44 | 44-13
2024-10-28 | 44 | 44-13
2024-10-29 | 44 | 44-13
2024-10-30 | 44 | 44-13
2024-10-31 | 44 | 44-13
2024-11-01 | 44 | 44-13
2024-11-02 | 44 | 45-13
2024-11-03 | 45 | 45-13
2024-11-04 | 45 | 45-13
2024-11-05 | 45 | 45-13
2024-11-06 | 45 | 45-13
2024-11-07 | 45 | 45-13
2024-11-08 | 45 | 45-13
2024-11-09 | 45 | 46-13
2024-11-10 | 46 | 46-13
2024-11-11 | 46 | 46-13
2024-11-12 | 46 | 46-13
2024-11-13 | 46 | 46-13
2024-11-14 | 46 | 46-13
2024-11-15 | 46 | 46-13
2024-11-16 | 46 | 47-13
2024-11-17 | 47 | 47-13
2024-11-18 | 47 | 47-13
2024-11-19 | 47 | 47-13
2024-11-20 | 47 | 47-13
2024-11-21 | 47 | 47-13
2024-11-22 | 47 | 47-13
2024-11-23 | 47 | 48-13
2024-11-24 | 48 | 48-13
2024-11-25 | 48 | 48-13
2024-11-26 | 48 | 48-13
2024-11-27 | 48 | 48-13
2024-11-28 | 48 | 48-13
2024-11-29 | 48 | 48-13
2024-11-30 | 48 | 49-13
2024-12-01 | 49 | 49-13
2024-12-02 | 49 | 49-13
2024-12-03 | 49 | 49-13
2024-12-04 | 49 | 49-13
2024-12-05 | 49 | 49-13
2024-12-06 | 49 | 49-13
2024-12-07 | 49 | 50-13
2024-12-08 | 50 | 50-13
2024-12-09 | 50 | 50-13
2024-12-10 | 50 | 50-13
2024-12-11 | 50 | 50-13
2024-12-12 | 50 | 50-13
2024-12-13 | 50 | 50-13
2024-12-14 | 50 | 51-13
2024-12-15 | 51 | 51-13
2024-12-16 | 51 | 51-13
2024-12-17 | 51 | 51-13
2024-12-18 | 51 | 51-13
2024-12-19 | 51 | 51-13
2024-12-20 | 51 | 51-13
2024-12-21 | 51 | 52-13
2024-12-22 | 52 | 52-13
2024-12-23 | 52 | 52-13
2024-12-24 | 52 | 52-13
2024-12-25 | 52 | 52-13
2024-12-26 | 52 | 52-13
2024-12-27 | 52 | 52-13
2024-12-28 | 52 | 53-13
2024-12-29 | 53 | 53-13
2024-12-30 | 53 | 53-13
2024-12-31 | 53 | 1-14
2025-01-01 | 1 | 1-14
2025-01-02 | 1 | 1-14
2025-01-03 | 1 | 1-14
2025-01-04 | 1 | 2-14
2025-01-05 | 2 | 2-14
2025-01-06 | 2 | 2-14
2025-01-07 | 2 | 2-14
2025-01-08 | 2 | 2-14
2025-01-09 | 2 | 2-14
2025-01-10 | 2 | 2-14
2025-01-11 | 2 | 3-14
2025-01-12 | 3 | 3-14
2025-01-13 | 3 | 3-14
2025-01-14 | 3 | 3-14
2025-01-15 | 3 | 3-14
2025-01-16 | 3 | 3-14
2025-01-17 | 3 | 3-14
2025-01-18 | 3 | 4-14
2025-01-19 | 4 | 4-14
2025-01-20 | 4 | 4-14
2025-01-21 | 4 | 4-14
2025-01-22 | 4 | 4-14
2025-01-23 | 4 | 4-14
2025-01-24 | 4 | 4-14
2025-01-25 | 4 | 5-14
2025-01-26 | 5 | 5-14
2025-01-27 | 5 | 5-14
2025-01-28 | 5 | 5-14
2025-01-29 | 5 | 5-14
2025-01-30 | 5 | 5-14
2025-01-31 | 5 | 5-14
2025-02-01 | 5 | 6-14
2025-02-02 | 6 | 6-14
2025-02-03 | 6 | 6-14
2025-02-04 | 6 | 6-14
2025-02-05 | 6 | 6-14
2025-02-06 | 6 | 6-14
2025-02-07 | 6 | 6-14
2025-02-08 | 6 | 7-14
2025-02-09 | 7 | 7-14
2025-02-10 | 7 | 7-14
2025-02-11 | 7 | 7-14
2025-02-12 | 7 | 7-14
2025-02-13 | 7 | 7-14
2025-02-14 | 7 | 7-14
2025-02-15 | 7 | 8-14
2025-02-16 | 8 | 8-14
2025-02-17 | 8 | 8-14
2025-02-18 | 8 | 8-14
2025-02-19 | 8 | 8-14
2025-02-20 | 8 | 8-14
2025-02-21 | 8 | 8-14
2025-02-22 | 8 | 9-14
2025-02-23 | 9 | 9-14
2025-02-24 | 9 | 9-14
2025-02-25 | 9 | 9-14
2025-02-26 | 9 | 9-14
2025-02-27 | 9 | 9-14
2025-02-28 | 9 | 9-14
2025-03-01 | 9 | 10-14
2025-03-02 | 10 | 10-14
2025-03-03 | 10 | 10-14
2025-03-04 | 10 | 10-14
2025-03-05 | 10 | 10-14
2025-03-06 | 10 | 10-14
2025-03-07 | 10 | 10-14
2025-03-08 | 10 | 11-14
2025-03-09 | 11 | 11-14
2025-03-10 | 11 | 11-14
2025-03-11 | 11 | 11-14
2025-03-12 | 11 | 11-14
2025-03-13 | 11 | 11-14
2025-03-14 | 11 | 11-14
2025-03-15 | 11 | 12-14
2025-03-16 | 12 | 12-14
2025-03-17 | 12 | 12-14
2025-03-18 | 12 | 12-14
2025-03-19 | 12 | 12-14
2025-03-20 | 12 | 12-14
2025-03-21 | 12 | 12-14
2025-03-22 | 12 | 13-14
2025-03-23 | 13 | 13-14
2025-03-24 | 13 | 13-14
2025-03-25 | 13 | 13-14
2025-03-26 | 13 | 13-14
2025-03-27 | 13 | 13-14
2025-03-28 | 13 | 13-14
2025-03-29 | 13 | 14-14
2025-03-30 | 14 | 14-14
2025-03-31 | 14 | 14-14
2025-04-01 | 14 | 14-14
2025-04-02 | 14 | 14-14
2025-04-03 | 14 | 14-14
2025-04-04 | 14 | 14-14
2025-04-05 | 14 | 15-14
2025-04-06 | 15 | 15-14
2025-04-07 | 15 | 15-14
2025-04-08 | 15 | 15-14
2025-04-09 | 15 | 15-14
2025-04-10 | 15 | 15-14
2025-04-11 | 15 | 15-14
2025-04-12 | 15 | 16-14
2025-04-13 | 16 | 16-14
2025-04-14 | 16 | 16-14
2025-04-15 | 16 | 16-14
2025-04-16 | 16 | 16-14
2025-04-17 | 16 | 16-14
2025-04-18 | 16 | 16-14
2025-04-19 | 16 | 17-14
2025-04-20 | 17 | 17-14
2025-04-21 | 17 | 17-14
2025-04-22 | 17 | 17-14
2025-04-23 | 17 | 17-14
2025-04-24 | 17 | 17-14
2025-04-25 | 17 | 17-14
2025-04-26 | 17 | 18-14
2025-04-27 | 18 | 18-14
2025-04-28 | 18 | 18-14
2025-04-29 | 18 | 18-14
2025-04-30 | 18 | 18-14
2025-05-01 | 18 | 18-14
2025-05-02 | 18 | 18-14
2025-05-03 | 18 | 19-14
2025-05-04 | 19 | 19-14
2025-05-05 | 19 | 19-14
2025-05-06 | 19 | 19-14
2025-05-07 | 19 | 19-14
2025-05-08 | 19 | 19-14
2025-05-09 | 19 | 19-14
2025-05-10 | 19 | 20-14
2025-05-11 | 20 | 20-14
2025-05-12 | 20 | 20-14
2025-05-13 | 20 | 20-14
2025-05-14 | 20 | 20-14
2025-05-15 | 20 | 20-14
2025-05-16 | 20 | 20-14
2025-05-17 | 20 | 21-14
2025-05-18 | 21 | 21-14
2025-05-19 | 21 | 21-14
2025-05-20 | 21 | 21-14
2025-05-21 | 21 | 21-14
2025-05-22 | 21 | 21-14
2025-05-23 | 21 | 21-14
2025-05-24 | 21 | 22-14
2025-05-25 | 22 | 22-14
2025-05-26 | 22 | 22-14
2025-05-27 | 22 | 22-14
2025-05-28 | 22 | 22-14
2025-05-29 | 22 | 22-14
2025-05-30 | 22 | 22-14
2025-05-31 | 22 | 23-14
2025-06-01 | 23 | 23-14
2025-06-02 | 23 | 23-14
2025-06-03 | 23 | 23-14
2025-06-04 | 23 | 23-14
2025-06-05 | 23 | 23-14
2025-06-06 | 23 | 23-14
2025-06-07 | 23 | 24-14
2025-06-08 | 24 | 24-14
2025-06-09 | 24 | 24-14
2025-06-10 | 24 | 24-14
2025-06-11 | 24 | 24-14
2025-06-12 | 24 | 24-14
2025-06-13 | 24 | 24-14
2025-06-14 | 24 | 25-14
2025-06-15 | 25 | 25-14
2025-06-16 | 25 | 25-14
2025-06-17 | 25 | 25-14
2025-06-18 | 25 | 25-14
2025-06-19 | 25 | 25-14
2025-06-20 | 25 | 25-14
2025-06-21 | 25 | 26-14
2025-06-22 | 26 | 26-14
2025-06-23 | 26 | 26-14
2025-06-24 | 26 | 26-14
2025-06-25 | 26 | 26-14
2025-06-26 | 26 | 26-14
2025-06-27 | 26 | 26-14
2025-06-28 | 26 | 27-14
2025-06-29 | 27 | 27-14
2025-06-30 | 27 | 27-14
2025-07-01 | 27 | 27-14
2025-07-02 | 27 | 27-14
2025-07-03 | 27 | 27-14
2025-07-04 | 27 | 27-14
2025-07-05 | 27 | 28-14
2025-07-06 | 28 | 28-14
2025-07-07 | 28 | 28-14
2025-07-08 | 28 | 28-14
2025-07-09 | 28 | 28-14
2025-07-10 | 28 | 28-14
2025-07-11 | 28 | 28-14
2025-07-12 | 28 | 29-14
2025-07-13 | 29 | 29-14
2025-07-14 | 29 | 29-14
2025-07-15 | 29 | 29-14
2025-07-16 | 29 | 29-14
2025-07-17 | 29 | 29-14
2025-07-18 | 29 | 29-14
2025-07-19 | 29 | 30-14
2025-07-20 | 30 | 30-14
2025-07-21 | 30 | 30-14
2025-07-22 | 30 | 30-14
2025-07-23 | 30 | 30-14
2025-07-24 | 30 | 30-14
2025-07-25 | 30 | 30-14
2025-07-26 | 30 | 31-14
2025-07-27 | 31 | 31-14
2025-07-28 | 31 | 31-14
2025-07-29 | 31 | 31-14
2025-07-30 | 31 | 31-14
2025-07-31 | 31 | 31-14
2025-08-01 | 31 | 31-14
2025-08-02 | 31 | 32-14
2025-08-03 | 32 | 32-14
2025-08-04 | 32 | 32-14
2025-08-05 | 32 | 32-14
2025-08-06 | 32 | 32-14
2025-08-07 | 32 | 32-14
2025-08-08 | 32 | 32-14
2025-08-09 | 32 | 33-14
2025-08-10 | 33 | 33-14
2025-08-11 | 33 | 33-14
2025-08-12 | 33 | 33-14
2025-08-13 | 33 | 33-14
2025-08-14 | 33 | 33-14
2025-08-15 | 33 | 33-14
2025-08-16 | 33 | 34-14
2025-08-17 | 34 | 34-14
2025-08-18 | 34 | 34-14
2025-08-19 | 34 | 34-14
2025-08-20 | 34 | 34-14
2025-08-21 | 34 | 34-14
2025-08-22 | 34 | 34-14
2025-08-23 | 34 | 35-14
2025-08-24 | 35 | 35-14
2025-08-25 | 35 | 35-14
2025-08-26 | 35 | 35-14
2025-08-27 | 35 | 35-14
2025-08-28 | 35 | 35-14
2025-08-29 | 35 | 35-14
2025-08-30 | 35 | 36-14
2025-08-31 | 36 | 36-14
2025-09-01 | 36 | 36-14
2025-09-02 | 36 | 36-14
2025-09-03 | 36 | 36-14
2025-09-04 | 36 | 36-14
2025-09-05 | 36 | 36-14
2025-09-06 | 36 | 37-14
2025-09-07 | 37 | 37-14
2025-09-08 | 37 | 37-14
2025-09-09 | 37 | 37-14
2025-09-10 | 37 | 37-14
2025-09-11 | 37 | 37-14
2025-09-12 | 37 | 37-14
2025-09-13 | 37 | 38-14
2025-09-14 | 38 | 38-14
2025-09-15 | 38 | 38-14
2025-09-16 | 38 | 38-14
2025-09-17 | 38 | 38-14
2025-09-18 | 38 | 38-14
2025-09-19 | 38 | 38-14
2025-09-20 | 38 | 39-14
2025-09-21 | 39 | 39-14
2025-09-22 | 39 | 39-14
2025-09-23 | 39 | 39-14
2025-09-24 | 39 | 39-14
2025-09-25 | 39 | 39-14
2025-09-26 | 39 | 39-14
2025-09-27 | 39 | 40-14
2025-09-28 | 40 | 40-14
2025-09-29 | 40 | 40-14
2025-09-30 | 40 | 40-14
2025-10-01 | 40 | 40-14
2025-10-02 | 40 | 40-14
2025-10-03 | 40 | 40-14
2025-10-04 | 40 | 41-14
2025-10-05 | 41 | 41-14
2025-10-06 | 41 | 41-14
2025-10-07 | 41 | 41-14
2025-10-08 | 41 | 41-14
2025-10-09 | 41 | 41-14
2025-10-10 | 41 | 41-14
2025-10-11 | 41 | 42-14
2025-10-12 | 42 | 42-14
2025-10-13 | 42 | 42-14
2025-10-14 | 42 | 42-14
2025-10-15 | 42 | 42-14
2025-10-16 | 42 | 42-14
2025-10-17 | 42 | 42-14
2025-10-18 | 42 | 43-14
2025-10-19 | 43 | 43-14
2025-10-20 | 43 | 43-14
2025-10-21 | 43 | 43-14
2025-10-22 | 43 | 43-14
2025-10-23 | 43 | 43-14
2025-10-24 | 43 | 43-14
2025-10-25 | 43 | 44-14
2025-10-26 | 44 | 44-14
2025-10-27 | 44 | 44-14
2025-10-28 | 44 | 44-14
2025-10-29 | 44 | 44-14
2025-10-30 | 44 | 44-14
2025-10-31 | 44 | 44-14
2025-11-01 | 44 | 45-14
2025-11-02 | 45 | 45-14
2025-11-03 | 45 | 45-14
2025-11-04 | 45 | 45-14
2025-11-05 | 45 | 45-14
2025-11-06 | 45 | 45-14
2025-11-07 | 45 | 45-14
2025-11-08 | 45 | 46-14
2025-11-09 | 46 | 46-14
2025-11-10 | 46 | 46-14
2025-11-11 | 46 | 46-14
2025-11-12 | 46 | 46-14
2025-11-13 | 46 | 46-14
2025-11-14 | 46 | 46-14
2025-11-15 | 46 | 47-14
2025-11-16 | 47 | 47-14
2025-11-17 | 47 | 47-14
2025-11-18 | 47 | 47-14
2025-11-19 | 47 | 47-14
2025-11-20 | 47 | 47-14
2025-11-21 | 47 | 47-14
2025-11-22 | 47 | 48-14
2025-11-23 | 48 | 48-14
2025-11-24 | 48 | 48-14
2025-11-25 | 48 | 48-14
2025-11-26 | 48 | 48-14
2025-11-27 | 48 | 48-14
2025-11-28 | 48 | 48-14
2025-11-29 | 48 | 49-14
2025-11-30 | 49 | 49-14
2025-12-01 | 49 | 49-14
2025-12-02 | 49 | 49-14
2025-12-03 | 49 | 49-14
2025-12-04 | 49 | 49-14
2025-12-05 | 49 | 49-14
2025-12-06 | 49 | 50-14
2025-12-07 | 50 | 50-14
2025-12-08 | 50 | 50-14
2025-12-09 | 50 | 50-14
2025-12-10 | 50 | 50-14
2025-12-11 | 50 | 50-14
2025-12-12 | 50 | 50-14
2025-12-13 | 50 | 51-14
2025-12-14 | 51 | 51-14
2025-12-15 | 51 | 51-14
2025-12-16 | 51 | 51-14
2025-12-17 | 51 | 51-14
2025-12-18 | 51 | 51-14
2025-12-19 | 51 | 51-14
2025-12-20 | 51 | 52-14
2025-12-21 | 52 | 52-14
2025-12-22 | 52 | 52-14
2025-12-23 | 52 | 52-14
2025-12-24 | 52 | 52-14
2025-12-25 | 52 | 52-14
2025-12-26 | 52 | 52-14
2025-12-27 | 52 | 53-14
2025-12-28 | 53 | 53-14
2025-12-29 | 53 | 53-14
2025-12-30 | 53 | 53-14
2025-12-31 | 1 | 1-15
2026-01-01 | 1 | 1-15
2026-01-02 | 1 | 1-15
2026-01-03 | 2 | 2-15
2026-01-04 | 2 | 2-15
2026-01-05 | 2 | 2-15
2026-01-06 | 2 | 2-15
2026-01-07 | 2 | 2-15
2026-01-08 | 2 | 2-15
2026-01-09 | 2 | 2-15
2026-01-10 | 3 | 3-15
2026-01-11 | 3 | 3-15
2026-01-12 | 3 | 3-15
2026-01-13 | 3 | 3-15
2026-01-14 | 3 | 3-15
2026-01-15 | 3 | 3-15
2026-01-16 | 3 | 3-15
2026-01-17 | 4 | 4-15
2026-01-18 | 4 | 4-15
2026-01-19 | 4 | 4-15
2026-01-20 | 4 | 4-15
2026-01-21 | 4 | 4-15
2026-01-22 | 4 | 4-15
2026-01-23 | 4 | 4-15
2026-01-24 | 5 | 5-15
2026-01-25 | 5 | 5-15
2026-01-26 | 5 | 5-15
2026-01-27 | 5 | 5-15
2026-01-28 | 5 | 5-15
2026-01-29 | 5 | 5-15
2026-01-30 | 5 | 5-15
2026-01-31 | 6 | 6-15
2026-02-01 | 6 | 6-15
2026-02-02 | 6 | 6-15
2026-02-03 | 6 | 6-15
2026-02-04 | 6 | 6-15
2026-02-05 | 6 | 6-15
2026-02-06 | 6 | 6-15
2026-02-07 | 7 | 7-15
2026-02-08 | 7 | 7-15
2026-02-09 | 7 | 7-15
2026-02-10 | 7 | 7-15
2026-02-11 | 7 | 7-15
2026-02-12 | 7 | 7-15
2026-02-13 | 7 | 7-15
2026-02-14 | 8 | 8-15
2026-02-15 | 8 | 8-15
2026-02-16 | 8 | 8-15
2026-02-17 | 8 | 8-15
2026-02-18 | 8 | 8-15
2026-02-19 | 8 | 8-15
2026-02-20 | 8 | 8-15
2026-02-21 | 9 | 9-15
2026-02-22 | 9 | 9-15
2026-02-23 | 9 | 9-15
2026-02-24 | 9 | 9-15
2026-02-25 | 9 | 9-15
2026-02-26 | 9 | 9-15
2026-02-27 | 9 | 9-15
2026-02-28 | 10 | 10-15
2026-03-01 | 10 | 10-15
2026-03-02 | 10 | 10-15
2026-03-03 | 10 | 10-15
2026-03-04 | 10 | 10-15
2026-03-05 | 10 | 10-15
2026-03-06 | 10 | 10-15
2026-03-07 | 11 | 11-15
2026-03-08 | 11 | 11-15
2026-03-09 | 11 | 11-15
2026-03-10 | 11 | 11-15
2026-03-11 | 11 | 11-15
2026-03-12 | 11 | 11-15
2026-03-13 | 11 | 11-15
2026-03-14 | 12 | 12-15
2026-03-15 | 12 | 12-15
2026-03-16 | 12 | 12-15
2026-03-17 | 12 | 12-15
2026-03-18 | 12 | 12-15
2026-03-19 | 12 | 12-15
2026-03-20 | 12 | 12-15
2026-03-21 | 13 | 13-15
2026-03-22 | 13 | 13-15
2026-03-23 | 13 | 13-15
2026-03-24 | 13 | 13-15
2026-03-25 | 13 | 13-15
2026-03-26 | 13 | 13-15
2026-03-27 | 13 | 13-15
2026-03-28 | 14 | 14-15
2026-03-29 | 14 | 14-15
2026-03-30 | 14 | 14-15
2026-03-31 | 14 | 14-15
2026-04-01 | 14 | 14-15
2026-04-02 | 14 | 14-15
2026-04-03 | 14 | 14-15
2026-04-04 | 15 | 15-15
2026-04-05 | 15 | 15-15
2026-04-06 | 15 | 15-15
2026-04-07 | 15 | 15-15
2026-04-08 | 15 | 15-15
2026-04-09 | 15 | 15-15
2026-04-10 | 15 | 15-15
2026-04-11 | 16 | 16-15
2026-04-12 | 16 | 16-15
2026-04-13 | 16 | 16-15
2026-04-14 | 16 | 16-15
2026-04-15 | 16 | 16-15
2026-04-16 | 16 | 16-15
2026-04-17 | 16 | 16-15
2026-04-18 | 17 | 17-15
2026-04-19 | 17 | 17-15
2026-04-20 | 17 | 17-15
2026-04-21 | 17 | 17-15
2026-04-22 | 17 | 17-15
2026-04-23 | 17 | 17-15
2026-04-24 | 17 | 17-15
2026-04-25 | 18 | 18-15
2026-04-26 | 18 | 18-15
2026-04-27 | 18 | 18-15
2026-04-28 | 18 | 18-15
2026-04-29 | 18 | 18-15
2026-04-30 | 18 | 18-15
2026-05-01 | 18 | 18-15
2026-05-02 | 19 | 19-15
2026-05-03 | 19 | 19-15
2026-05-04 | 19 | 19-15
2026-05-05 | 19 | 19-15
2026-05-06 | 19 | 19-15
2026-05-07 | 19 | 19-15
2026-05-08 | 19 | 19-15
2026-05-09 | 20 | 20-15
2026-05-10 | 20 | 20-15
2026-05-11 | 20 | 20-15
2026-05-12 | 20 | 20-15
2026-05-13 | 20 | 20-15
2026-05-14 | 20 | 20-15
2026-05-15 | 20 | 20-15
2026-05-16 | 21 | 21-15
2026-05-17 | 21 | 21-15
2026-05-18 | 21 | 21-15
2026-05-19 | 21 | 21-15
2026-05-20 | 21 | 21-15
2026-05-21 | 21 | 21-15
2026-05-22 | 21 | 21-15
2026-05-23 | 22 | 22-15
2026-05-24 | 22 | 22-15
2026-05-25 | 22 | 22-15
2026-05-26 | 22 | 22-15
2026-05-27 | 22 | 22-15
2026-05-28 | 22 | 22-15
2026-05-29 | 22 | 22-15
2026-05-30 | 23 | 23-15
2026-05-31 | 23 | 23-15
2026-06-01 | 23 | 23-15
2026-06-02 | 23 | 23-15
2026-06-03 | 23 | 23-15
2026-06-04 | 23 | 23-15
2026-06-05 | 23 | 23-15
2026-06-06 | 24 | 24-15
2026-06-07 | 24 | 24-15
2026-06-08 | 24 | 24-15
2026-06-09 | 24 | 24-15
2026-06-10 | 24 | 24-15
2026-06-11 | 24 | 24-15
2026-06-12 | 24 | 24-15
2026-06-13 | 25 | 25-15
2026-06-14 | 25 | 25-15
2026-06-15 | 25 | 25-15
2026-06-16 | 25 | 25-15
2026-06-17 | 25 | 25-15
2026-06-18 | 25 | 25-15
2026-06-19 | 25 | 25-15
2026-06-20 | 26 | 26-15
2026-06-21 | 26 | 26-15
2026-06-22 | 26 | 26-15
2026-06-23 | 26 | 26-15
2026-06-24 | 26 | 26-15
2026-06-25 | 26 | 26-15
2026-06-26 | 26 | 26-15
2026-06-27 | 27 | 27-15
2026-06-28 | 27 | 27-15
2026-06-29 | 27 | 27-15
2026-06-30 | 27 | 27-15
2026-07-01 | 27 | 27-15
2026-07-02 | 27 | 27-15
2026-07-03 | 27 | 27-15
2026-07-04 | 28 | 28-15
2026-07-05 | 28 | 28-15
2026-07-06 | 28 | 28-15
2026-07-07 | 28 | 28-15
2026-07-08 | 28 | 28-15
2026-07-09 | 28 | 28-15
2026-07-10 | 28 | 28-15
2026-07-11 | 29 | 29-15
2026-07-12 | 29 | 29-15
2026-07-13 | 29 | 29-15
2026-07-14 | 29 | 29-15
2026-07-15 | 29 | 29-15
2026-07-16 | 29 | 29-15
2026-07-17 | 29 | 29-15
2026-07-18 | 30 | 30-15
2026-07-19 | 30 | 30-15
2026-07-20 | 30 | 30-15
2026-07-21 | 30 | 30-15
2026-07-22 | 30 | 30-15
2026-07-23 | 30 | 30-15
2026-07-24 | 30 | 30-15
2026-07-25 | 31 | 31-15
2026-07-26 | 31 | 31-15
2026-07-27 | 31 | 31-15
2026-07-28 | 31 | 31-15
2026-07-29 | 31 | 31-15
2026-07-30 | 31 | 31-15
2026-07-31 | 31 | 31-15
2026-08-01 | 32 | 32-15
2026-08-02 | 32 | 32-15
2026-08-03 | 32 | 32-15
2026-08-04 | 32 | 32-15
2026-08-05 | 32 | 32-15
2026-08-06 | 32 | 32-15
2026-08-07 | 32 | 32-15
2026-08-08 | 33 | 33-15
2026-08-09 | 33 | 33-15
2026-08-10 | 33 | 33-15
2026-08-11 | 33 | 33-15
2026-08-12 | 33 | 33-15
2026-08-13 | 33 | 33-15
2026-08-14 | 33 | 33-15
2026-08-15 | 34 | 34-15
2026-08-16 | 34 | 34-15
2026-08-17 | 34 | 34-15
2026-08-18 | 34 | 34-15
2026-08-19 | 34 | 34-15
2026-08-20 | 34 | 34-15
2026-08-21 | 34 | 34-15
2026-08-22 | 35 | 35-15
2026-08-23 | 35 | 35-15
2026-08-24 | 35 | 35-15
2026-08-25 | 35 | 35-15
2026-08-26 | 35 | 35-15
2026-08-27 | 35 | 35-15
2026-08-28 | 35 | 35-15
2026-08-29 | 36 | 36-15
2026-08-30 | 36 | 36-15
2026-08-31 | 36 | 36-15
2026-09-01 | 36 | 36-15
2026-09-02 | 36 | 36-15
2026-09-03 | 36 | 36-15
2026-09-04 | 36 | 36-15
2026-09-05 | 37 | 37-15
2026-09-06 | 37 | 37-15
2026-09-07 | 37 | 37-15
2026-09-08 | 37 | 37-15
2026-09-09 | 37 | 37-15
2026-09-10 | 37 | 37-15
2026-09-11 | 37 | 37-15
2026-09-12 | 38 | 38-15
2026-09-13 | 38 | 38-15
2026-09-14 | 38 | 38-15
2026-09-15 | 38 | 38-15
2026-09-16 | 38 | 38-15
2026-09-17 | 38 | 38-15
2026-09-18 | 38 | 38-15
2026-09-19 | 39 | 39-15
2026-09-20 | 39 | 39-15
2026-09-21 | 39 | 39-15
2026-09-22 | 39 | 39-15
2026-09-23 | 39 | 39-15
2026-09-24 | 39 | 39-15
2026-09-25 | 39 | 39-15
2026-09-26 | 40 | 40-15
2026-09-27 | 40 | 40-15
2026-09-28 | 40 | 40-15
2026-09-29 | 40 | 40-15
2026-09-30 | 40 | 40-15
2026-10-01 | 40 | 40-15
2026-10-02 | 40 | 40-15
2026-10-03 | 41 | 41-15
2026-10-04 | 41 | 41-15
2026-10-05 | 41 | 41-15
2026-10-06 | 41 | 41-15
2026-10-07 | 41 | 41-15
2026-10-08 | 41 | 41-15
2026-10-09 | 41 | 41-15
2026-10-10 | 42 | 42-15
2026-10-11 | 42 | 42-15
2026-10-12 | 42 | 42-15
2026-10-13 | 42 | 42-15
2026-10-14 | 42 | 42-15
2026-10-15 | 42 | 42-15
2026-10-16 | 42 | 42-15
2026-10-17 | 43 | 43-15
2026-10-18 | 43 | 43-15
2026-10-19 | 43 | 43-15
2026-10-20 | 43 | 43-15
2026-10-21 | 43 | 43-15
2026-10-22 | 43 | 43-15
2026-10-23 | 43 | 43-15
2026-10-24 | 44 | 44-15
2026-10-25 | 44 | 44-15
2026-10-26 | 44 | 44-15
2026-10-27 | 44 | 44-15
2026-10-28 | 44 | 44-15
2026-10-29 | 44 | 44-15
2026-10-30 | 44 | 44-15
2026-10-31 | 45 | 45-15
2026-11-01 | 45 | 45-15
2026-11-02 | 45 | 45-15
2026-11-03 | 45 | 45-15
2026-11-04 | 45 | 45-15
2026-11-05 | 45 | 45-15
2026-11-06 | 45 | 45-15
2026-11-07 | 46 | 46-15
2026-11-08 | 46 | 46-15
2026-11-09 | 46 | 46-15
2026-11-10 | 46 | 46-15
2026-11-11 | 46 | 46-15
2026-11-12 | 46 | 46-15
2026-11-13 | 46 | 46-15
2026-11-14 | 47 | 47-15
2026-11-15 | 47 | 47-15
2026-11-16 | 47 | 47-15
2026-11-17 | 47 | 47-15
2026-11-18 | 47 | 47-15
2026-11-19 | 47 | 47-15
2026-11-20 | 47 | 47-15
2026-11-21 | 48 | 48-15
2026-11-22 | 48 | 48-15
2026-11-23 | 48 | 48-15
2026-11-24 | 48 | 48-15
2026-11-25 | 48 | 48-15
2026-11-26 | 48 | 48-15
2026-11-27 | 48 | 48-15
2026-11-28 | 49 | 49-15
2026-11-29 | 49 | 49-15
2026-11-30 | 49 | 49-15
2026-12-01 | 49 | 49-15
2026-12-02 | 49 | 49-15
2026-12-03 | 49 | 49-15
2026-12-04 | 49 | 49-15
2026-12-05 | 50 | 50-15
2026-12-06 | 50 | 50-15
2026-12-07 | 50 | 50-15
2026-12-08 | 50 | 50-15
2026-12-09 | 50 | 50-15
2026-12-10 | 50 | 50-15
2026-12-11 | 50 | 50-15
2026-12-12 | 51 | 51-15
2026-12-13 | 51 | 51-15
2026-12-14 | 51 | 51-15
2026-12-15 | 51 | 51-15
2026-12-16 | 51 | 51-15
2026-12-17 | 51 | 51-15
2026-12-18 | 51 | 51-15
2026-12-19 | 52 | 52-15
2026-12-20 | 52 | 52-15
2026-12-21 | 52 | 52-15
2026-12-22 | 52 | 52-15
2026-12-23 | 52 | 52-15
2026-12-24 | 52 | 52-15
2026-12-25 | 52 | 52-15
2026-12-26 | 53 | 53-15
2026-12-27 | 53 | 53-15
2026-12-28 | 53 | 53-15
2026-12-29 | 53 | 53-15
2026-12-30 | 53 | 53-15
2026-12-31 | 1 | 1-16
2027-01-01 | 1 | 1-16
2027-01-02 | 1 | 1-16
2027-01-03 | 2 | 2-16
2027-01-04 | 2 | 2-16
2027-01-05 | 2 | 2-16
2027-01-06 | 2 | 2-16
2027-01-07 | 2 | 2-16
2027-01-08 | 2 | 2-16
2027-01-09 | 2 | 2-16
2027-01-10 | 3 | 3-16
2027-01-11 | 3 | 3-16
2027-01-12 | 3 | 3-16
2027-01-13 | 3 | 3-16
2027-01-14 | 3 | 3-16
2027-01-15 | 3 | 3-16
2027-01-16 | 3 | 3-16
2027-01-17 | 4 | 4-16
2027-01-18 | 4 | 4-16
2027-01-19 | 4 | 4-16
2027-01-20 | 4 | 4-16
2027-01-21 | 4 | 4-16
2027-01-22 | 4 | 4-16
2027-01-23 | 4 | 4-16
2027-01-24 | 5 | 5-16
2027-01-25 | 5 | 5-16
2027-01-26 | 5 | 5-16
2027-01-27 | 5 | 5-16
2027-01-28 | 5 | 5-16
2027-01-29 | 5 | 5-16
2027-01-30 | 5 | 5-16
2027-01-31 | 6 | 6-16
2027-02-01 | 6 | 6-16
2027-02-02 | 6 | 6-16
2027-02-03 | 6 | 6-16
2027-02-04 | 6 | 6-16
2027-02-05 | 6 | 6-16
2027-02-06 | 6 | 6-16
2027-02-07 | 7 | 7-16
2027-02-08 | 7 | 7-16
2027-02-09 | 7 | 7-16
2027-02-10 | 7 | 7-16
2027-02-11 | 7 | 7-16
2027-02-12 | 7 | 7-16
2027-02-13 | 7 | 7-16
2027-02-14 | 8 | 8-16
2027-02-15 | 8 | 8-16
2027-02-16 | 8 | 8-16
2027-02-17 | 8 | 8-16
2027-02-18 | 8 | 8-16
2027-02-19 | 8 | 8-16
2027-02-20 | 8 | 8-16
2027-02-21 | 9 | 9-16
2027-02-22 | 9 | 9-16
2027-02-23 | 9 | 9-16
2027-02-24 | 9 | 9-16
2027-02-25 | 9 | 9-16
2027-02-26 | 9 | 9-16
2027-02-27 | 9 | 9-16
2027-02-28 | 10 | 10-16
2027-03-01 | 10 | 10-16
2027-03-02 | 10 | 10-16
2027-03-03 | 10 | 10-16
2027-03-04 | 10 | 10-16
2027-03-05 | 10 | 10-16
2027-03-06 | 10 | 10-16
2027-03-07 | 11 | 11-16
2027-03-08 | 11 | 11-16
2027-03-09 | 11 | 11-16
2027-03-10 | 11 | 11-16
2027-03-11 | 11 | 11-16
2027-03-12 | 11 | 11-16
2027-03-13 | 11 | 11-16
2027-03-14 | 12 | 12-16
2027-03-15 | 12 | 12-16
2027-03-16 | 12 | 12-16
2027-03-17 | 12 | 12-16
2027-03-18 | 12 | 12-16
2027-03-19 | 12 | 12-16
2027-03-20 | 12 | 12-16
2027-03-21 | 13 | 13-16
2027-03-22 | 13 | 13-16
2027-03-23 | 13 | 13-16
2027-03-24 | 13 | 13-16
2027-03-25 | 13 | 13-16
2027-03-26 | 13 | 13-16
2027-03-27 | 13 | 13-16
2027-03-28 | 14 | 14-16
2027-03-29 | 14 | 14-16
2027-03-30 | 14 | 14-16
2027-03-31 | 14 | 14-16
2027-04-01 | 14 | 14-16
2027-04-02 | 14 | 14-16
2027-04-03 | 14 | 14-16
2027-04-04 | 15 | 15-16
2027-04-05 | 15 | 15-16
2027-04-06 | 15 | 15-16
2027-04-07 | 15 | 15-16
2027-04-08 | 15 | 15-16
2027-04-09 | 15 | 15-16
2027-04-10 | 15 | 15-16
2027-04-11 | 16 | 16-16
2027-04-12 | 16 | 16-16
2027-04-13 | 16 | 16-16
2027-04-14 | 16 | 16-16
2027-04-15 | 16 | 16-16
2027-04-16 | 16 | 16-16
2027-04-17 | 16 | 16-16
2027-04-18 | 17 | 17-16
2027-04-19 | 17 | 17-16
2027-04-20 | 17 | 17-16
2027-04-21 | 17 | 17-16
2027-04-22 | 17 | 17-16
2027-04-23 | 17 | 17-16
2027-04-24 | 17 | 17-16
2027-04-25 | 18 | 18-16
2027-04-26 | 18 | 18-16
2027-04-27 | 18 | 18-16
2027-04-28 | 18 | 18-16
2027-04-29 | 18 | 18-16
2027-04-30 | 18 | 18-16
2027-05-01 | 18 | 18-16
2027-05-02 | 19 | 19-16
2027-05-03 | 19 | 19-16
2027-05-04 | 19 | 19-16
2027-05-05 | 19 | 19-16
2027-05-06 | 19 | 19-16
2027-05-07 | 19 | 19-16
2027-05-08 | 19 | 19-16
2027-05-09 | 20 | 20-16
2027-05-10 | 20 | 20-16
2027-05-11 | 20 | 20-16
2027-05-12 | 20 | 20-16
2027-05-13 | 20 | 20-16
2027-05-14 | 20 | 20-16
2027-05-15 | 20 | 20-16
2027-05-16 | 21 | 21-16
2027-05-17 | 21 | 21-16
2027-05-18 | 21 | 21-16
2027-05-19 | 21 | 21-16
2027-05-20 | 21 | 21-16
2027-05-21 | 21 | 21-16
2027-05-22 | 21 | 21-16
2027-05-23 | 22 | 22-16
2027-05-24 | 22 | 22-16
2027-05-25 | 22 | 22-16
2027-05-26 | 22 | 22-16
2027-05-27 | 22 | 22-16
2027-05-28 | 22 | 22-16
2027-05-29 | 22 | 22-16
2027-05-30 | 23 | 23-16
2027-05-31 | 23 | 23-16
2027-06-01 | 23 | 23-16
2027-06-02 | 23 | 23-16
2027-06-03 | 23 | 23-16
2027-06-04 | 23 | 23-16
2027-06-05 | 23 | 23-16
2027-06-06 | 24 | 24-16
2027-06-07 | 24 | 24-16
2027-06-08 | 24 | 24-16
2027-06-09 | 24 | 24-16
2027-06-10 | 24 | 24-16
2027-06-11 | 24 | 24-16
2027-06-12 | 24 | 24-16
2027-06-13 | 25 | 25-16
2027-06-14 | 25 | 25-16
2027-06-15 | 25 | 25-16
2027-06-16 | 25 | 25-16
2027-06-17 | 25 | 25-16
2027-06-18 | 25 | 25-16
2027-06-19 | 25 | 25-16
2027-06-20 | 26 | 26-16
2027-06-21 | 26 | 26-16
2027-06-22 | 26 | 26-16
2027-06-23 | 26 | 26-16
2027-06-24 | 26 | 26-16
2027-06-25 | 26 | 26-16
2027-06-26 | 26 | 26-16
2027-06-27 | 27 | 27-16
2027-06-28 | 27 | 27-16
2027-06-29 | 27 | 27-16
2027-06-30 | 27 | 27-16
2027-07-01 | 27 | 27-16
2027-07-02 | 27 | 27-16
2027-07-03 | 27 | 27-16
2027-07-04 | 28 | 28-16
2027-07-05 | 28 | 28-16
2027-07-06 | 28 | 28-16
2027-07-07 | 28 | 28-16
2027-07-08 | 28 | 28-16
2027-07-09 | 28 | 28-16
2027-07-10 | 28 | 28-16
2027-07-11 | 29 | 29-16
2027-07-12 | 29 | 29-16
2027-07-13 | 29 | 29-16
2027-07-14 | 29 | 29-16
2027-07-15 | 29 | 29-16
2027-07-16 | 29 | 29-16
2027-07-17 | 29 | 29-16
2027-07-18 | 30 | 30-16
2027-07-19 | 30 | 30-16
2027-07-20 | 30 | 30-16
2027-07-21 | 30 | 30-16
2027-07-22 | 30 | 30-16
2027-07-23 | 30 | 30-16
2027-07-24 | 30 | 30-16
2027-07-25 | 31 | 31-16
2027-07-26 | 31 | 31-16
2027-07-27 | 31 | 31-16
2027-07-28 | 31 | 31-16
2027-07-29 | 31 | 31-16
2027-07-30 | 31 | 31-16
2027-07-31 | 31 | 31-16
2027-08-01 | 32 | 32-16
2027-08-02 | 32 | 32-16
2027-08-03 | 32 | 32-16
2027-08-04 | 32 | 32-16
2027-08-05 | 32 | 32-16
2027-08-06 | 32 | 32-16
2027-08-07 | 32 | 32-16
2027-08-08 | 33 | 33-16
2027-08-09 | 33 | 33-16
2027-08-10 | 33 | 33-16
2027-08-11 | 33 | 33-16
2027-08-12 | 33 | 33-16
2027-08-13 | 33 | 33-16
2027-08-14 | 33 | 33-16
2027-08-15 | 34 | 34-16
2027-08-16 | 34 | 34-16
2027-08-17 | 34 | 34-16
2027-08-18 | 34 | 34-16
2027-08-19 | 34 | 34-16
2027-08-20 | 34 | 34-16
2027-08-21 | 34 | 34-16
2027-08-22 | 35 | 35-16
2027-08-23 | 35 | 35-16
2027-08-24 | 35 | 35-16
2027-08-25 | 35 | 35-16
2027-08-26 | 35 | 35-16
2027-08-27 | 35 | 35-16
2027-08-28 | 35 | 35-16
2027-08-29 | 36 | 36-16
2027-08-30 | 36 | 36-16
2027-08-31 | 36 | 36-16
2027-09-01 | 36 | 36-16
2027-09-02 | 36 | 36-16
2027-09-03 | 36 | 36-16
2027-09-04 | 36 | 36-16
2027-09-05 | 37 | 37-16
2027-09-06 | 37 | 37-16
2027-09-07 | 37 | 37-16
2027-09-08 | 37 | 37-16
2027-09-09 | 37 | 37-16
2027-09-10 | 37 | 37-16
2027-09-11 | 37 | 37-16
2027-09-12 | 38 | 38-16
2027-09-13 | 38 | 38-16
2027-09-14 | 38 | 38-16
2027-09-15 | 38 | 38-16
2027-09-16 | 38 | 38-16
2027-09-17 | 38 | 38-16
2027-09-18 | 38 | 38-16
2027-09-19 | 39 | 39-16
2027-09-20 | 39 | 39-16
2027-09-21 | 39 | 39-16
2027-09-22 | 39 | 39-16
2027-09-23 | 39 | 39-16
2027-09-24 | 39 | 39-16
2027-09-25 | 39 | 39-16
2027-09-26 | 40 | 40-16
2027-09-27 | 40 | 40-16
2027-09-28 | 40 | 40-16
2027-09-29 | 40 | 40-16
2027-09-30 | 40 | 40-16
2027-10-01 | 40 | 40-16
2027-10-02 | 40 | 40-16
2027-10-03 | 41 | 41-16
2027-10-04 | 41 | 41-16
2027-10-05 | 41 | 41-16
2027-10-06 | 41 | 41-16
2027-10-07 | 41 | 41-16
2027-10-08 | 41 | 41-16
2027-10-09 | 41 | 41-16
2027-10-10 | 42 | 42-16
2027-10-11 | 42 | 42-16
2027-10-12 | 42 | 42-16
2027-10-13 | 42 | 42-16
2027-10-14 | 42 | 42-16
2027-10-15 | 42 | 42-16
2027-10-16 | 42 | 42-16
2027-10-17 | 43 | 43-16
2027-10-18 | 43 | 43-16
2027-10-19 | 43 | 43-16
2027-10-20 | 43 | 43-16
2027-10-21 | 43 | 43-16
2027-10-22 | 43 | 43-16
2027-10-23 | 43 | 43-16
2027-10-24 | 44 | 44-16
2027-10-25 | 44 | 44-16
2027-10-26 | 44 | 44-16
2027-10-27 | 44 | 44-16
2027-10-28 | 44 | 44-16
2027-10-29 | 44 | 44-16
2027-10-30 | 44 | 44-16
2027-10-31 | 45 | 45-16
2027-11-01 | 45 | 45-16
2027-11-02 | 45 | 45-16
2027-11-03 | 45 | 45-16
2027-11-04 | 45 | 45-16
2027-11-05 | 45 | 45-16
2027-11-06 | 45 | 45-16
2027-11-07 | 46 | 46-16
2027-11-08 | 46 | 46-16
2027-11-09 | 46 | 46-16
2027-11-10 | 46 | 46-16
2027-11-11 | 46 | 46-16
2027-11-12 | 46 | 46-16
2027-11-13 | 46 | 46-16
2027-11-14 | 47 | 47-16
2027-11-15 | 47 | 47-16
2027-11-16 | 47 | 47-16
2027-11-17 | 47 | 47-16
2027-11-18 | 47 | 47-16
2027-11-19 | 47 | 47-16
2027-11-20 | 47 | 47-16
2027-11-21 | 48 | 48-16
2027-11-22 | 48 | 48-16
2027-11-23 | 48 | 48-16
2027-11-24 | 48 | 48-16
2027-11-25 | 48 | 48-16
2027-11-26 | 48 | 48-16
2027-11-27 | 48 | 48-16
2027-11-28 | 49 | 49-16
2027-11-29 | 49 | 49-16
2027-11-30 | 49 | 49-16
2027-12-01 | 49 | 49-16
2027-12-02 | 49 | 49-16
2027-12-03 | 49 | 49-16
2027-12-04 | 49 | 49-16
2027-12-05 | 50 | 50-16
2027-12-06 | 50 | 50-16
2027-12-07 | 50 | 50-16
2027-12-08 | 50 | 50-16
2027-12-09 | 50 | 50-16
2027-12-10 | 50 | 50-16
2027-12-11 | 50 | 50-16
2027-12-12 | 51 | 51-16
2027-12-13 | 51 | 51-16
2027-12-14 | 51 | 51-16
2027-12-15 | 51 | 51-16
2027-12-16 | 51 | 51-16
2027-12-17 | 51 | 51-16
2027-12-18 | 51 | 51-16
2027-12-19 | 52 | 52-16
2027-12-20 | 52 | 52-16
2027-12-21 | 52 | 52-16
2027-12-22 | 52 | 52-16
2027-12-23 | 52 | 52-16
2027-12-24 | 52 | 52-16
2027-12-25 | 52 | 52-16
2027-12-26 | 53 | 53-16
2027-12-27 | 53 | 53-16
2027-12-28 | 53 | 53-16
2027-12-29 | 53 | 53-16
2027-12-30 | 53 | 53-16
2027-12-31 | 53 | 53-16
2028-01-01 | 53 | 53-16
2028-01-02 | 1 | 1-17
2028-01-03 | 1 | 1-17
2028-01-04 | 1 | 1-17
2028-01-05 | 1 | 1-17
2028-01-06 | 1 | 1-17
2028-01-07 | 1 | 1-17
2028-01-08 | 1 | 1-17
2028-01-09 | 2 | 2-17
2028-01-10 | 2 | 2-17
2028-01-11 | 2 | 2-17
2028-01-12 | 2 | 2-17
2028-01-13 | 2 | 2-17
2028-01-14 | 2 | 2-17
2028-01-15 | 2 | 2-17
2028-01-16 | 3 | 3-17
2028-01-17 | 3 | 3-17
2028-01-18 | 3 | 3-17
2028-01-19 | 3 | 3-17
2028-01-20 | 3 | 3-17
2028-01-21 | 3 | 3-17
2028-01-22 | 3 | 3-17
2028-01-23 | 4 | 4-17
2028-01-24 | 4 | 4-17
2028-01-25 | 4 | 4-17
2028-01-26 | 4 | 4-17
2028-01-27 | 4 | 4-17
2028-01-28 | 4 | 4-17
2028-01-29 | 4 | 4-17
2028-01-30 | 5 | 5-17
2028-01-31 | 5 | 5-17
2028-02-01 | 5 | 5-17
2028-02-02 | 5 | 5-17
2028-02-03 | 5 | 5-17
2028-02-04 | 5 | 5-17
2028-02-05 | 5 | 5-17
2028-02-06 | 6 | 6-17
2028-02-07 | 6 | 6-17
2028-02-08 | 6 | 6-17
2028-02-09 | 6 | 6-17
2028-02-10 | 6 | 6-17
2028-02-11 | 6 | 6-17
2028-02-12 | 6 | 6-17
2028-02-13 | 7 | 7-17
2028-02-14 | 7 | 7-17
2028-02-15 | 7 | 7-17
2028-02-16 | 7 | 7-17
2028-02-17 | 7 | 7-17
2028-02-18 | 7 | 7-17
2028-02-19 | 7 | 7-17
2028-02-20 | 8 | 8-17
2028-02-21 | 8 | 8-17
2028-02-22 | 8 | 8-17
2028-02-23 | 8 | 8-17
2028-02-24 | 8 | 8-17
2028-02-25 | 8 | 8-17
2028-02-26 | 8 | 8-17
2028-02-27 | 9 | 9-17
2028-02-28 | 9 | 9-17
2028-02-29 | 9 | 9-17
2028-03-01 | 9 | 9-17
2028-03-02 | 9 | 9-17
2028-03-03 | 9 | 9-17
2028-03-04 | 9 | 9-17
2028-03-05 | 10 | 10-17
2028-03-06 | 10 | 10-17
2028-03-07 | 10 | 10-17
2028-03-08 | 10 | 10-17
2028-03-09 | 10 | 10-17
2028-03-10 | 10 | 10-17
2028-03-11 | 10 | 10-17
2028-03-12 | 11 | 11-17
2028-03-13 | 11 | 11-17
2028-03-14 | 11 | 11-17
2028-03-15 | 11 | 11-17
2028-03-16 | 11 | 11-17
2028-03-17 | 11 | 11-17
2028-03-18 | 11 | 11-17
2028-03-19 | 12 | 12-17
2028-03-20 | 12 | 12-17
2028-03-21 | 12 | 12-17
2028-03-22 | 12 | 12-17
2028-03-23 | 12 | 12-17
2028-03-24 | 12 | 12-17
2028-03-25 | 12 | 12-17
2028-03-26 | 13 | 13-17
2028-03-27 | 13 | 13-17
2028-03-28 | 13 | 13-17
2028-03-29 | 13 | 13-17
2028-03-30 | 13 | 13-17
2028-03-31 | 13 | 13-17
2028-04-01 | 13 | 13-17
2028-04-02 | 14 | 14-17
2028-04-03 | 14 | 14-17
2028-04-04 | 14 | 14-17
2028-04-05 | 14 | 14-17
2028-04-06 | 14 | 14-17
2028-04-07 | 14 | 14-17
2028-04-08 | 14 | 14-17
2028-04-09 | 15 | 15-17
2028-04-10 | 15 | 15-17
2028-04-11 | 15 | 15-17
2028-04-12 | 15 | 15-17
2028-04-13 | 15 | 15-17
2028-04-14 | 15 | 15-17
2028-04-15 | 15 | 15-17
2028-04-16 | 16 | 16-17
2028-04-17 | 16 | 16-17
2028-04-18 | 16 | 16-17
2028-04-19 | 16 | 16-17
2028-04-20 | 16 | 16-17
2028-04-21 | 16 | 16-17
2028-04-22 | 16 | 16-17
2028-04-23 | 17 | 17-17
2028-04-24 | 17 | 17-17
2028-04-25 | 17 | 17-17
2028-04-26 | 17 | 17-17
2028-04-27 | 17 | 17-17
2028-04-28 | 17 | 17-17
2028-04-29 | 17 | 17-17
2028-04-30 | 18 | 18-17
2028-05-01 | 18 | 18-17
2028-05-02 | 18 | 18-17
2028-05-03 | 18 | 18-17
2028-05-04 | 18 | 18-17
2028-05-05 | 18 | 18-17
2028-05-06 | 18 | 18-17
2028-05-07 | 19 | 19-17
2028-05-08 | 19 | 19-17
2028-05-09 | 19 | 19-17
2028-05-10 | 19 | 19-17
2028-05-11 | 19 | 19-17
2028-05-12 | 19 | 19-17
2028-05-13 | 19 | 19-17
2028-05-14 | 20 | 20-17
2028-05-15 | 20 | 20-17
2028-05-16 | 20 | 20-17
2028-05-17 | 20 | 20-17
2028-05-18 | 20 | 20-17
2028-05-19 | 20 | 20-17
2028-05-20 | 20 | 20-17
2028-05-21 | 21 | 21-17
2028-05-22 | 21 | 21-17
2028-05-23 | 21 | 21-17
2028-05-24 | 21 | 21-17
2028-05-25 | 21 | 21-17
2028-05-26 | 21 | 21-17
2028-05-27 | 21 | 21-17
2028-05-28 | 22 | 22-17
2028-05-29 | 22 | 22-17
2028-05-30 | 22 | 22-17
2028-05-31 | 22 | 22-17
2028-06-01 | 22 | 22-17
2028-06-02 | 22 | 22-17
2028-06-03 | 22 | 22-17
2028-06-04 | 23 | 23-17
2028-06-05 | 23 | 23-17
2028-06-06 | 23 | 23-17
2028-06-07 | 23 | 23-17
2028-06-08 | 23 | 23-17
2028-06-09 | 23 | 23-17
2028-06-10 | 23 | 23-17
2028-06-11 | 24 | 24-17
2028-06-12 | 24 | 24-17
2028-06-13 | 24 | 24-17
2028-06-14 | 24 | 24-17
2028-06-15 | 24 | 24-17
2028-06-16 | 24 | 24-17
2028-06-17 | 24 | 24-17
2028-06-18 | 25 | 25-17
2028-06-19 | 25 | 25-17
2028-06-20 | 25 | 25-17
2028-06-21 | 25 | 25-17
2028-06-22 | 25 | 25-17
2028-06-23 | 25 | 25-17
2028-06-24 | 25 | 25-17
2028-06-25 | 26 | 26-17
2028-06-26 | 26 | 26-17
2028-06-27 | 26 | 26-17
2028-06-28 | 26 | 26-17
2028-06-29 | 26 | 26-17
2028-06-30 | 26 | 26-17
2028-07-01 | 26 | 26-17
2028-07-02 | 27 | 27-17
2028-07-03 | 27 | 27-17
2028-07-04 | 27 | 27-17
2028-07-05 | 27 | 27-17
2028-07-06 | 27 | 27-17
2028-07-07 | 27 | 27-17
2028-07-08 | 27 | 27-17
2028-07-09 | 28 | 28-17
2028-07-10 | 28 | 28-17
2028-07-11 | 28 | 28-17
2028-07-12 | 28 | 28-17
2028-07-13 | 28 | 28-17
2028-07-14 | 28 | 28-17
2028-07-15 | 28 | 28-17
2028-07-16 | 29 | 29-17
2028-07-17 | 29 | 29-17
2028-07-18 | 29 | 29-17
2028-07-19 | 29 | 29-17
2028-07-20 | 29 | 29-17
2028-07-21 | 29 | 29-17
2028-07-22 | 29 | 29-17
2028-07-23 | 30 | 30-17
2028-07-24 | 30 | 30-17
2028-07-25 | 30 | 30-17
2028-07-26 | 30 | 30-17
2028-07-27 | 30 | 30-17
2028-07-28 | 30 | 30-17
2028-07-29 | 30 | 30-17
2028-07-30 | 31 | 31-17
2028-07-31 | 31 | 31-17
2028-08-01 | 31 | 31-17
2028-08-02 | 31 | 31-17
2028-08-03 | 31 | 31-17
2028-08-04 | 31 | 31-17
2028-08-05 | 31 | 31-17
2028-08-06 | 32 | 32-17
2028-08-07 | 32 | 32-17
2028-08-08 | 32 | 32-17
2028-08-09 | 32 | 32-17
2028-08-10 | 32 | 32-17
2028-08-11 | 32 | 32-17
2028-08-12 | 32 | 32-17
2028-08-13 | 33 | 33-17
2028-08-14 | 33 | 33-17
2028-08-15 | 33 | 33-17
2028-08-16 | 33 | 33-17
2028-08-17 | 33 | 33-17
2028-08-18 | 33 | 33-17
2028-08-19 | 33 | 33-17
2028-08-20 | 34 | 34-17
2028-08-21 | 34 | 34-17
2028-08-22 | 34 | 34-17
2028-08-23 | 34 | 34-17
2028-08-24 | 34 | 34-17
2028-08-25 | 34 | 34-17
2028-08-26 | 34 | 34-17
2028-08-27 | 35 | 35-17
2028-08-28 | 35 | 35-17
2028-08-29 | 35 | 35-17
2028-08-30 | 35 | 35-17
2028-08-31 | 35 | 35-17
2028-09-01 | 35 | 35-17
2028-09-02 | 35 | 35-17
2028-09-03 | 36 | 36-17
2028-09-04 | 36 | 36-17
2028-09-05 | 36 | 36-17
2028-09-06 | 36 | 36-17
2028-09-07 | 36 | 36-17
2028-09-08 | 36 | 36-17
2028-09-09 | 36 | 36-17
2028-09-10 | 37 | 37-17
2028-09-11 | 37 | 37-17
2028-09-12 | 37 | 37-17
2028-09-13 | 37 | 37-17
2028-09-14 | 37 | 37-17
2028-09-15 | 37 | 37-17
2028-09-16 | 37 | 37-17
2028-09-17 | 38 | 38-17
2028-09-18 | 38 | 38-17
2028-09-19 | 38 | 38-17
2028-09-20 | 38 | 38-17
2028-09-21 | 38 | 38-17
2028-09-22 | 38 | 38-17
2028-09-23 | 38 | 38-17
2028-09-24 | 39 | 39-17
2028-09-25 | 39 | 39-17
2028-09-26 | 39 | 39-17
2028-09-27 | 39 | 39-17
2028-09-28 | 39 | 39-17
2028-09-29 | 39 | 39-17
2028-09-30 | 39 | 39-17
2028-10-01 | 40 | 40-17
2028-10-02 | 40 | 40-17
2028-10-03 | 40 | 40-17
2028-10-04 | 40 | 40-17
2028-10-05 | 40 | 40-17
2028-10-06 | 40 | 40-17
2028-10-07 | 40 | 40-17
2028-10-08 | 41 | 41-17
2028-10-09 | 41 | 41-17
2028-10-10 | 41 | 41-17
2028-10-11 | 41 | 41-17
2028-10-12 | 41 | 41-17
2028-10-13 | 41 | 41-17
2028-10-14 | 41 | 41-17
2028-10-15 | 42 | 42-17
2028-10-16 | 42 | 42-17
2028-10-17 | 42 | 42-17
2028-10-18 | 42 | 42-17
2028-10-19 | 42 | 42-17
2028-10-20 | 42 | 42-17
2028-10-21 | 42 | 42-17
2028-10-22 | 43 | 43-17
2028-10-23 | 43 | 43-17
2028-10-24 | 43 | 43-17
2028-10-25 | 43 | 43-17
2028-10-26 | 43 | 43-17
2028-10-27 | 43 | 43-17
2028-10-28 | 43 | 43-17
2028-10-29 | 44 | 44-17
2028-10-30 | 44 | 44-17
2028-10-31 | 44 | 44-17
2028-11-01 | 44 | 44-17
2028-11-02 | 44 | 44-17
2028-11-03 | 44 | 44-17
2028-11-04 | 44 | 44-17
2028-11-05 | 45 | 45-17
2028-11-06 | 45 | 45-17
2028-11-07 | 45 | 45-17
2028-11-08 | 45 | 45-17
2028-11-09 | 45 | 45-17
2028-11-10 | 45 | 45-17
2028-11-11 | 45 | 45-17
2028-11-12 | 46 | 46-17
2028-11-13 | 46 | 46-17
2028-11-14 | 46 | 46-17
2028-11-15 | 46 | 46-17
2028-11-16 | 46 | 46-17
2028-11-17 | 46 | 46-17
2028-11-18 | 46 | 46-17
2028-11-19 | 47 | 47-17
2028-11-20 | 47 | 47-17
2028-11-21 | 47 | 47-17
2028-11-22 | 47 | 47-17
2028-11-23 | 47 | 47-17
2028-11-24 | 47 | 47-17
2028-11-25 | 47 | 47-17
2028-11-26 | 48 | 48-17
2028-11-27 | 48 | 48-17
2028-11-28 | 48 | 48-17
2028-11-29 | 48 | 48-17
2028-11-30 | 48 | 48-17
2028-12-01 | 48 | 48-17
2028-12-02 | 48 | 48-17
2028-12-03 | 49 | 49-17
2028-12-04 | 49 | 49-17
2028-12-05 | 49 | 49-17
2028-12-06 | 49 | 49-17
2028-12-07 | 49 | 49-17
2028-12-08 | 49 | 49-17
2028-12-09 | 49 | 49-17
2028-12-10 | 50 | 50-17
2028-12-11 | 50 | 50-17
2028-12-12 | 50 | 50-17
2028-12-13 | 50 | 50-17
2028-12-14 | 50 | 50-17
2028-12-15 | 50 | 50-17
2028-12-16 | 50 | 50-17
2028-12-17 | 51 | 51-17
2028-12-18 | 51 | 51-17
2028-12-19 | 51 | 51-17
2028-12-20 | 51 | 51-17
2028-12-21 | 51 | 51-17
2028-12-22 | 51 | 51-17
2028-12-23 | 51 | 51-17
2028-12-24 | 52 | 52-17
2028-12-25 | 52 | 52-17
2028-12-26 | 52 | 52-17
2028-12-27 | 52 | 52-17
2028-12-28 | 52 | 52-17
2028-12-29 | 52 | 52-17
2028-12-30 | 52 | 52-17
2028-12-31 | 53 | 53-17
2029-01-01 | 1 | 1-18
2029-01-02 | 1 | 1-18
2029-01-03 | 1 | 1-18
2029-01-04 | 1 | 1-18
2029-01-05 | 1 | 1-18
2029-01-06 | 1 | 1-18
2029-01-07 | 2 | 2-18
2029-01-08 | 2 | 2-18
2029-01-09 | 2 | 2-18
2029-01-10 | 2 | 2-18
2029-01-11 | 2 | 2-18
2029-01-12 | 2 | 2-18
2029-01-13 | 2 | 2-18
2029-01-14 | 3 | 3-18
2029-01-15 | 3 | 3-18
2029-01-16 | 3 | 3-18
2029-01-17 | 3 | 3-18
2029-01-18 | 3 | 3-18
2029-01-19 | 3 | 3-18
2029-01-20 | 3 | 3-18
2029-01-21 | 4 | 4-18
2029-01-22 | 4 | 4-18
2029-01-23 | 4 | 4-18
2029-01-24 | 4 | 4-18
2029-01-25 | 4 | 4-18
2029-01-26 | 4 | 4-18
2029-01-27 | 4 | 4-18
2029-01-28 | 5 | 5-18
2029-01-29 | 5 | 5-18
2029-01-30 | 5 | 5-18
2029-01-31 | 5 | 5-18
2029-02-01 | 5 | 5-18
2029-02-02 | 5 | 5-18
2029-02-03 | 5 | 5-18
2029-02-04 | 6 | 6-18
2029-02-05 | 6 | 6-18
2029-02-06 | 6 | 6-18
2029-02-07 | 6 | 6-18
2029-02-08 | 6 | 6-18
2029-02-09 | 6 | 6-18
2029-02-10 | 6 | 6-18
2029-02-11 | 7 | 7-18
2029-02-12 | 7 | 7-18
2029-02-13 | 7 | 7-18
2029-02-14 | 7 | 7-18
2029-02-15 | 7 | 7-18
2029-02-16 | 7 | 7-18
2029-02-17 | 7 | 7-18
2029-02-18 | 8 | 8-18
2029-02-19 | 8 | 8-18
2029-02-20 | 8 | 8-18
2029-02-21 | 8 | 8-18
2029-02-22 | 8 | 8-18
2029-02-23 | 8 | 8-18
2029-02-24 | 8 | 8-18
2029-02-25 | 9 | 9-18
2029-02-26 | 9 | 9-18
2029-02-27 | 9 | 9-18
2029-02-28 | 9 | 9-18
2029-03-01 | 9 | 9-18
2029-03-02 | 9 | 9-18
2029-03-03 | 9 | 9-18
2029-03-04 | 10 | 10-18
2029-03-05 | 10 | 10-18
2029-03-06 | 10 | 10-18
2029-03-07 | 10 | 10-18
2029-03-08 | 10 | 10-18
2029-03-09 | 10 | 10-18
2029-03-10 | 10 | 10-18
2029-03-11 | 11 | 11-18
2029-03-12 | 11 | 11-18
2029-03-13 | 11 | 11-18
2029-03-14 | 11 | 11-18
2029-03-15 | 11 | 11-18
2029-03-16 | 11 | 11-18
2029-03-17 | 11 | 11-18
2029-03-18 | 12 | 12-18
2029-03-19 | 12 | 12-18
2029-03-20 | 12 | 12-18
2029-03-21 | 12 | 12-18
2029-03-22 | 12 | 12-18
2029-03-23 | 12 | 12-18
2029-03-24 | 12 | 12-18
2029-03-25 | 13 | 13-18
2029-03-26 | 13 | 13-18
2029-03-27 | 13 | 13-18
2029-03-28 | 13 | 13-18
2029-03-29 | 13 | 13-18
2029-03-30 | 13 | 13-18
2029-03-31 | 13 | 13-18
2029-04-01 | 14 | 14-18
2029-04-02 | 14 | 14-18
2029-04-03 | 14 | 14-18
2029-04-04 | 14 | 14-18
2029-04-05 | 14 | 14-18
2029-04-06 | 14 | 14-18
2029-04-07 | 14 | 14-18
2029-04-08 | 15 | 15-18
2029-04-09 | 15 | 15-18
2029-04-10 | 15 | 15-18
2029-04-11 | 15 | 15-18
2029-04-12 | 15 | 15-18
2029-04-13 | 15 | 15-18
2029-04-14 | 15 | 15-18
2029-04-15 | 16 | 16-18
2029-04-16 | 16 | 16-18
2029-04-17 | 16 | 16-18
2029-04-18 | 16 | 16-18
2029-04-19 | 16 | 16-18
2029-04-20 | 16 | 16-18
2029-04-21 | 16 | 16-18
2029-04-22 | 17 | 17-18
2029-04-23 | 17 | 17-18
2029-04-24 | 17 | 17-18
2029-04-25 | 17 | 17-18
2029-04-26 | 17 | 17-18
2029-04-27 | 17 | 17-18
2029-04-28 | 17 | 17-18
2029-04-29 | 18 | 18-18
2029-04-30 | 18 | 18-18
2029-05-01 | 18 | 18-18
2029-05-02 | 18 | 18-18
2029-05-03 | 18 | 18-18
2029-05-04 | 18 | 18-18
2029-05-05 | 18 | 18-18
2029-05-06 | 19 | 19-18
2029-05-07 | 19 | 19-18
2029-05-08 | 19 | 19-18
2029-05-09 | 19 | 19-18
2029-05-10 | 19 | 19-18
2029-05-11 | 19 | 19-18
2029-05-12 | 19 | 19-18
2029-05-13 | 20 | 20-18
2029-05-14 | 20 | 20-18
2029-05-15 | 20 | 20-18
2029-05-16 | 20 | 20-18
2029-05-17 | 20 | 20-18
2029-05-18 | 20 | 20-18
2029-05-19 | 20 | 20-18
2029-05-20 | 21 | 21-18
2029-05-21 | 21 | 21-18
2029-05-22 | 21 | 21-18
2029-05-23 | 21 | 21-18
2029-05-24 | 21 | 21-18
2029-05-25 | 21 | 21-18
2029-05-26 | 21 | 21-18
2029-05-27 | 22 | 22-18
2029-05-28 | 22 | 22-18
2029-05-29 | 22 | 22-18
2029-05-30 | 22 | 22-18
2029-05-31 | 22 | 22-18
2029-06-01 | 22 | 22-18
2029-06-02 | 22 | 22-18
2029-06-03 | 23 | 23-18
2029-06-04 | 23 | 23-18
2029-06-05 | 23 | 23-18
2029-06-06 | 23 | 23-18
2029-06-07 | 23 | 23-18
2029-06-08 | 23 | 23-18
2029-06-09 | 23 | 23-18
2029-06-10 | 24 | 24-18
2029-06-11 | 24 | 24-18
2029-06-12 | 24 | 24-18
2029-06-13 | 24 | 24-18
2029-06-14 | 24 | 24-18
2029-06-15 | 24 | 24-18
2029-06-16 | 24 | 24-18
2029-06-17 | 25 | 25-18
2029-06-18 | 25 | 25-18
2029-06-19 | 25 | 25-18
2029-06-20 | 25 | 25-18
2029-06-21 | 25 | 25-18
2029-06-22 | 25 | 25-18
2029-06-23 | 25 | 25-18
2029-06-24 | 26 | 26-18
2029-06-25 | 26 | 26-18
2029-06-26 | 26 | 26-18
2029-06-27 | 26 | 26-18
2029-06-28 | 26 | 26-18
2029-06-29 | 26 | 26-18
2029-06-30 | 26 | 26-18
2029-07-01 | 27 | 27-18
2029-07-02 | 27 | 27-18
2029-07-03 | 27 | 27-18
2029-07-04 | 27 | 27-18
2029-07-05 | 27 | 27-18
2029-07-06 | 27 | 27-18
2029-07-07 | 27 | 27-18
2029-07-08 | 28 | 28-18
2029-07-09 | 28 | 28-18
2029-07-10 | 28 | 28-18
2029-07-11 | 28 | 28-18
2029-07-12 | 28 | 28-18
2029-07-13 | 28 | 28-18
2029-07-14 | 28 | 28-18
2029-07-15 | 29 | 29-18
2029-07-16 | 29 | 29-18
2029-07-17 | 29 | 29-18
2029-07-18 | 29 | 29-18
2029-07-19 | 29 | 29-18
2029-07-20 | 29 | 29-18
2029-07-21 | 29 | 29-18
2029-07-22 | 30 | 30-18
2029-07-23 | 30 | 30-18
2029-07-24 | 30 | 30-18
2029-07-25 | 30 | 30-18
2029-07-26 | 30 | 30-18
2029-07-27 | 30 | 30-18
2029-07-28 | 30 | 30-18
2029-07-29 | 31 | 31-18
2029-07-30 | 31 | 31-18
2029-07-31 | 31 | 31-18
2029-08-01 | 31 | 31-18
2029-08-02 | 31 | 31-18
2029-08-03 | 31 | 31-18
2029-08-04 | 31 | 31-18
2029-08-05 | 32 | 32-18
2029-08-06 | 32 | 32-18
2029-08-07 | 32 | 32-18
2029-08-08 | 32 | 32-18
2029-08-09 | 32 | 32-18
2029-08-10 | 32 | 32-18
2029-08-11 | 32 | 32-18
2029-08-12 | 33 | 33-18
2029-08-13 | 33 | 33-18
2029-08-14 | 33 | 33-18
2029-08-15 | 33 | 33-18
2029-08-16 | 33 | 33-18
2029-08-17 | 33 | 33-18
2029-08-18 | 33 | 33-18
2029-08-19 | 34 | 34-18
2029-08-20 | 34 | 34-18
2029-08-21 | 34 | 34-18
2029-08-22 | 34 | 34-18
2029-08-23 | 34 | 34-18
2029-08-24 | 34 | 34-18
2029-08-25 | 34 | 34-18
2029-08-26 | 35 | 35-18
2029-08-27 | 35 | 35-18
2029-08-28 | 35 | 35-18
2029-08-29 | 35 | 35-18
2029-08-30 | 35 | 35-18
2029-08-31 | 35 | 35-18
2029-09-01 | 35 | 35-18
2029-09-02 | 36 | 36-18
2029-09-03 | 36 | 36-18
2029-09-04 | 36 | 36-18
2029-09-05 | 36 | 36-18
2029-09-06 | 36 | 36-18
2029-09-07 | 36 | 36-18
2029-09-08 | 36 | 36-18
2029-09-09 | 37 | 37-18
2029-09-10 | 37 | 37-18
2029-09-11 | 37 | 37-18
2029-09-12 | 37 | 37-18
2029-09-13 | 37 | 37-18
2029-09-14 | 37 | 37-18
2029-09-15 | 37 | 37-18
2029-09-16 | 38 | 38-18
2029-09-17 | 38 | 38-18
2029-09-18 | 38 | 38-18
2029-09-19 | 38 | 38-18
2029-09-20 | 38 | 38-18
2029-09-21 | 38 | 38-18
2029-09-22 | 38 | 38-18
2029-09-23 | 39 | 39-18
2029-09-24 | 39 | 39-18
2029-09-25 | 39 | 39-18
2029-09-26 | 39 | 39-18
2029-09-27 | 39 | 39-18
2029-09-28 | 39 | 39-18
2029-09-29 | 39 | 39-18
2029-09-30 | 40 | 40-18
2029-10-01 | 40 | 40-18
2029-10-02 | 40 | 40-18
2029-10-03 | 40 | 40-18
2029-10-04 | 40 | 40-18
2029-10-05 | 40 | 40-18
2029-10-06 | 40 | 40-18
2029-10-07 | 41 | 41-18
2029-10-08 | 41 | 41-18
2029-10-09 | 41 | 41-18
2029-10-10 | 41 | 41-18
2029-10-11 | 41 | 41-18
2029-10-12 | 41 | 41-18
2029-10-13 | 41 | 41-18
2029-10-14 | 42 | 42-18
2029-10-15 | 42 | 42-18
2029-10-16 | 42 | 42-18
2029-10-17 | 42 | 42-18
2029-10-18 | 42 | 42-18
2029-10-19 | 42 | 42-18
2029-10-20 | 42 | 42-18
2029-10-21 | 43 | 43-18
2029-10-22 | 43 | 43-18
2029-10-23 | 43 | 43-18
2029-10-24 | 43 | 43-18
2029-10-25 | 43 | 43-18
2029-10-26 | 43 | 43-18
2029-10-27 | 43 | 43-18
2029-10-28 | 44 | 44-18
2029-10-29 | 44 | 44-18
2029-10-30 | 44 | 44-18
2029-10-31 | 44 | 44-18
2029-11-01 | 44 | 44-18
2029-11-02 | 44 | 44-18
2029-11-03 | 44 | 44-18
2029-11-04 | 45 | 45-18
2029-11-05 | 45 | 45-18
2029-11-06 | 45 | 45-18
2029-11-07 | 45 | 45-18
2029-11-08 | 45 | 45-18
2029-11-09 | 45 | 45-18
2029-11-10 | 45 | 45-18
2029-11-11 | 46 | 46-18
2029-11-12 | 46 | 46-18
2029-11-13 | 46 | 46-18
2029-11-14 | 46 | 46-18
2029-11-15 | 46 | 46-18
2029-11-16 | 46 | 46-18
2029-11-17 | 46 | 46-18
2029-11-18 | 47 | 47-18
2029-11-19 | 47 | 47-18
2029-11-20 | 47 | 47-18
2029-11-21 | 47 | 47-18
2029-11-22 | 47 | 47-18
2029-11-23 | 47 | 47-18
2029-11-24 | 47 | 47-18
2029-11-25 | 48 | 48-18
2029-11-26 | 48 | 48-18
2029-11-27 | 48 | 48-18
2029-11-28 | 48 | 48-18
2029-11-29 | 48 | 48-18
2029-11-30 | 48 | 48-18
2029-12-01 | 48 | 48-18
2029-12-02 | 49 | 49-18
2029-12-03 | 49 | 49-18
2029-12-04 | 49 | 49-18
2029-12-05 | 49 | 49-18
2029-12-06 | 49 | 49-18
2029-12-07 | 49 | 49-18
2029-12-08 | 49 | 49-18
2029-12-09 | 50 | 50-18
2029-12-10 | 50 | 50-18
2029-12-11 | 50 | 50-18
2029-12-12 | 50 | 50-18
2029-12-13 | 50 | 50-18
2029-12-14 | 50 | 50-18
2029-12-15 | 50 | 50-18
2029-12-16 | 51 | 51-18
2029-12-17 | 51 | 51-18
2029-12-18 | 51 | 51-18
2029-12-19 | 51 | 51-18
2029-12-20 | 51 | 51-18
2029-12-21 | 51 | 51-18
2029-12-22 | 51 | 51-18
2029-12-23 | 52 | 52-18
2029-12-24 | 52 | 52-18
2029-12-25 | 52 | 52-18
2029-12-26 | 52 | 52-18
2029-12-27 | 52 | 52-18
2029-12-28 | 52 | 52-18
2029-12-29 | 52 | 52-18
2029-12-30 | 53 | 53-18
2029-12-31 | 53 | 53-18
2030-01-01 | 1 | 1-19
2030-01-02 | 1 | 1-19
2030-01-03 | 1 | 1-19
2030-01-04 | 1 | 1-19
2030-01-05 | 1 | 1-19
2030-01-06 | 2 | 2-19
2030-01-07 | 2 | 2-19
2030-01-08 | 2 | 2-19
2030-01-09 | 2 | 2-19
2030-01-10 | 2 | 2-19
2030-01-11 | 2 | 2-19
2030-01-12 | 2 | 2-19
2030-01-13 | 3 | 3-19
2030-01-14 | 3 | 3-19
2030-01-15 | 3 | 3-19
2030-01-16 | 3 | 3-19
2030-01-17 | 3 | 3-19
2030-01-18 | 3 | 3-19
2030-01-19 | 3 | 3-19
2030-01-20 | 4 | 4-19
2030-01-21 | 4 | 4-19
2030-01-22 | 4 | 4-19
2030-01-23 | 4 | 4-19
2030-01-24 | 4 | 4-19
2030-01-25 | 4 | 4-19
2030-01-26 | 4 | 4-19
2030-01-27 | 5 | 5-19
2030-01-28 | 5 | 5-19
2030-01-29 | 5 | 5-19
2030-01-30 | 5 | 5-19
2030-01-31 | 5 | 5-19
2030-02-01 | 5 | 5-19
2030-02-02 | 5 | 5-19
2030-02-03 | 6 | 6-19
2030-02-04 | 6 | 6-19
2030-02-05 | 6 | 6-19
2030-02-06 | 6 | 6-19
2030-02-07 | 6 | 6-19
2030-02-08 | 6 | 6-19
2030-02-09 | 6 | 6-19
2030-02-10 | 7 | 7-19
2030-02-11 | 7 | 7-19
2030-02-12 | 7 | 7-19
2030-02-13 | 7 | 7-19
2030-02-14 | 7 | 7-19
2030-02-15 | 7 | 7-19
2030-02-16 | 7 | 7-19
2030-02-17 | 8 | 8-19
2030-02-18 | 8 | 8-19
2030-02-19 | 8 | 8-19
2030-02-20 | 8 | 8-19
2030-02-21 | 8 | 8-19
2030-02-22 | 8 | 8-19
2030-02-23 | 8 | 8-19
2030-02-24 | 9 | 9-19
2030-02-25 | 9 | 9-19
2030-02-26 | 9 | 9-19
2030-02-27 | 9 | 9-19
2030-02-28 | 9 | 9-19
2030-03-01 | 9 | 9-19
2030-03-02 | 9 | 9-19
2030-03-03 | 10 | 10-19
2030-03-04 | 10 | 10-19
2030-03-05 | 10 | 10-19
2030-03-06 | 10 | 10-19
2030-03-07 | 10 | 10-19
2030-03-08 | 10 | 10-19
2030-03-09 | 10 | 10-19
2030-03-10 | 11 | 11-19
2030-03-11 | 11 | 11-19
2030-03-12 | 11 | 11-19
2030-03-13 | 11 | 11-19
2030-03-14 | 11 | 11-19
2030-03-15 | 11 | 11-19
2030-03-16 | 11 | 11-19
2030-03-17 | 12 | 12-19
2030-03-18 | 12 | 12-19
2030-03-19 | 12 | 12-19
2030-03-20 | 12 | 12-19
2030-03-21 | 12 | 12-19
2030-03-22 | 12 | 12-19
2030-03-23 | 12 | 12-19
2030-03-24 | 13 | 13-19
2030-03-25 | 13 | 13-19
2030-03-26 | 13 | 13-19
2030-03-27 | 13 | 13-19
2030-03-28 | 13 | 13-19
2030-03-29 | 13 | 13-19
2030-03-30 | 13 | 13-19
2030-03-31 | 14 | 14-19
2030-04-01 | 14 | 14-19
2030-04-02 | 14 | 14-19
2030-04-03 | 14 | 14-19
2030-04-04 | 14 | 14-19
2030-04-05 | 14 | 14-19
2030-04-06 | 14 | 14-19
2030-04-07 | 15 | 15-19
2030-04-08 | 15 | 15-19
2030-04-09 | 15 | 15-19
2030-04-10 | 15 | 15-19
2030-04-11 | 15 | 15-19
2030-04-12 | 15 | 15-19
2030-04-13 | 15 | 15-19
2030-04-14 | 16 | 16-19
2030-04-15 | 16 | 16-19
2030-04-16 | 16 | 16-19
2030-04-17 | 16 | 16-19
2030-04-18 | 16 | 16-19
2030-04-19 | 16 | 16-19
2030-04-20 | 16 | 16-19
2030-04-21 | 17 | 17-19
2030-04-22 | 17 | 17-19
2030-04-23 | 17 | 17-19
2030-04-24 | 17 | 17-19
2030-04-25 | 17 | 17-19
2030-04-26 | 17 | 17-19
2030-04-27 | 17 | 17-19
2030-04-28 | 18 | 18-19
2030-04-29 | 18 | 18-19
2030-04-30 | 18 | 18-19
2030-05-01 | 18 | 18-19
2030-05-02 | 18 | 18-19
2030-05-03 | 18 | 18-19
2030-05-04 | 18 | 18-19
2030-05-05 | 19 | 19-19
2030-05-06 | 19 | 19-19
2030-05-07 | 19 | 19-19
2030-05-08 | 19 | 19-19
2030-05-09 | 19 | 19-19
2030-05-10 | 19 | 19-19
2030-05-11 | 19 | 19-19
2030-05-12 | 20 | 20-19
2030-05-13 | 20 | 20-19
2030-05-14 | 20 | 20-19
2030-05-15 | 20 | 20-19
2030-05-16 | 20 | 20-19
2030-05-17 | 20 | 20-19
2030-05-18 | 20 | 20-19
2030-05-19 | 21 | 21-19
2030-05-20 | 21 | 21-19
2030-05-21 | 21 | 21-19
2030-05-22 | 21 | 21-19
2030-05-23 | 21 | 21-19
2030-05-24 | 21 | 21-19
2030-05-25 | 21 | 21-19
2030-05-26 | 22 | 22-19
2030-05-27 | 22 | 22-19
2030-05-28 | 22 | 22-19
2030-05-29 | 22 | 22-19
2030-05-30 | 22 | 22-19
2030-05-31 | 22 | 22-19
2030-06-01 | 22 | 22-19
2030-06-02 | 23 | 23-19
2030-06-03 | 23 | 23-19
2030-06-04 | 23 | 23-19
2030-06-05 | 23 | 23-19
2030-06-06 | 23 | 23-19
2030-06-07 | 23 | 23-19
2030-06-08 | 23 | 23-19
2030-06-09 | 24 | 24-19
2030-06-10 | 24 | 24-19
2030-06-11 | 24 | 24-19
2030-06-12 | 24 | 24-19
2030-06-13 | 24 | 24-19
2030-06-14 | 24 | 24-19
2030-06-15 | 24 | 24-19
2030-06-16 | 25 | 25-19
2030-06-17 | 25 | 25-19
2030-06-18 | 25 | 25-19
2030-06-19 | 25 | 25-19
2030-06-20 | 25 | 25-19
2030-06-21 | 25 | 25-19
2030-06-22 | 25 | 25-19
2030-06-23 | 26 | 26-19
2030-06-24 | 26 | 26-19
2030-06-25 | 26 | 26-19
2030-06-26 | 26 | 26-19
2030-06-27 | 26 | 26-19
2030-06-28 | 26 | 26-19
2030-06-29 | 26 | 26-19
2030-06-30 | 27 | 27-19
2030-07-01 | 27 | 27-19
2030-07-02 | 27 | 27-19
2030-07-03 | 27 | 27-19
2030-07-04 | 27 | 27-19
2030-07-05 | 27 | 27-19
2030-07-06 | 27 | 27-19
2030-07-07 | 28 | 28-19
2030-07-08 | 28 | 28-19
2030-07-09 | 28 | 28-19
2030-07-10 | 28 | 28-19
2030-07-11 | 28 | 28-19
2030-07-12 | 28 | 28-19
2030-07-13 | 28 | 28-19
2030-07-14 | 29 | 29-19
2030-07-15 | 29 | 29-19
2030-07-16 | 29 | 29-19
2030-07-17 | 29 | 29-19
2030-07-18 | 29 | 29-19
2030-07-19 | 29 | 29-19
2030-07-20 | 29 | 29-19
2030-07-21 | 30 | 30-19
2030-07-22 | 30 | 30-19
2030-07-23 | 30 | 30-19
2030-07-24 | 30 | 30-19
2030-07-25 | 30 | 30-19
2030-07-26 | 30 | 30-19
2030-07-27 | 30 | 30-19
2030-07-28 | 31 | 31-19
2030-07-29 | 31 | 31-19
2030-07-30 | 31 | 31-19
2030-07-31 | 31 | 31-19
2030-08-01 | 31 | 31-19
2030-08-02 | 31 | 31-19
2030-08-03 | 31 | 31-19
2030-08-04 | 32 | 32-19
2030-08-05 | 32 | 32-19
2030-08-06 | 32 | 32-19
2030-08-07 | 32 | 32-19
2030-08-08 | 32 | 32-19
2030-08-09 | 32 | 32-19
2030-08-10 | 32 | 32-19
2030-08-11 | 33 | 33-19
2030-08-12 | 33 | 33-19
2030-08-13 | 33 | 33-19
2030-08-14 | 33 | 33-19
2030-08-15 | 33 | 33-19
2030-08-16 | 33 | 33-19
2030-08-17 | 33 | 33-19
2030-08-18 | 34 | 34-19
2030-08-19 | 34 | 34-19
2030-08-20 | 34 | 34-19
2030-08-21 | 34 | 34-19
2030-08-22 | 34 | 34-19
2030-08-23 | 34 | 34-19
2030-08-24 | 34 | 34-19
2030-08-25 | 35 | 35-19
2030-08-26 | 35 | 35-19
2030-08-27 | 35 | 35-19
2030-08-28 | 35 | 35-19
2030-08-29 | 35 | 35-19
2030-08-30 | 35 | 35-19
2030-08-31 | 35 | 35-19
2030-09-01 | 36 | 36-19
2030-09-02 | 36 | 36-19
2030-09-03 | 36 | 36-19
2030-09-04 | 36 | 36-19
2030-09-05 | 36 | 36-19
2030-09-06 | 36 | 36-19
2030-09-07 | 36 | 36-19
2030-09-08 | 37 | 37-19
2030-09-09 | 37 | 37-19
2030-09-10 | 37 | 37-19
2030-09-11 | 37 | 37-19
2030-09-12 | 37 | 37-19
2030-09-13 | 37 | 37-19
2030-09-14 | 37 | 37-19
2030-09-15 | 38 | 38-19
2030-09-16 | 38 | 38-19
2030-09-17 | 38 | 38-19
2030-09-18 | 38 | 38-19
2030-09-19 | 38 | 38-19
2030-09-20 | 38 | 38-19
2030-09-21 | 38 | 38-19
2030-09-22 | 39 | 39-19
2030-09-23 | 39 | 39-19
2030-09-24 | 39 | 39-19
2030-09-25 | 39 | 39-19
2030-09-26 | 39 | 39-19
2030-09-27 | 39 | 39-19
2030-09-28 | 39 | 39-19
2030-09-29 | 40 | 40-19
2030-09-30 | 40 | 40-19
2030-10-01 | 40 | 40-19
2030-10-02 | 40 | 40-19
2030-10-03 | 40 | 40-19
2030-10-04 | 40 | 40-19
2030-10-05 | 40 | 40-19
2030-10-06 | 41 | 41-19
2030-10-07 | 41 | 41-19
2030-10-08 | 41 | 41-19
2030-10-09 | 41 | 41-19
2030-10-10 | 41 | 41-19
2030-10-11 | 41 | 41-19
2030-10-12 | 41 | 41-19
2030-10-13 | 42 | 42-19
2030-10-14 | 42 | 42-19
2030-10-15 | 42 | 42-19
2030-10-16 | 42 | 42-19
2030-10-17 | 42 | 42-19
2030-10-18 | 42 | 42-19
2030-10-19 | 42 | 42-19
2030-10-20 | 43 | 43-19
2030-10-21 | 43 | 43-19
2030-10-22 | 43 | 43-19
2030-10-23 | 43 | 43-19
2030-10-24 | 43 | 43-19
2030-10-25 | 43 | 43-19
2030-10-26 | 43 | 43-19
2030-10-27 | 44 | 44-19
2030-10-28 | 44 | 44-19
2030-10-29 | 44 | 44-19
2030-10-30 | 44 | 44-19
2030-10-31 | 44 | 44-19
2030-11-01 | 44 | 44-19
2030-11-02 | 44 | 44-19
2030-11-03 | 45 | 45-19
2030-11-04 | 45 | 45-19
2030-11-05 | 45 | 45-19
2030-11-06 | 45 | 45-19
2030-11-07 | 45 | 45-19
2030-11-08 | 45 | 45-19
2030-11-09 | 45 | 45-19
2030-11-10 | 46 | 46-19
2030-11-11 | 46 | 46-19
2030-11-12 | 46 | 46-19
2030-11-13 | 46 | 46-19
2030-11-14 | 46 | 46-19
2030-11-15 | 46 | 46-19
2030-11-16 | 46 | 46-19
2030-11-17 | 47 | 47-19
2030-11-18 | 47 | 47-19
2030-11-19 | 47 | 47-19
2030-11-20 | 47 | 47-19
2030-11-21 | 47 | 47-19
2030-11-22 | 47 | 47-19
2030-11-23 | 47 | 47-19
2030-11-24 | 48 | 48-19
2030-11-25 | 48 | 48-19
2030-11-26 | 48 | 48-19
2030-11-27 | 48 | 48-19
2030-11-28 | 48 | 48-19
2030-11-29 | 48 | 48-19
2030-11-30 | 48 | 48-19
2030-12-01 | 49 | 49-19
2030-12-02 | 49 | 49-19
2030-12-03 | 49 | 49-19
2030-12-04 | 49 | 49-19
2030-12-05 | 49 | 49-19
2030-12-06 | 49 | 49-19
2030-12-07 | 49 | 49-19
2030-12-08 | 50 | 50-19
2030-12-09 | 50 | 50-19
2030-12-10 | 50 | 50-19
2030-12-11 | 50 | 50-19
2030-12-12 | 50 | 50-19
2030-12-13 | 50 | 50-19
2030-12-14 | 50 | 50-19
2030-12-15 | 51 | 51-19
2030-12-16 | 51 | 51-19
2030-12-17 | 51 | 51-19
2030-12-18 | 51 | 51-19
2030-12-19 | 51 | 51-19
2030-12-20 | 51 | 51-19
2030-12-21 | 51 | 51-19
2030-12-22 | 52 | 52-19
2030-12-23 | 52 | 52-19
2030-12-24 | 52 | 52-19
2030-12-25 | 52 | 52-19
2030-12-26 | 52 | 52-19
2030-12-27 | 52 | 52-19
2030-12-28 | 52 | 52-19
2030-12-29 | 53 | 53-19
2030-12-30 | 53 | 53-19
2030-12-31 | 53 | 53-19
2031-01-01 | 1 | 1-20
2031-01-02 | 1 | 1-20
2031-01-03 | 1 | 1-20
2031-01-04 | 1 | 1-20
2031-01-05 | 2 | 2-20
2031-01-06 | 2 | 2-20
2031-01-07 | 2 | 2-20
2031-01-08 | 2 | 2-20
2031-01-09 | 2 | 2-20
2031-01-10 | 2 | 2-20
2031-01-11 | 2 | 2-20
2031-01-12 | 3 | 3-20
2031-01-13 | 3 | 3-20
2031-01-14 | 3 | 3-20
2031-01-15 | 3 | 3-20
2031-01-16 | 3 | 3-20
2031-01-17 | 3 | 3-20
2031-01-18 | 3 | 3-20
2031-01-19 | 4 | 4-20
2031-01-20 | 4 | 4-20
2031-01-21 | 4 | 4-20
2031-01-22 | 4 | 4-20
2031-01-23 | 4 | 4-20
2031-01-24 | 4 | 4-20
2031-01-25 | 4 | 4-20
2031-01-26 | 5 | 5-20
2031-01-27 | 5 | 5-20
2031-01-28 | 5 | 5-20
2031-01-29 | 5 | 5-20
2031-01-30 | 5 | 5-20
2031-01-31 | 5 | 5-20
2031-02-01 | 5 | 5-20
2031-02-02 | 6 | 6-20
2031-02-03 | 6 | 6-20
2031-02-04 | 6 | 6-20
2031-02-05 | 6 | 6-20
2031-02-06 | 6 | 6-20
2031-02-07 | 6 | 6-20
2031-02-08 | 6 | 6-20
2031-02-09 | 7 | 7-20
2031-02-10 | 7 | 7-20
2031-02-11 | 7 | 7-20
2031-02-12 | 7 | 7-20
2031-02-13 | 7 | 7-20
2031-02-14 | 7 | 7-20
2031-02-15 | 7 | 7-20
2031-02-16 | 8 | 8-20
2031-02-17 | 8 | 8-20
2031-02-18 | 8 | 8-20
2031-02-19 | 8 | 8-20
2031-02-20 | 8 | 8-20
2031-02-21 | 8 | 8-20
2031-02-22 | 8 | 8-20
2031-02-23 | 9 | 9-20
2031-02-24 | 9 | 9-20
2031-02-25 | 9 | 9-20
2031-02-26 | 9 | 9-20
2031-02-27 | 9 | 9-20
2031-02-28 | 9 | 9-20
2031-03-01 | 9 | 9-20
2031-03-02 | 10 | 10-20
2031-03-03 | 10 | 10-20
2031-03-04 | 10 | 10-20
2031-03-05 | 10 | 10-20
2031-03-06 | 10 | 10-20
2031-03-07 | 10 | 10-20
2031-03-08 | 10 | 10-20
2031-03-09 | 11 | 11-20
2031-03-10 | 11 | 11-20
2031-03-11 | 11 | 11-20
2031-03-12 | 11 | 11-20
2031-03-13 | 11 | 11-20
2031-03-14 | 11 | 11-20
2031-03-15 | 11 | 11-20
2031-03-16 | 12 | 12-20
2031-03-17 | 12 | 12-20
2031-03-18 | 12 | 12-20
2031-03-19 | 12 | 12-20
2031-03-20 | 12 | 12-20
2031-03-21 | 12 | 12-20
2031-03-22 | 12 | 12-20
2031-03-23 | 13 | 13-20
2031-03-24 | 13 | 13-20
2031-03-25 | 13 | 13-20
2031-03-26 | 13 | 13-20
2031-03-27 | 13 | 13-20
2031-03-28 | 13 | 13-20
2031-03-29 | 13 | 13-20
2031-03-30 | 14 | 14-20
2031-03-31 | 14 | 14-20
2031-04-01 | 14 | 14-20
2031-04-02 | 14 | 14-20
2031-04-03 | 14 | 14-20
2031-04-04 | 14 | 14-20
2031-04-05 | 14 | 14-20
2031-04-06 | 15 | 15-20
2031-04-07 | 15 | 15-20
2031-04-08 | 15 | 15-20
2031-04-09 | 15 | 15-20
2031-04-10 | 15 | 15-20
2031-04-11 | 15 | 15-20
2031-04-12 | 15 | 15-20
2031-04-13 | 16 | 16-20
2031-04-14 | 16 | 16-20
2031-04-15 | 16 | 16-20
2031-04-16 | 16 | 16-20
2031-04-17 | 16 | 16-20
2031-04-18 | 16 | 16-20
2031-04-19 | 16 | 16-20
2031-04-20 | 17 | 17-20
2031-04-21 | 17 | 17-20
2031-04-22 | 17 | 17-20
2031-04-23 | 17 | 17-20
2031-04-24 | 17 | 17-20
2031-04-25 | 17 | 17-20
2031-04-26 | 17 | 17-20
2031-04-27 | 18 | 18-20
2031-04-28 | 18 | 18-20
2031-04-29 | 18 | 18-20
2031-04-30 | 18 | 18-20
2031-05-01 | 18 | 18-20
2031-05-02 | 18 | 18-20
2031-05-03 | 18 | 18-20
2031-05-04 | 19 | 19-20
2031-05-05 | 19 | 19-20
2031-05-06 | 19 | 19-20
2031-05-07 | 19 | 19-20
2031-05-08 | 19 | 19-20
2031-05-09 | 19 | 19-20
2031-05-10 | 19 | 19-20
2031-05-11 | 20 | 20-20
2031-05-12 | 20 | 20-20
2031-05-13 | 20 | 20-20
2031-05-14 | 20 | 20-20
2031-05-15 | 20 | 20-20
2031-05-16 | 20 | 20-20
2031-05-17 | 20 | 20-20
2031-05-18 | 21 | 21-20
2031-05-19 | 21 | 21-20
2031-05-20 | 21 | 21-20
2031-05-21 | 21 | 21-20
2031-05-22 | 21 | 21-20
2031-05-23 | 21 | 21-20
2031-05-24 | 21 | 21-20
2031-05-25 | 22 | 22-20
2031-05-26 | 22 | 22-20
2031-05-27 | 22 | 22-20
2031-05-28 | 22 | 22-20
2031-05-29 | 22 | 22-20
2031-05-30 | 22 | 22-20
2031-05-31 | 22 | 22-20
2031-06-01 | 23 | 23-20
2031-06-02 | 23 | 23-20
2031-06-03 | 23 | 23-20
2031-06-04 | 23 | 23-20
2031-06-05 | 23 | 23-20
2031-06-06 | 23 | 23-20
2031-06-07 | 23 | 23-20
2031-06-08 | 24 | 24-20
2031-06-09 | 24 | 24-20
2031-06-10 | 24 | 24-20
2031-06-11 | 24 | 24-20
2031-06-12 | 24 | 24-20
2031-06-13 | 24 | 24-20
2031-06-14 | 24 | 24-20
2031-06-15 | 25 | 25-20
2031-06-16 | 25 | 25-20
2031-06-17 | 25 | 25-20
2031-06-18 | 25 | 25-20
2031-06-19 | 25 | 25-20
2031-06-20 | 25 | 25-20
2031-06-21 | 25 | 25-20
2031-06-22 | 26 | 26-20
2031-06-23 | 26 | 26-20
2031-06-24 | 26 | 26-20
2031-06-25 | 26 | 26-20
2031-06-26 | 26 | 26-20
2031-06-27 | 26 | 26-20
2031-06-28 | 26 | 26-20
2031-06-29 | 27 | 27-20
2031-06-30 | 27 | 27-20
2031-07-01 | 27 | 27-20
2031-07-02 | 27 | 27-20
2031-07-03 | 27 | 27-20
2031-07-04 | 27 | 27-20
2031-07-05 | 27 | 27-20
2031-07-06 | 28 | 28-20
2031-07-07 | 28 | 28-20
2031-07-08 | 28 | 28-20
2031-07-09 | 28 | 28-20
2031-07-10 | 28 | 28-20
2031-07-11 | 28 | 28-20
2031-07-12 | 28 | 28-20
2031-07-13 | 29 | 29-20
2031-07-14 | 29 | 29-20
2031-07-15 | 29 | 29-20
2031-07-16 | 29 | 29-20
2031-07-17 | 29 | 29-20
2031-07-18 | 29 | 29-20
2031-07-19 | 29 | 29-20
2031-07-20 | 30 | 30-20
2031-07-21 | 30 | 30-20
2031-07-22 | 30 | 30-20
2031-07-23 | 30 | 30-20
2031-07-24 | 30 | 30-20
2031-07-25 | 30 | 30-20
2031-07-26 | 30 | 30-20
2031-07-27 | 31 | 31-20
2031-07-28 | 31 | 31-20
2031-07-29 | 31 | 31-20
2031-07-30 | 31 | 31-20
2031-07-31 | 31 | 31-20
2031-08-01 | 31 | 31-20
2031-08-02 | 31 | 31-20
2031-08-03 | 32 | 32-20
2031-08-04 | 32 | 32-20
2031-08-05 | 32 | 32-20
2031-08-06 | 32 | 32-20
2031-08-07 | 32 | 32-20
2031-08-08 | 32 | 32-20
2031-08-09 | 32 | 32-20
2031-08-10 | 33 | 33-20
2031-08-11 | 33 | 33-20
2031-08-12 | 33 | 33-20
2031-08-13 | 33 | 33-20
2031-08-14 | 33 | 33-20
2031-08-15 | 33 | 33-20
2031-08-16 | 33 | 33-20
2031-08-17 | 34 | 34-20
2031-08-18 | 34 | 34-20
2031-08-19 | 34 | 34-20
2031-08-20 | 34 | 34-20
2031-08-21 | 34 | 34-20
2031-08-22 | 34 | 34-20
2031-08-23 | 34 | 34-20
2031-08-24 | 35 | 35-20
2031-08-25 | 35 | 35-20
2031-08-26 | 35 | 35-20
2031-08-27 | 35 | 35-20
2031-08-28 | 35 | 35-20
2031-08-29 | 35 | 35-20
2031-08-30 | 35 | 35-20
2031-08-31 | 36 | 36-20
2031-09-01 | 36 | 36-20
2031-09-02 | 36 | 36-20
2031-09-03 | 36 | 36-20
2031-09-04 | 36 | 36-20
2031-09-05 | 36 | 36-20
2031-09-06 | 36 | 36-20
2031-09-07 | 37 | 37-20
2031-09-08 | 37 | 37-20
2031-09-09 | 37 | 37-20
2031-09-10 | 37 | 37-20
2031-09-11 | 37 | 37-20
2031-09-12 | 37 | 37-20
2031-09-13 | 37 | 37-20
2031-09-14 | 38 | 38-20
2031-09-15 | 38 | 38-20
2031-09-16 | 38 | 38-20
2031-09-17 | 38 | 38-20
2031-09-18 | 38 | 38-20
2031-09-19 | 38 | 38-20
2031-09-20 | 38 | 38-20
2031-09-21 | 39 | 39-20
2031-09-22 | 39 | 39-20
2031-09-23 | 39 | 39-20
2031-09-24 | 39 | 39-20
2031-09-25 | 39 | 39-20
2031-09-26 | 39 | 39-20
2031-09-27 | 39 | 39-20
2031-09-28 | 40 | 40-20
2031-09-29 | 40 | 40-20
2031-09-30 | 40 | 40-20
2031-10-01 | 40 | 40-20
2031-10-02 | 40 | 40-20
2031-10-03 | 40 | 40-20
2031-10-04 | 40 | 40-20
2031-10-05 | 41 | 41-20
2031-10-06 | 41 | 41-20
2031-10-07 | 41 | 41-20
2031-10-08 | 41 | 41-20
2031-10-09 | 41 | 41-20
2031-10-10 | 41 | 41-20
2031-10-11 | 41 | 41-20
2031-10-12 | 42 | 42-20
2031-10-13 | 42 | 42-20
2031-10-14 | 42 | 42-20
2031-10-15 | 42 | 42-20
2031-10-16 | 42 | 42-20
2031-10-17 | 42 | 42-20
2031-10-18 | 42 | 42-20
2031-10-19 | 43 | 43-20
2031-10-20 | 43 | 43-20
2031-10-21 | 43 | 43-20
2031-10-22 | 43 | 43-20
2031-10-23 | 43 | 43-20
2031-10-24 | 43 | 43-20
2031-10-25 | 43 | 43-20
2031-10-26 | 44 | 44-20
2031-10-27 | 44 | 44-20
2031-10-28 | 44 | 44-20
2031-10-29 | 44 | 44-20
2031-10-30 | 44 | 44-20
2031-10-31 | 44 | 44-20
2031-11-01 | 44 | 44-20
2031-11-02 | 45 | 45-20
2031-11-03 | 45 | 45-20
2031-11-04 | 45 | 45-20
2031-11-05 | 45 | 45-20
2031-11-06 | 45 | 45-20
2031-11-07 | 45 | 45-20
2031-11-08 | 45 | 45-20
2031-11-09 | 46 | 46-20
2031-11-10 | 46 | 46-20
2031-11-11 | 46 | 46-20
2031-11-12 | 46 | 46-20
2031-11-13 | 46 | 46-20
2031-11-14 | 46 | 46-20
2031-11-15 | 46 | 46-20
2031-11-16 | 47 | 47-20
2031-11-17 | 47 | 47-20
2031-11-18 | 47 | 47-20
2031-11-19 | 47 | 47-20
2031-11-20 | 47 | 47-20
2031-11-21 | 47 | 47-20
2031-11-22 | 47 | 47-20
2031-11-23 | 48 | 48-20
2031-11-24 | 48 | 48-20
2031-11-25 | 48 | 48-20
2031-11-26 | 48 | 48-20
2031-11-27 | 48 | 48-20
2031-11-28 | 48 | 48-20
2031-11-29 | 48 | 48-20
2031-11-30 | 49 | 49-20
2031-12-01 | 49 | 49-20
2031-12-02 | 49 | 49-20
2031-12-03 | 49 | 49-20
2031-12-04 | 49 | 49-20
2031-12-05 | 49 | 49-20
2031-12-06 | 49 | 49-20
2031-12-07 | 50 | 50-20
2031-12-08 | 50 | 50-20
2031-12-09 | 50 | 50-20
2031-12-10 | 50 | 50-20
2031-12-11 | 50 | 50-20
2031-12-12 | 50 | 50-20
2031-12-13 | 50 | 50-20
2031-12-14 | 51 | 51-20
2031-12-15 | 51 | 51-20
2031-12-16 | 51 | 51-20
2031-12-17 | 51 | 51-20
2031-12-18 | 51 | 51-20
2031-12-19 | 51 | 51-20
2031-12-20 | 51 | 51-20
2031-12-21 | 52 | 52-20
2031-12-22 | 52 | 52-20
2031-12-23 | 52 | 52-20
2031-12-24 | 52 | 52-20
2031-12-25 | 52 | 52-20
2031-12-26 | 52 | 52-20
2031-12-27 | 52 | 52-20
2031-12-28 | 53 | 53-20
2031-12-29 | 53 | 53-20
2031-12-30 | 53 | 53-20
Formulas:
Week no. = WEEKNUM([Date])